## 2025
PROGRAMME TITLE | Accelerating Innovative Monitoring (AIM) For Forests
IMPACT | Impact Indicator 1 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
Long-term, transformational sustainable land-use management and reduction in deforestation, and GHG emissions from the forest & land-use sector are reduced in line with Paris Agreement & Sustainable Development Goals | Extent to which AIM is likely to lead to transformational change (KPI 15) | Planned | 3 | 3 | 3 | 4 | 4 | 5 | 5
|  | Achieved |  | 3 | 3 | 4
Source
KPI 15. Methodology developed with MEL advisor and FAO. Annex 4
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29 | Assumptions
Greater financial flows for forest countries and communities enabling governments to deliver sustainable development and meet NDCs, and enhance livelihoods of forest-dependent people | Volume & type of forest/land-use credits verified due to support from AIM (carbon credits,millions) | Planned | 0 | 0 | 25 | 50 | 75 | 100 | 130 | Donors (including the UK) remain committed to climate finance and carbon markets increasingly take up REDD+ Forest countries remain committed towards addressing deforestation, have strong institutions in place to access and manage climate finance, and their forest mitigation programmes are successful Related results-based and technical assistance programmes proceed successfully (FCPF, ISFL, REM, LEAF, UNREDD TA, GCF, NICFI, others) Forest countries continue with strong political commitment to sustainable land and forest management and using forest monitoring as its enabler.The international community’s efforts to address deforestation (e.g., through nature restoration and through transparent commodity supply chains) continue gaining momentum, leveraging strong information and data
|  |  |  | 21 | 64 | 64.0724
Source
Documentation of standards - country submissions to reputable carbon standards and reporting contexts
| Outcome Indicator 1.2 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| Number of countries supported to cover forests and land-use categories within UNFCCC reporting as a result of AIM (including against the NDCs) | Planned | 0 | 0 | 2 | 4 | 6 | 8 | 10
|  | Achieved | 0: 0; 2: 2; 4: 4
Source
Country submissions to the UNFCCC
| Outcome Indicator 1.3 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| Number of (a) individuals and (b) organisations supported by AIM (including women, IPs, CSOs, and local communities) - TA KPI 2 | Planned | (a) 0; (b) 0 | (a): 100; (b) 10 | (a) 2000; (b) 36 | (a) 3000; (b) 42 | (a) 4000; (b) 48 | (a) 5000; (b) 54 | (a) 6000; (b) 60
|  | Achieved | 0: (a) 1268; (b) 23; 2: (a) 3508 (b) 42; 4: (a) 11,983; (b) 53
Source
TA KPI 2 - UK TA KPI Methodology, developed with MEL advisor and FAO (Annex 3)
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
Increased and sustained conservation and reforestation of forests, sustainable land management as a result of enhanced data addressing technical, methodological and innovation gaps | Number of countries supported through AIM4Forests - TA KPI 1 | Planned | 0 | 6 | 13 | 15 | 20 | 20 | 20
|  | Achieved | 0: 10; 2: 14; 4: 19
Source
TA KPI 1 - UK TA KPI Methodology, developed with MEL advisor and FAO (Annex 2)
| Outcome Indicator 2.2 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| Number of institutions in AIM4Forests countries with improved capacities in utilising high-resolution satellites and data for forests and land use | Planned | 0 | 6 | 13 | 15 | 20 | 20 | 20
|  | Achieved | 0: 9; 2: 13; 4: 16
Source
Country work plans and annual country progress updates
| Outcome Indicator 2.3 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| Number of key methodological challenges overcome through alignment, innovation and deployment | Planned | 0 | 2 | 3 | 4 | 6 | 8 | 10
|  | Achieved | 0: 2; 2: 5; 4: 6
Source
Technical notes / tools / materials on methodological challenges. FAO Output 2.1
| Outcome Indicator 2.4 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| Number of countries reporting on nature restoration to the CBD, which received support from AIM4Forests. | Planned | N/A | N/A | 0 | 0 | 10 | 15 | 20
|  | Achieved | 4: 0
Source
NBSAPs, CBD 7th National Reports, Workshop reports
OUTCOME 3 | Outcome Indicator 3.1 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29 | Assumptions
REDD+ programmes operate more effectively, accurately and inclusively, results are delivered as a result of AIM, and increased consumer confidence on integrity of REDD+ credits | Number of REDD+ national/sub-national programmes actively supported by AIM4Forests on efforts to access climate finance | Planned | 0 | 6 | 9 | 12 | 15 | 15 | 15 | Related UK REDD+/ICF Programmes are implemented and successful (FCPF, ISFL, REM, LEAF, UNREDD TA) at all stages of REDD+ (readiness, implementation and results-based payments/benefits), including as a result of AIM Consumer appetite and interest for forest carbon credits remains
|  | Achieved | 0: 8; 2: 11; 4: 12
Source
Country workplans and annual country progress updates
| Outcome Indicator 3.2 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| Volume of emissions reduced or avoided in forestry and land use sector reported to reputable carbon standards and reporting contexts, by countries which receive active monitoring support from AIM4Forests, showcasing an innovative approach to managing land and forests (mTCO2e) | Planned | 0 | 0 | 40 | 80 | 120 | 150 | 200
|  | Achieved | 0: 36; 2: 79; 4: 142.0757
Source
Country submissions to reputable carbon standards and reporting contexts (will contribute to KPI 15)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29 | Assumptions
Forest Monitoring integrates latest technical knowledge as disseminated through open-access learning programmes, leverages innovative platforms and global datasets and is guided by aligned methodologies | Number of open-access e-learning modules, online course and platforms created by AIM4Forests | Planned | 0 | 2 | 9 | 11 | 13 | 15 | 15 | AIM4Forests technical solutions effectively meet country demand while leveraging innovation AIM4Forests identifies those issues that matter most for delivering methodological knowledge
|  | Achieved | 0: 6; 2: 9; 4: 11
Source
FAO Results Indicator 1.1 - course/platforms available
| Output Indicator 1.2 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| Number of users of e-learning modules, online course and platforms created by AIM4Forests | Planned | 0 users | 100 | 8000 | 10000 | 14000 | 16000 | 18000
|  | Achieved | 0: 4677; 2: 10897; 4: 18807
Source
FAO Results Indicator 1.2 - platform metrics
| Output Indicator 1.3 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| % of participants at e-learning courses indicating that they (a) acquired new knowledge; (b) they will apply the new knowledge | Planned | 0 | (a) 75%; (b) 75% | (a) 75%; (b) 75% | (a) 75%; (b) 75% | (a) 75%; (b) 75% | (a) 75%; (b) 75% | (a) 75%; (b) 75%
|  | Achieved | 0: (a) 98%; (b) 98%; 2: (a) 99%; (b) 99%; 4: (a) 98%; (b) 97%
Source
FAO Results Indicator 1.3 - platform metrics, surveys
| Output Indicator 1.4 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| Number of emerging technologies, tools and innovative solutions developed/supported to deployment by AIM4Forests | Planned | 0 | 0 | 2 | 4 | 6 | 8 | 10
|  | Achieved | 0: 0; 2: 4; 4: 6
Source
FAO Results Indicator 1.4 - tools available
| Output Indicator 1.5 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| Number of total users to new technologies, tools, and innovative solutions | Planned | 0 | 100 | 200 | 400 | 600 | 800 | 1000
|  | Achieved | 0: N/A; 2: 588; 4: 6373
Source
Platform metrics, surveys for gathering qualitative data
| Output Indicator 1.6 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| Number of AIM-hosted (a) technical meetings/webinars on methodological challenges, (b) publications on methodological challenges | Planned | 0 | (a) 2; (b) 2 | (a) 3; (b) 3 | (a) 4; (b) 4 | (a) 6; (b) 6 | (a) 8; (b) 8 | (a) 10; (b) 10
|  | Achieved | 0: (a) 2; (b) 1; 2: (a) 7; (b) 5; 4: (a) 11; (b) 8
Source
FAO Results Indicator 1.5 - meeting reports/ publications
| Output Indicator 1.7 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| Global-scale dataset on nature restoration | Planned | N/A | N/A | 0 | 0 | 1 | 1 | 1
|  | Achieved | 4: 0
Source
FERM nature restoration dashboard
| Output Indicator 1.8 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| Number of countries involved in co-development of the global-scale dataset on nature restoration through participation in regional workshops. | Planned | N/A | N/A | 0 | 20 | 30 | 40 | 45
|  | Achieved | 4: 29
Source
Workshop reports
IMPACT WEIGHTING (%) | Output Indicator 1.9 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29 | RISK RATING
40% | Number of countries involved in co-development of the global-scale dataset on nature restoration, which include nature restoration in their KMGBF reporting 2026. | Planned | N/A | N/A | 0 | 0 | 10 | 15 | 20 | Minor
|  | Achieved | 4: 0
Source
NBSAPs, CBD 7th National Reports, workshop reports
OUTPUT 2 | Output Indicator 2.1 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29 | Assumptions
Forest communities and Indigenous Peoples are empowered to participate in forest monitoring and MRV for emerging carbon standards through a community of practice | Number of (a) events showcasing IPLC stewardship; (b) IP-led community of practice events | Planned | 0 | (a) 0; (b) 1 | (a) 1; (b) 2 | (a) 3; (b) 4 | (a) 3; (b) 4 | (a) 4; (b) 4 | (a) 5; (b) 5 | National policies and legal frameworks enable cross-sectoral collaboration and are receptive towards engaging empowered Indigenous Peoples and local communities in forest monitoring Emerging requirements in carbon markets and transparent commodity value chains provide a role for Indigenous Peoples and local communities
|  | Achieved | 0: 0; 2: (a) 2; (b) 0; 4: (a) 6; (b) 4
Source
FAO Results Indicator 2.1 - meeting notes/ event recordings
| Output Indicator 2.2 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| Number of attendees at IP-led community of practice events and training events, specifically (a) the total number of attendees; and (b) % of women attendees; and (c) the number of countries represented | Planned | 0 | 0 | (a) 20; (b) 50%; (c)6 | (a) 40; (b) 50%; (c) 8 | (a) 60; (b) 50%; (c) 8 | (a) 80 (b) 50% (c) 10 | (a) 100; (b) 50%; (c)10
|  | Achieved | 0: 0; 2: 0; 4: (a) 165; (b) 31%; (b) 21
Source
FAO Results Indicator 2.2- Event reports
| Output Indicator 2.3 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| IP-led community of practice events and training events leading to knowledge growth, specifically: (a) percentage of participants indicating they acquired new knowledge; (b) percentage of participants indicating they will apply the new knowledge; and (c) indication from periodic surveys of growing technical knowledge on forest monitoring and MRV. | Planned | 0 | 0 | (a) 75%; (b) 75%; (c) Yes | (a) 75%; (b) 75%; (c) Yes | (a) 75%; (b) 75%; (c) Yes | (a) 75%; (b) 75%; (c) Yes | (a) 75%; (b) 75%; (c) Yes
|  | Achieved | 0: 0; 2: 0; 4: (a) 100%; (b) 100%
Source
FAO Results Indicator 2.3 - technical material available / deployments
| Output Indicator 2.4 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| Integration of IP&LC land indicators in international reporting frameworks. | Planned | 0 | 0 | 0 | 1 | 1 | 1 | 1
|  | Achieved | 0: 0; 2: 0; 4: 1
Source
Decisions by international bodies
IMPACT WEIGHTING (%) | Output Indicator 2.5 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29 | RISK RATING
20% | Assessment on "to what extent is AIM4Forests contributing to enhancing the role of IP&LC within national forest monitoring systems and forest mitigation efforts in target countries?" | Planned | 3 | 3 | 3 | 3 | 4 | 4 | 5 | Moderate
|  | Achieved | 0: 1 - no focus group discussion implemented in 2023, as the IP&LC work package will kick off in 2024; 2: 3; 4: 3
Source
Scoring based on methodology outlined in KPI15 methodology (Annex 4). Contributes to KPI 15 Score 1: Substantial evidence suggests that Aim4Forests is not making a positive contribution; Score 2: Partial evidence suggests that Aim4Forests is not making a positive contribution; Score 3: Not enough evidence yet to assess, or the balance of evidence is inconclusive; Score 4: Partial evidence suggests that Aim4Forests is making a positive contribution; Score 5: Substantial evidence suggests that Aim4Forests is making a positive contribution
OUTPUT 3 | Output Indicator 3.1 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29 | Assumptions
Countries address technical and functional gaps and develop forest monitoring systems that are sustainable, robust, relevant to policy priorities and accessible to all. | Number of countries (a) engaging with the CLP Programme of Support to initiate the country-led planning process; and (b) with progress towards institutionalized forest monitoring through a country-led planning process with strong momentum and full country ownership. | Planned | 0 | (a) 2; (b) 0 | (a) 6; (b) 2 | (a) 10; (b) 4 | (a) 14; (b) 7 | (a) 18; (b) 9 | (a) 20; (b) 12 | Countries are committed to strengthening their technical and functional forest monitoring capacity and taking on board innovative technical solutions AIM4Forests has access to needed funds and human resources to provide technical assistance
|  | Achieved | 0: (a) 3; (b) 0; 2: (a) 6; (b) 2
Source
FAO Results Indicator 3.1 - CLP documentation
| Output Indicator 3.2 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| Number of technical support providers using the country-led planning process (other than FAO through AIM4Forests) | Planned | 0 | 1 | 2 | 3 | 4 | 5 | 5
|  | Achieved | 1: 0; 2: 2
Source
FAO Results Indicator 3.2 - CLP workshop reports
| Output Indicator 3.3 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| Number of countries with technical assistance packages deployed in the context of (a) data-driven resource management, (b) high-quality measurement, reporting and verification of mitigation actions, (c) transparent commodity value chains, (d) tracking nature restoration progress, (e) any of the above. | Planned | (a) 0; (b) 0; (c) 0; (d) 0; (e) 0 | (a) 3; (b) 8; (c) 2; (d) 0; (e) 6 | (a) 8; (b) 9; (c) 4; (d) 4; (e) 12 | (a) 10; (b) 12; (c) 4; (d) 5; (e) 14 | (a) 10; (b) 15; (c) 4; (d) 5; (e) 16 | (a) 10; (b) 15; (c) 4; (d) 5; (e) 18 | (a) 10; (b) 15; (c) 4; (d) 5; (e) 20
|  | Achieved | 1: (e)9; 2: (e) 13
Source
FAO Results Indicator 3.3 - Technical assistance packages / country annual workplan progress
| Output Indicator 3.4 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29
| Number of countries (a) with capacity assessments conducted in the context of country technical assistance and (b) with integrated capacity development trajectories guiding capacity development. | Planned | (a) 0; (b) 0 | (a) 0; (b) 0 | (a) 10; (b) 3 | (a) 18); (b) 5 | (a) 20; (b) 7 | (a) 20; (b) 10 | (a) 20; (b) 12
|  | Achieved | 2: (a) 15
Source
FAO Results Indicator 3.4 - CLP documentation
IMPACT WEIGHTING (%) | Output Indicator 3.5 |  | Baseline: FY22/23 | Milestone 1: FY23/24 | Milestone 2: FY24/25 | Milestone 3: FY25/26 | Milestone 4: FY26/27 | Milestone: FY27/28 | Target: FY28/29 | RISK RATING
40% | Number of (sub)national forest and climate policies and legislation informed by country technical assistance. | Planned | N/A | N/A | N/A | 2 | 4 | 6 | 8 | Moderate
Achieved | bar: 0
Source
NB. This indicator is inspired by TA KPI 3 and tracks concrete contributions made by work under Outputs 4 and 5 to anchor forest monitoring in government-led policy and legislative processes, including in those cases where direct attribution could be hard to establish.
Note on F130: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: does this need to be 3 ( too early to assess) or NA?