## Logframe
PROJECT TITLE | BioCarbon Fund Initiative for Sustainable Forest Landscapes (BioCF ISFL)
IMPACT | Impact Indicator 1 |  | Baseline: FY14 | Milestone 1: FY19 | Milestone 2: FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | Target: FY31
Sustainably managed forest and agricultural landscapes contribute to low carbon development and achievement of Paris Agreement climate goals. | KPI 15 - Extent to which ISFL is likely to lead to transformational change | Planned |  | N/A | N/A | N/A | N/A | N/A | 4 | 4 | 4 | 4 | 5 | 5 | 5 - ISFL has worked at scale across a integrated land-use approach to - foster local political will & ownership of emissions reductions programmes; drive technical capacity development and support in ISFL countries; leverage incentives for change (mobilising public and private finance); and provides evidence of long-term sustainability of improved land-use.
|  | Achieved |  |  |  | FY23: 4; FY24: 4
Source
Potential to incorporate WB indicator: T1.3 (non-ISFL programmes replicate or incorpoate ISFL approaches in their programme design)
Methodology defined in Results Note Collection
Results will be reported on each year, and discussed
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline: FY14 | Milestone 1: FY19 | Milestone 2: FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | Target: FY31 | Assumptions
The BioCF ISFL has improved forest and agricultural land management and land use, contributed to reduced emissions from forest and agricultural ecosystems (including REDD+) and protected biodiversity through integrated low carbon jurisdictional development pathways, equitable distribution of benefits and mobilisation of investment through partnerships between public and private sectors. | Net change in greenhouse gas emissions (tCO2e) tonnes of greenhouse gas emissions reduced or avoided as a result of ISFL | Planned |  | To be developed once ERPAs finalised | To be developed once ERPAs finalised | To be developed once ERPAs finalised | To be developed once ERPAs finalised | To be developed once ERPAs finalised | 34674493 | 52707647 | 71030264 | 91685858 | 114743070 | 126886013 | 126886013 | External disruptive factors (such as macroeconomic, political, environmental, and anthropogenic factors) are minimal ISFL program countries have adequate financial and technical capacity Relevant strategies and policies adequately support, or at least do not contradict, the program’s objectives and are adequately governed and funded. This includes relevant sectoral policies, as well as the impact that other sector strategies and policies may have on forests and land use (i.e., agriculture, energy, mining, transportation, etc.)
|  | Achieved |  |  | Not reporting | FY22: Not reporting; FY23: 0; FY24: 0; FY25: 15078897
Source
T1.2 (greenhouse gas emission reduction in ISFL programme areas
KPI6 (Net change in GHG in tCO2e reduced or avoided)
NOTES: - FY27, FY28, FY29 and FY30 milestones do not align with WB milestones (which have not been set). We calculated interim milestones using the emission reductions estimates outlined in the ERPDs.
| Outcome Indicator 1.2 |  | Baseline: FY14 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | Target: FY31
| a) Decrease in area (ha) of conversions from forest to other land uses in ISFL programme areas and b) area (ha) of land use converted to forest in ISFL programme areas | Planned |  | 1209 | 4496 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
|  | Achieved |  | 0 | FY21: Not reporting; FY22: 1699; FY23: 1699; FY24: 2114; FY25: a) Decrease cannot be calculated until more results are reported (area of conversions from forest to toher land uses was 16,012) b) 29,056
Source
T2.O1.2a: Area of conversions from forest to other land uses in ISFL program areas T2.O1.2b: Area of other land uses converted to forest in ISFL program areas
KPI 8 (Number of ha where deforestation and degradation have been avoided through ICF support)
NOTES: - In FY25, this indicator was changed from "Area (ha) of avoided deforestation compared to a reference level in ISFL programme areas" to "a) Decrease in area (ha) of conversions from forest to other land uses in ISFL programme areas and b) area (ha) of land use converted to forest in ISFL programme areas". This reflects a change made by WB from T2.O1.2, "Reduction in deforestation compared to a reference level in ISFL programme areas" to the above two indicators T2.O1.2a and T2.O1.2b. This change was made as only the Zambia grant programme, which closed in 2024, reported on the former T2.O1.2 indicator.
| Outcome Indicator 1.3 |  | Baseline: FY14 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | Target: FY31
| Volume of finance mobilised for climate change purposes as a result of ISFL (disaggregated for non-ODA public finance and private finance) | Planned |  | N/A | N/A | N/A | N/A | N/A | For profit: $10,750,000 Not for profit: $14,500,000 | For profit: $17,500,000 Not for profit: $23,000,000 | For profit: $24,250,000 Not for profit: $31,500,000 | For profit: $31,000,000 Not for profit: $40,000,000 | For profit: $31,000,000 Not for profit: $40,000,000 | For profit: $31,000,000 Not for profit: $40,000,000 | For-profit: $31m Not-for-profit: $40m
|  | Achieved |  |  | FY21: For-profit private: $4m; FY22: For-profit private: $4m; FY23: For-profit private: $4.5m Not-for-profit: $111.7; FY24: For-profit private: $9.5m Not-for-profit: $170.55m; FY25: For profit: $9,500,000 Not for profit: $212,550,000
[5 empty] | Not-for-profit (public or private): $94.78m | Not-for-profit (public or private): $104.28m
Source
T2.O3.1 and T2.O3.2 (volume of not-for-profit and for profit finance (public/private) leveraged to contribute to ISFL objectives)
KPI 11 & 12 (Volume of public / private finance mobilised for climate change purposed as a result of ICF funding)
NOTES: - Targets are set for ER programmes, but not grant programmes, but results from both are reported. For the purpose of Annual Review reporting, the programme manager should request disaggregated data from the WB. - WB will not set targets, but will report annually. Milestones are only set for countries with signed ERPAs (Zambia and Ethiopia). DESNZ has calculated FY25-FY27 targets using the baselines and EOP targets set out in Zambia and Ethiopia's ER programme PADs and a linear trend. Targets will be updated when other countries' ERPAs are signed.
| Outcome Indicator 1.4 |  | Baseline: FY14 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | Target: FY31
| Extent to which ISFL has influenced REDD+ Country Participants' national approaches to sustainable forest resource management and land-use (including among women, women's groups, IPs, CSOs, local communities) | Planned |  | 0 | At least six reforms in forest and land-use policy, legislation or other regulations that an ISFL programme has explicitly supported. | At least seven reforms in forest and land-use policy, legislation or other regulations that an ISLF programme has explicitly supported. There is evidence of such policies, strategies and plans having a clear recognition for social inclusion (gender, IPs, local communities) and a lasting impact beyond the scope of the programme. | At least eight reforms in forest and land-use policy, legislation or other regulations that an ISLF programme has explicitly supported. There is evidence of such policies, strategies and plans having a clear recognition for social inclusion (gender, IPs, local communities) and a lasting impact beyond the scope of the programme. | There is evidence that ISFL practices and approaches have influenced policies, strategies, plans and other elements of country frameworks for sustainable forest and land-use management in at least two countries, with at least ten reforms in forest and land-use policy, legislation or other regulations that an ISLF programme has explicitly supported. There is evidence of such policies, strategies and plans having a clear recognition for social inclusion (gender, IPs, local communities) and a lasting impact beyond the scope of the programme | There is evidence that ISFL practices and approaches have influenced policies, strategies, plans and other elements of country frameworks for sustainable forest and land-use management in at least three countries, with at least twelve reforms in forest and land-use policy, legislation or other regulations that an ISLF programme has explicitly supported. There is evidence of such policies, strategies and plans having a clear recognition for social inclusion (gender, IPs, local communities) and a lasting impact beyond the scope of the programme | There is evidence that ISFL practices and approaches have influenced policies, strategies, plans and other elements of country frameworks for sustainable forest and land-use management in at least three countries, with at least fourteen reforms in forest and land-use policy, legislation or other regulations that an ISLF programme has explicitly supported. There is evidence of such policies, strategies and plans having a clear recognition for social inclusion (gender, IPs, local communities) and a lasting impact beyond the scope of the programme. | There is evidence that ISFL practices and approaches have influenced policies, strategies, plans and other elements of country frameworks for sustainable forest and land-use management in at least four countries, with at least fourteen reforms in forest and land-use policy, legislation or other regulations that an ISLF programme has explicitly supported. There is evidence of such policies, strategies and plans having a clear recognition for social inclusion (gender, IPs, local communities) and a lasting impact beyond the scope of the programme | There is evidence that ISFL practices and approaches have further influenced policies, strategies, plans and other elements of country frameworks for sustainable forest and land-use management in at least five countries, with at least fourteen reforms in forest and land-use policy, legislation or other regulations that an ISLF programme has explicitly supported. There is evidence of such policies, strategies and plans having a clear recognition for social inclusion (gender, IPs, local communities) and a lasting impact beyond the scope of the programme | There is evidence that ISFL practices and approaches have further influenced policies, strategies, plans and other elements of country frameworks for sustainable forest and land-use management in at least five countries, with at least fourteen reforms in forest and land-use policy, legislation or other regulations that an ISLF programme has explicitly supported. There is evidence of such policies, strategies and plans having a clear recognition for social inclusion (gender, IPs, local communities) and a lasting impact beyond the scope of the programme | There is evidence that ISFL practices and approaches have further influenced policies, strategies, plans and other elements of country frameworks for sustainable forest and land-use management in at least five countries, with at least fourteen reforms in forest and land-use policy, legislation or other regulations that an ISLF programme has explicitly supported. There is evidence of such policies, strategies and plans having a clear recognition for social inclusion (gender, IPs, local communities) and a lasting impact beyond the scope of the programme | There is evidence that ISFL practices and approaches have influenced policies, strategies, plans and other elements of country frameworks for sustainable forest and land-use management in at least five countries, with at least fourteen reforms in forest and land-use policy, legislation or other regulations that an ISLF programme has explicitly supported. There is evidence of such policies, strategies and plans having a clear recognition for social inclusion (gender, IPs, local communities) and a lasting impact beyond the scope of the programme.
|  | Achieved |  |  | FY21: 1; FY22: Non-ISFL programme replication: N/A; FY23: Non-ISFL programme replication: N/A Reforms: 28; FY24: Non-ISFL programme replication: 5 Reforms: 34; FY25: Non-ISFL programme replication: 5 Reforms: 35
Reforms: 23
Source
Qualitative adaptation of WB MEL indicators:
T1.3 - Non-ISFL programmes replicate or incorporate ISFL approaches in their programme design (will be reported on through ISFL's 2nd evaluation (FY23))
T2.O1.e - Reforms (new legislation, regulations or decrees, or removal of obstructive existing policies or regulations) in forest and land-use policy, legislation or other regulations to which ISFL has contribute to, and as a result of ISFL support)
Adaptation of KPI13 (Integration of climate change in national planning as a result of ICF support)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline: FY14 | Milestone 1: FY19 | Milestone 2: FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 |  | Target: FY31 | Assumptions
Jurisdictional-scale Emissions Reduction Programmes for reducing emissions and improving land management are planned and implemented | Total land area (ha) under sustainable landscape management (a) plans and (b) practices as a result of ISFL support, including where relevant: foresty, agriculture, other (CRI, FAP) | Planned |  | (a) 38,977 (b) 5,725 | (a) 1,890,359 (b) 48,707 | (a) 11,089,727 (b) 155,063 | (a) 13,166,122 (b) 163,584 | (a) 15,242,518 (b) 371,100 | (a) 17,318,913 (b) 441,998 | (a) 19,395,308 (b) 512,895 | (a) 19,395,308 (b) 583,792 | (a) 19,395,308 (b) 654,690 | (a) 19,395,308 (b) 725,587 |  | (a) 19,395,308 (b) 725,587 | ISFL program countries have adequate financial and technical capacity
| Impact Weighting: 22.5% | Achieved |  | - | (a) 9,013,332 (b) 146,541 | FY22: (a) 19,478,188 (b) 250,812; FY23: (a) 12,163,967 (b) 300,203; FY24: (a) 13,632,166 (b) 374,547; FY25: (a) 13,607,436 (b) 361,039
Source
|  | T2.O1.a (Total land area brought under sustainable management plans as a result of ISFL support, including where relevant: forest plans, biodiversity plans, land use plans - ha) | [13 empty] | Relevant strategies and policies adequately support, or at least do not contradict, the program’s objectives and are adequately governed and funded. This includes relevant sectoral policies, as well as the impact that other sector strategies and policies may have on forests and land use (i.e., agriculture, energy, mining, transportation, etc.)
T2.O1.b (Total land area under sustainable landscape management practices as a result of ISFL support, including where relevant: foresty, agriculture, other (CRI, FAP)) - corresponds to KPI17
NOTES: - For FY19; FY21; FY31 - milestones/targets set with WB Programme Logframe. For FY22 and FY23 interim milestones were set based on achieved results and the 2026 target at the time through a simple linear trajectory for years 2022 - 2026 to aid with scoring components for Annual Review processes. - In FY24, the WB revised the FY31 target upwards to reflect additional funding given to Zambia. For FY24-FY29, DESNZ has set interim milestones based on achieved results in FY23 and the FY31 target through a simple linear trajectory for years 2024 - 2029 (the World Bank expect the FY31 target to be achieved in FY29).
| Output Indicator 1.2 |  | Baseline: FY14 | Milestone 1: FY19 | Milestone 2: FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | Target: FY31
| Amount of disbursement for ER payments ($, cumulative) | Planned |  | None set | To be developed post-ERPA signature | To be developed post-ERPA signature | To be developed post-ERPA signature | To be developed post-ERPA signature | 10000000 | 19980000 | 24960000 | 24960000 | 34920000 | 34920000 | 45000000
|  | Achieved |  |  | N/A | FY22: N/A; FY23: N/A; FY24: 0; FY25: 0
| Impact Weighting: 22.5% | Source
T2.O2.b (volume of ER purcahses from ISFL programmes in USD)
NOTES: - FY25-FY30 milestones do not align with WB milestones (which have not been set). Milestones have been caclulated on the expectation that ER payments will be made within 18 months of the end of each reporting period. These milestones only take into account the Ethiopia Phase 1 and Zambia ERPA and will updated once other ERPAs are signed.
| Output Indicator 1.3 (CLOSED) |  | Baseline: FY14 | Milestone 1: FY20 | FY21 | FY22: FY22; FY23: FY23; FY24: FY24 | Target: FY26
| Number of workshops and funded technical studies completed to prepare an ISFL programme | Planned | 0 | 53 (23 technical studies; 30 workshops) | N/A | FY22: 55 (25 technical studies; 30 workshops); FY23: N/A; FY24: N/A | 62 (32 technical studies; 30 workshops)
|  | Achieved |  |  | 121 (44 technical studies; 77 workshops) | FY22: (62 technical studies; 164 workshops); FY23: 612 (91 technical studies; 521 workshops); FY24: 816 (132 technical studies, 684 workshops)
| Impact Weighting: 15% 0% (close indicator) | Source
For FY19; FY21; FY26; FY31 - milestones/targets set with WB Programme Logframe.
CC.P.1 Number of funded technical studies completed
CC.P.4 Number of workshops held to prepare an ISFL programme
| Output Indicator 1.3 |  | Baseline: FY14 | Milestone 1: FY19 | Milestone 2: FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | Target: FY31
| Number of ERPDs completed (of which number of ERPAs signed) | Planned |  | 1 (0) | 4 (3) | 4 (1) | 5 (5) | 5 (5) | 5 (5) | 5 (5) | 5 (5) | 5 (5) | 5 (5) | 5 (5) | 5 (5)
|  | Achieved |  | 0 | 0 (0) | FY22: 1 (0); FY23: 2 (1); FY24: 5 (2); FY25: 5 (2)
| Impact Weighting: 22.5% | Source
T3.4 - Number of emission reductions purchase agreements signed
CC.I.2 - Number of Emissions Reductions Programme Documents completed
NOTES: - FY22 diverges from WB programme logframe, as we have conducted an internal re-baseline to account for accumulated delays & COVID-19 impacts
| Output Indicator 1.4 |  | Baseline: FY14 | Milestone 1: FY19 | Milestone 2: FY21 | FY22: FY22; FY23: FY23; FY24: FY24; FY25: FY25 | Target: FY26
| Number of ERPDs approved with subsequent phases that include at least 2 non-forest related AFOLU subcategories, and which demonstrate improved data quality over time. (e.g. livestock, soils, cropland, grassland, wetlands etc) | Planned |  | None set | 65% | FY22: 65%; FY23: 65%; FY24: 80%; FY25: 80% | 80%
|  | Achieved |  |  | 0% | FY22: 100%; FY24: 100%; FY25: 100%
| Impact Weighting: 22.5% | Source
Country ERPDs (cumulative %) - to take into consideration of subsequent phases of ERPDs being approved/ adapted and inclusive of further land-use sub-categories
IMPACT WEIGHTING (%) | Output Indicator 1.5 |  | Baseline: FY14 | Milestone 1: FY19 | Milestone 2: FY21 | FY22 | FY23 | FY24 | FY25 | FY25 | FY25 | FY25 | FY25 | FY25 | Target: FY26 | RISK RATING
50 | a) Number of approved ERPDs which directly reference National Biodiversity Strategies and Action Plans (NBSAPs), related regional and/or sub-national strategies and plans, and which include targets that demonstrate biodiveristy co-benefits; | Planned |  | None set | (a) 4 (b) 4 | (a) 4 (b) 4 | (a) 5 (b) 5 | (a) 5 (b) 5 | (a) 5 (b) 5 | (a) 5 (b) 5 | (a) 5 (b) 5 | (a) 5 (b) 5 | (a) 5 (b) 5 | (a) 5 (b) 5 | (a) 5 (b) 5
| b) Number of programmes that are designing or implementing biodiversity-friendly management strategies | Achieved |  |  | (a) 0 (b) 3 | FY22: (a) 1 (b) 4; FY23: (a) 1 (b) 4; FY24: (a) 1 (b) 4; FY25: (a) 3 (b) 4
| Impact Weighting: 10% | Source
Country ERPDs (cumulative %) - CC.I.3
Country programmes (number) - CC.I.5
NOTES: - Biodiversity indicators to be discussed prior when the biodiversity pilot is operational in Colombia.
OUTPUT 2 | Output Indicator 2.1 |  | Baseline: FY14 | Milestone 1: FY19 | Milestone 2: FY21 | FY22: FY22; FY23: FY23; FY24: FY24; FY25: FY25; FY26: FY26 | Target: FY31 | Assumptions
Jurisdictions have improved capacity and capability to manage land sustainably, deliver benefits equitably to land-users and contribute positively to local socio-economic development and protecting biodiversity | Land users who have adopted sustainable land management practices (% women) as a result of ISFL support, including in the following sectors where relevant: forestry, agriculture, other | Planned |  | 18,383 (average 18%) | 56,839 (average 23%) | FY22: 88738; FY23: 89249; FY24: 89760; FY25: 90271; FY26: 90,782 (average 30%) | 90,782 (average 30%) | ISFL program countries have adequate financial and technical capacity
| Impact Weighting: 33.3% | Achieved |  |  | 88,228 (22%) | FY22: 100,877 (23%); FY23: 148,802 (33%); FY24: 143,031 (36%); FY25: 143,785 (36%)
|  | Source | [13 empty] | Different stakeholders involved in the program’s design and implementation have been appropriately engaged
T2.O1.5 Land users who have adopted sustainable land management practices (% women) as a result of ISFL support, including in the following sectors where relevant: forestry, agriculture, other
NOTES: - FY22, FY23, FY24, FY25 milestones do not align with WB milestones (which have not been set). A linear trend has been used to calculate these results, taking achieved results from FY21 and final FY26 target. These will be used to aid UK Annual Review reporting. - Gender disaggregation is not reported by Mexico to WB for this indicator.
| Output Indicator 2.2 |  | Baseline: FY14 | Milestone 1: FY20 | Milestone 2: FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | Appropriate incentives are tailored to relevant stakeholders involved in the program, in a manner that encourages behavioral changes to fulfill the program’s objectives
| Volume of grants disbursed to ISFL programmes (US$ mill) | Planned | 0 | 30.5 | N/A | 33.6 | 42.6 | 55.98 | 63.52 | 69.69 | 74.55 | 78.14 | 80.53 | 81.84 | 82.2
| Impact Weighting: 33.3% | Achieved |  |  | FY21: 24.67 | FY22: 35.6; FY23: 47.03; FY24: 59.9; FY25: 69.3
Source
T3.2 (Volume of grants disbursed to ISFL programmes) - Data source: Official ISFL documents for BioCFPlus
NOTES: - FY22-FY30 milestones diverge from WB programme logframe. For FY22-FY25, we conducted an internal re-baseline to account for accumulated delays & COVID-19 impacts. We utilised a linear trend from FY21 results to FY26 target to calculate milestones for Annual Review reporting. In FY24, we re-calcuated a trend for FY24-FY30, to take into account additional grant funding provided to Zambia. For this, we used a quadratic trend from FY23 result to FY31 target to calculate milestones, as all programmes except Zambia expect to have disbursed all grant funding by FY26.
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline: FY14 | Milestone 1: FY19 | Milestone 2: FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | RISK RATING
25 | Number of communities or other organizations that have received benefits (assets and/or services) from emission reductions payments | Planned |  | None set | To be developed post-ERPD/BSP | To be developed post-ERPD/BSP | To be developed post-ERPD/BSP | 0 | 0 | 205 | 615 | 1127 | 1536 | 1844 | 2049 | Moderate
|  | Achieved |  |  | N/A | FY22: N/A; FY23: N/A; FY24: 0; FY25: 0
Source
| Impact Weighting: 33.3% | T2.O2.1 (Number of communities or other organizations that have received benefits (assets and/or services) from emission reductions payments)
NOTE: - Only countries with signed ERPAs (Ethiopia and Zambia) are reporting on this. FY25-FY30 milestones do not align with WB milestones (which have not been set). The final EOP target is for both Ethiopia and Zambia, but only Zambia has provided interim milestones. We added interim milestones by scaling up Zambia’s known milestones (FY26-FY28) to match the full programme’s EOP target, then extended that growth pattern across FY25-FY31.
OUTPUT 3 | Output Indicator 3.1 |  | Baseline: FY14 | Milestone 1: FY19 | Milestone 2: FY21 | FY22 | FY23 | FY24 | FY25 | FY26 |  |  |  |  | FY31 | Assumptions
Replicable and scalable models of public-private or private investment in place that enable sustainable revenue streams for local communities, protection of biodiversity and improved land-use management through sustainable practices | Number of people in private sector schemes adopting sustainable practices (disaggregated by gender) | Planned |  | To be developed | To be developed | To be developed | To be developed | 7954 | 268484 | 511603 |  |  |  |  | 511603
|  | Achieved |  |  |  | FY22: N/A; FY23: 6,305 (33%); FY24: 25,365 (36%); FY25: 28,304 (36%)
| Impact Weighting: 40% | Source
T2.O3.3.
Gender disaggregation will be reported on (but no targets set)
NOTES: - FY24 and FY25 milestones do not align with WB milestones (which have not been set). A linear trend has been used to calculate these results, taking achieved results from FY23 and final FY26 target. - In FY24, the WB revised the FY26/EOP target to account for additional funding provided to Zambia in FY23. As a result, we updated the FY25 target in line with this revision using a linear trend.
| Output Indicator 3.2 |  | Baseline: FY14 | Milestone 1: FY19 | Milestone 2: FY21 | FY22 | FY23 | FY24 | FY25 | FY26 |  |  |  |  | Target: FY31
| Number of partnerships established with: (a) for-profit private sector organisations; & (b) not-for-profit public or private organisation, due to ISFL support | Planned |  | (a) 3 (b) 3 | (a) 5 (b) 4 | (a) 17 (b) 17 | (a) 20 (b) 17 | (a) 23 (b) 17 | (a) 26 (b) 17 | (a) 29 (b) 17 |  |  |  |  | (a) 29 (b) 17
| Impact Weighting: 30% | Achieved |  |  | (a) 14 (b) 17 | FY22: (a) 20 (b) 31; FY23: (a) 46 (b) 36; FY24: (a) 74 (b) 74; FY25: (a) 75 (b) 74
Source
T2.O3.a & T2.O3.b
NOTES: - FY22, FY23, FY24, FY25, FY26 milestones do not align with WB milestones (which have not been set). A linear trend has been used to calculate these results, taking achieved results from FY21 and the WB final FY26 target. These will be used to aid UK Annual Review reporting. For (b) - we would encourage WB to re-baseline the target upward as it has already overachieved
| Output Indicator 3.3 |  | Baseline: FY14 | Milestone 1: FY19 | Milestone 2: FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | Target: FY31
| Number of engagements established with: (a) for-profit private sector organisations; & (b) not-for-profit public or private organisation, due to ISFL support | Planned |  | (a) 4 (b) 2 | (a) 8 (b) 4 | N/A | N/A | N/A | N/A | (a) 12 (b) 8 | (a) 12 (b) 8 | (a) 12 (b) 8 | (a) 12 (b) 8 | (a) 12 (b) 8 | (a) 12 (b) 8
|  | Achieved |  |  | (a) 11 (b) 26 | FY22: (a) 30 (b) 38; FY23: (a) 21 (b) 38; FY24: (a) 26 (b) 54; FY25: (a) 26 (b) 54
| Impact Weighting: 30% | Source
T2.O3.c & T2.O3.d
IMPACT WEIGHTING (%) | Output Indicator 3.4 |  | Baseline: FY22 |  |  |  | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | Target: FY31 | RISK RATING
25 | Number of businesses/private sector actors ensuring environmental and social benefits are created, sustainable, and scaled as a result of ISFL support | Planned |  |  |  |  | Demonstrable evidence that business/private sector actors have ensured env and social benefits as a result of ISFL support | Evidence that the amount of benefits created have increased from the previous year | Evidence that the amount of benefits created have increased from the previous year | Evidence that the amount of benefits created have increased from the previous year | Evidence that the amount of benefits created have increased from the previous year | Evidence that the amount of benefits created have increased from the previous year | Evidence that the amount of benefits created have increased from the previous year | Evidence that the amount of benefits created have increased from the previous year | Businesses/private sector actors have ensured environmental and social benefits are created, sustainable, and scaled as a result of ISFL support | Moderate
|  | Achieved |  |  |  |  | FY23: N/A; FY24: N/A; FY25: N/A
Source
T2.O3.4
| Impact Weighting: 0% | NOTES: - Output 3 weightings will be revised when indicator 3.4 is reported on. - In FY26, WB and DESNZ will discuss making this a qualitative indicator. For the purposes of the 2024/25 Annual Review where this indicator will not be reported on, the programme manager should make a qualitative assessment of the overall success of Output 3 across all five countries, alongside the scoring of output indicators 3.1, 3.2 and 3.3, to come to a final assessment of the overall score of this output.