## CEF TA Programme LogFrame
Clean Energy Fund Technical Assistance (CEF TA) Programme
IMPACT | Impact Indicator 1 |  | CEF TA portfolio 2015 | 2016 | 2017 | 2018 | 2019 | 2020
Increased country-level (public and private sector) action to implement successful low carbon projects that improves access to clean energy and reduces greenhouse gas (GHG) emissions | Expected GHG emissions reductions from capital projects initiated from CEF TA projects (tCO2) | Expected | 4499322 | 1012062 | 400000 | 4049141 | 400000
|  | Revised | 3943867 | 941,062 (5,357,300 - revised end of 2018) | N/A | N/A
|  | Notes |  | The PPTA for NEP: Power Transmission and Distribution Efficiency Enhancement Project was supported in 2016 and the loan was approved in 2017. Initial estimate in the PPTA document was 50,000 tCO2/yr for the ensuing loan but the approved loan document increased that estimate to 54,400 tCO2/yr. In 2018, the PPTA for the UZB Second Solar Power Project was closed. The loan will not be pursued by the government. Per PPTA document, the loan was expected to reduce 105,000 tCO2/yr had it been implemented. The ensuing loan for SRI Wind Power Project estimated 265,700 tCO2/yr compared to the initial estimate in the PPTA of 748,862 (a difference of 483,162). The ensuing loan for PRC Green Financing Platform estimates 5 million tCO2/yr. This was not recorded previously. (941,062 + 4,400 - 105,000 - 483,162 + 5,000,000 = 5,357,300). | In 2017, the IND: Railway Energy Efficiency Project was withdrawn from the portfolio since the schedule for the investment project will be delayed (for 2019). The allocation for the PPTA was reverted to the Facility. (1,012,062 - 71,000 = 941,062). | Revised, Sep2018: 4,499,322 tCO2/yr included the emission reduction from GCIs supported by CEF; reverted to 4,020,906 tCO2/yr. In 2018, the loan UZB: Samarkand Solar Power Project was terminated as requested by the government. The PPTA for the loan was supported by CEF in 2013 and 88,000 tCO2/yr was the expected emission reduction. Also in 2018, The TA AFG: RE Development (Biomass Cogeneration) Project was closed. It prepared the loan AFG: Energy Supply Improvement Investment Program (Solar Tranch 3) with an estimated 10,961 tCO2/yr emission reduction. (4,020,906 - 88,000 + 10,961 = 3,943,867).
Source
CEF TA annual results
| Impact Indicator 2 |  | CEF TA portfolio 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Total number of Asian Development Bank (ADB) Developing Member Countries (DMCs) supported by Clean Energy Fund TA activities per year and cumulatively since 2015 | Allocations | 32 | 19 | 5 | 14 | 1
|  | Revised | N/A | 18 | N/A | N/A
|  | Notes |  | It is worth noting that in 2016, RMI and TKM projects were supported by CEF for the first time. | In 2017, the IND: Railway Energy Efficiency Project was withdrawn from the portfolio since the schedule for the investment project will be delayed (for 2019). The allocation for the PPTA was reverted to the Facility. | Cumulative 2008-2018: 34 DMCs Cumulative 2016-2018: 22 DMCs | Cumulative 2008-2018: 34 DMCs Cumulative 2016-2018: 22 DMCs 1 supporting Indonesia and 1 regional direct charge.
Source
CEF TA and DC annual results
Projects
OUTCOME 1 | Outcome Indicator 1.1 |  |  | Project 1: TA9085 | Project 2: TA9225 | Project 3: TA9266 | Project 4: TA9251 | Project 5: TA9242 | Project 6: TA9308 | Project 7: CEFPDC00069 | Project 8: TA0033 | Project 9: TA9564 | Assumptions
|  |  |  | SRI: Wind Power Generation Project | RMI: Majuro Power Network Strengthening | REG: Improving Institutional Capacity on Preparing Energy Efficiency Investments | PRC: Strengthening Capacity in the Implementation of the Green Financing Platform for the Greater Beijing–Tianjin–Hebei Region | Pacific Renewable Energy Investment Facility | REG: Promoting Low-Carbon Development in Central Asia Regional Economic Cooperation Program Cities | REG: Asia Clean Energy Forum | REG: Integrated High Impact Innovation in Sustainable Energy Technology | REG: Floating Solar Energy Development
Improved climate finance (public and private) infrastructure | Summary of additional ADB climate finance and/or wider private finance leveraged from projects (if relevant to the case study in question) | Planned 2016 |  | The TA will prepare the feasibility study and due diligence assessments for the ensuing loan which is estimated at $750 million. The estimates for the full project includes loans from ADB, Green Climate Fund (soft loan), Agence Francaise de Developpement, private sector and the Government and/or Ceylon Electricity Board. Target approval of TA for 2016. | Part of the TA will be to prepare the feasibility study for investment in network and control systems for expanded renewable energy in RMI. CEF allocation for the TA authorized in September 2016. Target approval of TA for 2016. | The TA will target at least five energy efficiency investment projects identified. Target date for the pipeline of energy efficiency projects is by 2019. Target approval of TA for 2016. *** Per revised DMF (approved 8 December 2017), Outcome - At least 3 EE project concept papers prepared or approved. Output 2 - By 2019, At least 5 investment grade EE projects (ideally one per DMC) identified. | Approve the TA project. The TA is estimated to be US $1.5 billion for the initial set of subprojects to be financed under the project. US $500million each from ADB, Subborrowers and commercial banks. | Approve the TA project, which is estimated to cost US $5 million of which US $2 million will be financed on a grant basis by ADB's Technical Assistance Fund-V and US $3 million from CEF. The projects to be financed under the facility are estimated at US $750 million to be financed by ADB (US $200 million), co-financiers (US $500 million); and the governments (US $50 million). Cofinancing is estimated at US $300 million from the Green Climate Fund and another US $200 from other grant/s. US $12 million has been approved for initial projects, with US $5 million for TA. | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018) | Successful investments are replicated by others Increased investment leads to ability to deliver at a wider scale e.g. drives costs down Investments continue once TA projects have completed
|  | Achieved 2016 |  | Achieved. TA was approved in March 2016 and became effective in April 2016. Consulting firm was engaged in September 2016 to conduct project due diligence. | Achieved. TA was approved in November 2016 and became effective in December 2016. | Achieved. US $2 million from the CEF approved in 2016. Five countries targeted for support: Sri Lanka, Bhutan, Bangladesh, Maldives and Nepal. | Achieved. Project approved by the ADB. | Achieved. Project approved by the ADB. | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2017 |  | Project due diligence conducted with consulting services engaged from September 2016 to February 2018. | Approve project (for metering and the provision of consultants) and move into the project implementation phase. | The TA will identify at least five energy efficiency investment projects by 2019. TA support for the identified five countries confirmed. | Begin project implementation by starting to disburse funds for clean energy activities. | Begin project by undertaking feasibility studies. | Obtain ADB project approval. | ADB to obtain cofinancing from USAID and KEA. | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Achieved 2017 |  | Achieved. Feasibility study completed. Various surveys completed (e.g. Environmental Impact Assessment and Noise Survey) and final surveys close to completion. The project received a US $200 million loan from the ADB in October 2017. | Achieved. ADB approved a US $2 million grant for the advanced metering infrastructure in September 2017. | Achieved. Mobilized in-kind contribution from Korea Energy Agency (KEA) estimated at US$ 1.2million for technical advisory support. Knowledge Partnership Agreement signed by ADB and KEA for this project on 30 March 2017. | Achieved. The project has started implementation with EUR 78 million having been disbursed to support renewable energy, clean heating and green transport projects. | Achieved. Feasibility studies and due diligence are currently being completed for projects in 7 countries (Tonga, Cook Islands, Federated States of Micronesia, Marshal Islands, Samoa, Tuvalu and Nauru) as well as initial design of a Regional Renewable Energy Guarantee Facility and a Regional Energy Regulators Alliance. ADB has approved an additional $2.6 million from TASF-V to increase TA9242 to $7.6 million. | Achieved. The Low-carbon City Transformation in Xiangtan, Hunan loan project is at the early stage of procesing and the loan is expected to be approved in 2020. Indicative project cost is over US $600 million to finance key low carbon measures in Xiangtan. The TA was approved in 6 April 2017 with US $800,000 from CEF. It is being cofinanced by ADB for US $0.5 million, the Governance Cooperation Fund for US $0.35 million, the PRC Regional Cooperation and Poverty Reduction Fund for US $0.70 million, The Republic of Korea e-Asia and Knowledge partnership Fund for US $0.5 million; and ADB's Capacity Development Technical Assistance: Regional Cooperation and Integration Fund for US $0.5 million. The RETA team helped Xiantan (one of pilot cities of RETA) in preparing a loan project on low carbon city development, which was successfully accepted as a loan project in the CPM September meeting. | Achieved. Cofinanced with USAID and KEA. | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2018 |  | The PPTA to be extended until February 2019 to accommodate an additional survey request by the implementing agency, the Ceylon Electricity Board. The additional work to be approved in February 2018. | The TA to be extended until November 2018 to complete the phase two investment preparation for transformer and conductor replacement and renewable generation expansion. | The target date for the pipeline of energy efficiency projects is by 2019. | EUR 100 million plans to support renewable energy, clean heating and green transport projects | Complete technical support in above countries. Complete technical design for 2 regional projects. | N/A | ADB to obtain cofinancing from USAID and KEA. | TA approval in 2018. | *Not tracked in 2016-2018 (added in 2018)
|  | Achieved 2018 |  | Achieved. Additional international ornithologist was engaged to set up a system for passing the data after each survey visit to assess, check the quality of work and should cover both wind farm and transmission line, and provide training to local field surveyors. | Achieved. The Strategic Roadmap modeling done under the TA has identified five projects for RMI: (I) Diesel Power House Upgrade, (ii) Diesel Fuel Depot Refurbishment, (iii) Distribution Network Upgrade, (iv) Installation of 2MWp Solar PV, and (v) Installation of 1 MW Waste to Energy system. All environmental due diligence assessment were completed for each project. The TA directly resulted in a project (G0554) – the Advanced Metering Infrastructure project (approved in Nov 2017 for $2 million); and indirectly (but substantially) resulted in: (i) G0637 – the RMI Energy Security (tank farm rehab) project (approved in Dec 2018 for $12.7 million), and (ii) a TRTA for a waste to energy project (currently underway with HLT funding) to be completed Dec 2019 (and possible approval 2020). The TA was closed in 2018. | Achieved. In-country consultations carried out to discuss the results of energy audits and capacity building studies, as well as to identify potential energy efficiency projects that can be developed. | Achieved. US$215 million was disbursed in 2018 to support reneable energy, clean heating and green transport projects. | Achieved. Consultants were engaged to conduct feasibility studies and due diligence. Currently, there are 8 project preparatory activities being financed by CEF under the TA (i.e. projects for Tonga, Samoa, Tuvalu, Nauru, RMI, Regional RE Guarantee Facility, Regional IPP in Palau, and Federal States of Micronesia). About US $100 million from ADB and cofinancing funds will be committed for the projects. | N/A. The RETA successfully obtained additional US$700,000 from Clean Technology Fund (CTF) to support the preparation of financial and technical pre-feasibility studies on clean technology solutions for the pilot city of Astana, which is only eligible pilot city for CTF. The draft low-carbon strategy for Astana contains a short-, medium- and long-term climate plans. The short-term plan identifies a number of priority low-carbon actions and measures, which can demonstrate effective carbon reduction and also can create synergy and spillover effects. The CTF will provide support to prepare financial and technical pre-feasibility studies on these priority clean technology solutions in Astana. The additional CTF support will enhance the Astana low-carbon plan by advancing the project readiness for investment. | Achieved. Cofinanced with USAID and KEA. | Achieved. TA approved in 2018 | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2019 |  | N/A | N/A | To identify at least 5 energy efficiency projects. The TA is expected to be completed by November 2019. | EUR 70 million plans to support renewable energy, clean heating, green transport, and other energy efficiency improvement and pollution reduciton projects. | Four projects to be prepared to approval | N/A | ADB to obtain cofinancing from USAID and KEA. | N/A | Begin implementation - no additional funding planned
Source
Project Completion Reports
OUTCOME 2 | Outcome Indicator 2.1 |  | CEF TA portfolio 2015 | 2016 | 2017 | 2018 | 2019 | 2020 |  |  |  |  | Assumptions
Development of bankable clean energy projects (such as renewable energy and energy efficiency projects) | Number of Project Preparatory Technical Assistance (PPTA) projects per year and cumulatively since 2015 that resulted in the development of bankable clean energy projects (such as renewable energy and energy efficiency project proposals) | Planned | 7 PPTAs. | 6 PPTAs to receive allocation in 2016. | 3 PPTAs to receive allocation in 2017. | 2 PPTAs to receive allocation in 2018. | 2 TAs to receive allocation in 2019. | [5 empty] | Innovative technologies are being piloted Evidence of success is being shared and projects are being replicated Market actors have the expertise to deliver successful projects Projects continue without the TA support
|  | Achieved | Of the 7 PPTAs allocated to before 2016, 3 PPTAs have been completed, 2 of which have ongoing loans: UZB: Samarkand Solar Power Project and TON: Outer Island Renewable Energy Development Project. 2 PPTA, both allocated in 2013, have been completed in 2017: India: Concentrated Solar Power (CSP) Project and Azerbaijan: Renewable Energy Development (Biomass Cogeneration) Project. India's Ministry of New and Renewable Energy decided not to postpone implementation of the proposed CSP loan given the shift in focus to solar PV that demonstrated a significant cost reduction and was considered more affordable to pursue. The Azerbaijan project will not be pursued at the moment as it is not the government's priority. | Achieved. (In 2017, one of the PPTA. The IND project, was withdrawn from the portfolio. The schedule for the investment project will be delayed (for 2019) so the allocation for the PPTA was reverted to the Facility). 1 PPTA which received allocation in 2016 for SRI: Wind Power Generation Project has already resulted to an ensuing ADB loan approved in 2017. | Achieved. All three PPTAs were approved in 2017. In 2018, the additional financing for PRC: Developing Cost Effective Policies and Investments to Achieve Climate and Air Quality Goals in the Beijing-Tianjin-Hebei Region was withdrawn from the portfolio. The additional financing was supposed to support additional outputs to be jointly implemented with the World Energy Council (WEC). However, WEC underwent personnel changes and the appointment of new staff to implement the additional activities was uncertain. In March 2018, the outputs were deleted from the TA scope and the fund was reverted to the Facility. | 5 TRTAs received allocations in 2018. As of end 2018, 2 of the TRTAs have been approved by ADB: PRC: Air Quality Improvement in Greater Beijing - Tianjin - Hebei Region (Shandong Clean Heating and Cooling Project) and CAM: Support for a Sustainable Power Sector The TRTA and the loan for PRC: Air Quality Improvement in Greater Beijing - Tianjin - Hebei Region (Shandong Clean Heating and Cooling Project) were approved together.
|  | Notes | In 2018, the ongoing loan for UZB: Samarkand solar Power Project was cancelled. The PPTA for the project was approved in 2013. Also in 2018, the TA AFG: RE Development (Biomass Cogeneration) Project was closed. It was a CDTA financed in 2013 but it prepared the loan AFG: Energy Supply Improvement Investment Program (Solar Tranch 3) | Achieved: 3 TAs resulted to loan and grant projects Withdrawn: 1 Loan will not be pursued: 1 capacity building activities were pursued but was classified as PPTA: 1 In 2017, two TAs have resulted to ADB loans, the SRI: Wind Power Generation Project and the NEP: Power Transmission and Distribution Efficiency Enhancement Project while not ADB loan project, the REG: Pacific Renewable Energy Investment Facility has resulted to approved grants for Pacific DMCs. In 2018, the government already indicated that the UZB: Second Solar Power Project will not be pursued. | With the withdrawal of the PRC: Developing Cost Effective Policies and Investments to Achieve Climate and Air Quality Goals in the Beijing-Tianjin-Hebei Region in 2018, there are now only 2 ongoing PPTAs with allocations from 2017. | N/A
TA Completion Reports
| Outcome Indicator 2.2 |  | CEF TA portfolio 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Number of countries per year and cumulatively since 2015 that amended or developed new policies, regulations, standards to support the deployment of clean energy projects (such as renewable energy and energy efficiency projects) | Planned | 8 | 17 | 2 | 2 | 1
|  | Achieved | 8 | 17 (3 projects: one covers 11 countries, one covers 5 countries and one covers 1 country) | 2 (Indonesia and PRC; lower ambition compared to 2016 since of the projects is regional and covered 11 SIDS) | 1 - PRC (Since 2016, cumulative number of supported DMCS is 18)
Revised end of 2018
TA and DC Completion Reports
OUTPUT 1 | Output Indicator 1.1 |  |  | Project 1: TA9085 | Project 2: TA9225 | Project 3: TA9266 | Project 4: TA9251 | Project 5: TA9242 | Project 6: TA9308 | Project 7: CEFPDC00069 | Project 8: TA0033 | Project 9: TA9564 | Assumptions
|  |  |  | SRI: Wind Power Generation Project | RMI: Majuro Power Network Strengthening | REG: Improving Institutional Capacity on Preparing Energy Efficiency Investments | PRC: Strengthening Capacity in the Implementation of the Green Financing Platform for the Greater Beijing–Tianjin–Hebei Region | Pacific Renewable Energy Investment Facility | REG: Promoting Low-Carbon Development in Central Asia Regional Economic Cooperation Program Cities | REG: Asia Clean Energy Forum | REG: Integrated High Impact Innovation in Sustainable Energy Technology | REG: Floating Solar Energy Development
Increased institutional capacity and capability (impact weighting 25%) | Number and effectiveness of training events funded by the TA project | Planned 2016 |  | The TA includes training in wind forecast, control and management. Target approval of TA for 2016. | The TA includes two workshops and/or seminars on the use of analytical tools and project technical, financial, and economic analysis and investment project prioritization. CEF allocation for the TA authorized in September 2016. Target project approval for 2016. | N/A | Workshops are planned for 2017 to 2019 while publications are planned for 2019. Target TA approval in 2016. | Number of event training to be determined after country specific capacity assessments are completed. Complete assessments. Target TA approval in 2016 | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018) | Market actors utilise the information gained Market actors continue training to ensure no gradual loss of institutional knowledge
|  | Achieved 2016 |  | Achieved. TA was approved in March 2016 and became effective in April 2016. Consulting firm was engaged in September 2016. | Achieved. TA was approved in November 2016 and became effective in December 2016. | N/A | Achieved. TA was approved in November 2016. | Achieved. TA approved in November 2016. | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2017 |  | Training in wind forecast, control and management. | Two workshops and/or seminars on the use of analytical tools and project technical, financial, and economic analysis and investment project prioritisation. | Two training events planned - one conference (ACEF) in June 2017 and one workshop in China in Q4 of 2017. | 2 trainings on risk appraisal and underwriting skills related to green investment. | Training events in four power utilities (2017-2018). | N/A | Forum with 3 plenary sessions, 20 thematic track sessions and 21 deep dive workshops. | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Achieved 2017 |  | Achieved. TA training in wind forecast, control and management conducted. | Partially Achieved. On workshop held as a two-day course in Majuro. Training stream of the Majuro Network Strengthening Project included development and deployment of a solar photovoltaic design, maintenance and operation course. A total of 8 key technical personnel attended the two-day course in Majuro under the guidance of accredited solar PV instructor. One of the main conclusions from interactions with MEC crews is that the utility is struggling with adequate human resources for some of its key activities. Going forward, MEC should develop detailed strategy for developing its human resources, as MEC crews could benefit from specific technical trainings, with yearly refreshers. In addition, Projects bringing new technologies should also heavily focus on training at least two capable MEC resources for proper operation and maintenance, with yearly refresher courses. Finally, MEC could benefit from attracting new highly skilled resources, which will focus on integration of future generation, network, and new technologies. The numeracy and literacy of the participants has been an unexpected issue. | Achieved. The TA sponsored senior government representatives to attend two capacity building events - (1) 12th Asia Clean Energy Forum in June 2017 and (2) PRC workshop for Senior Personel on Electric Power Sector in October-November 2017. | Achieved. 2 trainings held. | Achieved. Initial capacity assessments completed. Training conducted in 2 power utilities (Marsall Islands and Tonga) | (A small training event on low-carbon development concept and strategy was provided at Changsha, Xiangtan city government and Hunan province government (PRC pilot cluster city) in May 2017). | Achieved. The 12th ACEF (2017) had 3 plenary sessions, 20 thematic track sessions and 21 deep dive workshops. | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2018 |  | N/A (remaining activity is for survey). | N/A (for TA completion in 2018). | Two training events planned - one in March 2018 (in Bangladesh) and one in Q4 of 2018 (location tbc). | Two trainings on foreign exchange and risk appraisal. | Training events in four power utilities (2017-2018). | One major capacity building workshop on low-carbon economy development will be organized with CAREC cities; a range of institutional capacity buidling trainings and seminars would be organized at pilot cities. (same for 2019). | Forum with 3 plenary sessions, 20 thematic track sessions and 21 deep dive workshops. | TA approval in 2018. | 1 inception workshop
|  | Achieved 2018 |  | Achieved. Additional inputs of ornithologist for the pre-construction survey are ongoing. An international biodiversity management expert's input was also increased to finalize the Biodiversity Management Plan (BMP) and to work out the collision monitoring procedure for better implementation of BMP. | N/A. TA was closed in 2018. | Achieved. Organized the following events: -1st Regional Knowledge Sharing Workshop on Energy Efficiency and Conservation (September 2018) with senior-level government officials from the 5 target DMCs attending. -Deep Dive Workshop on EE Technologies, Finance and Business Models in Developing Asian Countries on the sidelines of the 2018 Asia Clean Energy Forum. Sponsored participants to attend the 2018 Asia Clean Energy Forum in Manila (June 2018) and the ADB-Korea Energy Storage System Conference and Technical Tour (May-June 2018). | Achieved. 2 trainings were held on foreign exchange and risk appraisal. | Achieved. Two training events attended by stakeholders (40 trained through attendance at the Asia Clean Energy Forum and 8 through attendance at workshop on energy policy and regulation) | Exceeded. (i) Hunan and Xiangtan, Zhuzhou government representatives attened the training workshop on Green Procurement Policy, which was organized by ICLEI-EastAsia; (ii) The training on the Global Protocol for Community-Scale Greenhouse Gas Emission Inventories (GPC), online GHG inventory applications, city case studies, and successful examples of using GHG inventory in low-carbon development works were provided at all the pilot city governments, which are . Based on request from all the pilot city governments,including Changsha, Zhuzhou, and Xiangtan in the People’s Republic of China; Astana in Kazakhstan, and Ulaanbaatar in Mongolia. (iii) The International Forum on Low Carbon Development for Central Asia Regional Economic Cooperation Program Cities was held in Beijing, PRC on 4-6 December 2018. The main objective of the forum was to facilitate the exchange of knowledge and experiences from ongoing RETA’s pilot city experiences and international best practices. The Forum focused on cross-sectoral approaches for low carbon synergy creation, integrated planning, and emerging issues such as transforming old industrial towns into modern, liveable, low carbon, and climate resilient cities. A total of 235 participants from CAREC countries, including government representatives from Afghanistan, Azerbaijan, People’s Republic of China (PRC), Georgia, Kazakhstan, Kyrgyz Republic, Mongolia, Pakistan, Tajikistan, Turkmenistan, and Uzbekistan. From the PRC, representatives from Changsha, Dezhou, Dunhuang, Hanzhou, Jiaxing, Nanjing, Qingdao, Shanghai, Shenyang, Taiyuan, Wenzhou, Xiangtan, Zhenjiang, and Zhuzhou cities attended the forum. Workshop participants commented the range of innovative and effective ICT-based tools as highlights of the forum, such as greenhouse gas (GHG) online platform like ClearPath by ICLEI; (Climate) Adaptation Supporting Tool by Deltares; and Low-Carbon City Mapping tool by Kinesis. Using smart card system data, the detailed analysis made by World Resources Institute (WRI) also drew a lot of attention. The essential need to engage multi-stakeholders was discussed, particularly private sector engagement and activation and benefits of engaging young generation was emphasized. Green procurement policy was presented as one of the effective means of activating private sectors. Experiences from European countries and several PRC pilot cities were shared. Parallel meetings were held between DMC governments and forum speakers for further information exchange and collaboration. | Partially Achieved. Forum with 2 plenary seesion, 16 thematic track session and 16 deep dive workshops, 2 world café sessions, 1 networking day | Achieved. TA approved in 2018 | Achieved. 1 inception worskhop in AZE with participation from KGZ and AFG in November 2018.
|  | Planned 2019 |  | N/A | N/A | 2 activites being planned by the TA: -2nd Regional Knowledge Sharing Workshop on Energy Efficiency and Conservation (April 2019) -Deep Dive Workshop as part of the 2019 Asia Clean Energy Forum The TA is expected to be completed by November 2019. | 2 overseas trainings will be conducted on clean energy. | N/A. | (i) Detailed technical trainings on GPC is scheduled at all pilot cities; (ii) TA second international low-carbon city workshop is planed in Seoul, as Mayor of Seoul Metropolitan Government confirmed us to host it in 2019. | Forum with 3 plenary seesion, 16 thematic track session and 16 deep dive workshops, 2 world café sessions, 1 networking day | N/A. | 1 inception worskhop in AFG and KGZ. Possible study tour to Korea or Japan on floating solar.
Source
CEF TA annual result reporting and project completion reports
| Output Indicator 1.2 |  |  | Project 1: TA9085 | Project 2: TA9225 | Project 3: TA9266 | Project 4: TA9251 | Project 5: TA9242 | Project 6: TA9308 | Project 7: CEFPDC00069 | Project 8: TA0033 | Project 9: TA9564
|  |  |  | SRI: Wind Power Generation Project | RMI: Majuro Power Network Strengthening | REG: Improving Institutional Capacity on Preparing Energy Efficiency Investments | PRC: Strengthening Capacity in the Implementation of the Green Financing Platform for the Greater Beijing–Tianjin–Hebei Region | Pacific Renewable Energy Investment Facility | REG: Promoting Low-Carbon Development in Central Asia Regional Economic Cooperation Program Cities | REG: Asia Clean Energy Forum | REG: Integrated Hugh Impact Innovation in Sustainable Energy Technology | REG: Floating Solar Energy Development
| Stakeholders (public and private) that received technical assistance support | Planned 2016 |  | Ceylon Electricity Board and other institutions. | Ministry of Resources and Development, and the Marshalls Energy Company. | BAN: Sustainable and Renewable Energy Development Authority; BHU: Department of Renewable Energy; MLD: Ministry of Environment and Energy; NEP: Ministry of Energy; SRI: Sustainable Energy Authority. | China National Investment and Guarantee Corporation. | Three institutions (e.g. Cook Islands, Tonga and the Republic of Marshall Islands) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Achieved 2016 |  | Achieved. Ceylon Electricity Board and some small private sector companies. | Achieved. TA was approved in November 2016 and became effective in December 2016. | Achieved. Five countries are supported with dialogue with the governments of Bangladesh, Maldives, Bhutan, Sri Lanka and Nepal. | Achieved. China National Investment and Guarantee Corporation. | Achieved. Three institutions (Samoa, Tonga and the Federal States of Micronesia) TA approved in November 2016 | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2017 |  | Ceylon Electricity Board and other institutions. | Strengthen engagement with the targeted institutions (the Ministry of Resources and Development, and the Marshalls Energy Company). | Continue to give technical support to the five countries based on the agreed scope of assistance. | China National Investment and Guarantee Corporation. | Power utilities from seven countries (Samoa, Tonga, Federated States of Micronesia, Tuvalu, Nauru, Cook Islands and Republic of Marshall Islands, 2017-2018). | N/A | N/A | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Achieved 2017 |  | Achieved. The project received a US $200 million loan from the ADB. | Partially Achieved. In contact with the National Energy Planner (Angline Hines) at the Ministry of Resources and Development but she is the only person on this and has limited influence. | Achieved. In-country consultations undertaken for all identified institutions in the five countries. Countries conveyed their specific requests for assistance from project. Approval for changes in target activities for TA 9266 based on government requests secured. | Achieved. China National Investment and Guarantee Corporation. | Feasibility studies and due diligence are currently being completed for projects in 7 countries (Tonga, Cook Islands, Federated States of Micronesia, Marshal Islands, Samoa, Tuvalu and Nauru) | N/A | N/A | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2018 |  | N/A (remaining activity is for survey). | N/A (for TA completion in 2018). | Continue to give technical support to the five countries based on the agreed scope of assistance. | One (China National Investment and Guarantee Corporation) | Complete technical support in above countries. Complete technical design for 2 regional projects. | Target participants for the workshop for 2018: 2 government representatives per city; 50 cities (same for 2019). | N/A | TA approval in 2018. | 5 institutions in AZE, 2 in AFG and 1 in KGZ
|  | Achieved 2018 |  | N/A. The ornithologist provided training to local field surveyors on survey methodology simultaneously with the field data collection. | N/A. TA was closed in 2018. | Achieved. In-country consultations undertaken for all identified institutions to discuss the results of the energy audits undertaken in Bangladesh and Bhutan. Coordinate with identified institutions in Bangladesh, Bhutan, Nepal and Sri Lanka in the preparation of the EE capacity building studies. | Achieved. China National Investment and Guarantee Corporation | Achieved. Complete technical design for 2 projects. | Achieved. A total number of government institutions/organizations from Afghanistan, Azerbaijan, People’s Republic of China (PRC), Georgia, Kazakhstan, Kyrgyz Republic, Mongolia, Pakistan, Tajikistan, Turkmenistan, Uzbekistan, and the PRC, including city government representatives from Changsha, Dezhou, Dunhuang, Hanzhou, Jiaxing, Nanjing, Qingdao, Shanghai, Shenyang, Taiyuan, Wenzhou, Xiangtan, Zhenjiang, and Zhuzhou cities, got supported by the RETA to participate the low carbon city development workshop and learned a range of low-carbon projects and policy cases, which can further help in their low carbon related projects. | N/A | Achieved. TA approved in 2018 | Achieved. 5 institutions in AZE, 2 in AFG and 1 in KGZ
|  | Planned 2019 |  | N/A | N/A | Continue to give technical support to the 5 countries based on the agreed scope of assistance. The TA is expected to be completed by November 2019. | One (China National Investment and Guarantee Corporation) | Complete technical design for 4 projects. | Target participants for the workshop for 2019: 100 government representatives | N/A | N/A. | On-going support in AZE and 5 in AFG. Tentative for support in KGZ
|  | Source | [10 empty] | RISK RATING
|  | CEF TA annual result reporting and project completion reports | [10 empty] | Low
OUTPUT 2 | Output Indicator 2.1 |  |  | Project 1: TA9085 | Project 2: TA9225 | Project 3: TA9266 | Project 4: TA9251 | Project 5: TA9042 | Project 6: TA9308 | Project 7: CEFPDC00069 | Project 8: TA0033 | Project 9: TA9564 | Assumptions
|  |  |  | SRI: Wind Power Generation Project | RMI: Majuro Power Network Strengthening | REG: Improving Institutional Capacity on Preparing Energy Efficiency Investments | PRC: Strengthening Capacity in the Implementation of the Green Financing Platform for the Greater Beijing–Tianjin–Hebei Region | Pacific Renewable Energy Investment Facility | REG: Promoting Low-Carbon Development in Central Asia Regional Economic Cooperation Program Cities | REG: Asia Clean Energy Forum | REG: Integrated Hugh Impact Innovation in Sustainable Energy Technology | REG: Floating Solar Energy Development
Knowledge-sharing (impact weighting 25%) | Number and effectiveness of stakeholder events (such as conferences, forums and workshops, but excluding training events) organised / funded by the TA project | Planned 2016 |  | N/A | N/A | N/A | Workshops are planned for 2017 to 2019 while publications are planned for 2019. Target TA approval in 2016. | Target TA approval in 2016 | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018) | Market actors utilise the information gained Market actors continue training to ensure no gradual loss of institutional knowledge
|  | Achieved 2016 |  | N/A | N/A | N/A | TA was approved in November 2016 | TA was approved in November 2016 | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2017 |  | N/A | N/A | Two training events planned - one conference (ACEF) in June 2017 and one workshop in China in Q4 of 2017. | 5 workshops on new technologies and international best practices and on low-carbon technologies, new business models to scale up low-carbon development and production of guidelines. | Stakeholder events organized in three power utilities. | N/A | Forum with 3 plenary sessions, 20 thematic track sessions and 21 deep dive workshops. | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Achieved 2017 |  | N/A | N/A | Achieved. The TA sponsored senior government representatives to attend two capacity building events - (1) 12th Asia Clean Energy Forum in June 2017 and (2) PRC workshop for Senior Personel on Electric Power Sector in October-November 2017. | Achieved. 5 workshops held. | Achieved. Stakeholder events organized in three power utilities. | A small training event on low-carbon development concept and strategy was provided at Changsha, Xiangtan city government and Hunan province government (PRC pilot cluster city) in May 2017. | Achieved. The 12th ACEF (2017) had 3 plenary sessions, 20 thematic track sessions and 21 deep dive workshops. | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2018 |  | N/A (for TA completion in February 2019). | N/A (for TA completion in November 2018). | 3 training events planned - one in March 2018 (in Bangladesh), a deep dive workshop on EE as part of ACEF 2018, and one in Q4 of 2018 (location tbc). | 1 workshop with commerical banks and other finanical institutions. | Stakeholder events organized in five power utilities. | One major capacity building workshop on low-carbon economy development will be organized with CAREC cities; a range of institutional capacity buidling trainings and seminars would be organized at pilot cities. | Forum with 3 plenary sessions, 20 thematic track sessions and 21 deep dive workshops. | TA approval in 2018. | 1 inception worskhop in AZE with participation from KGZ and AFG
|  | Achieved 2018 |  | N/A. Training was conducted by the ornithologist to local field surveyors on survey methodology. | N/A. TA was closed in 2018. | Not Achieved. Organized the following events: -1st Policy Dialogue and Regional Knowledge Sharing Workshop on Energy Efficiency and Conservation (September 2018) with senior-level government officials from the 5 target DMCs attending. -A one-day Deep Dive Workshop on EE in the sidelines of the 2018 Asia Clean Energy Forum. Sponsored participants to attend the 2018 Asia Clean Energy Forum in Manila (June 2018) and the ADB-Korea Energy Storage System Conference and Technical Tour (May-June 2018). | Achieved. 1 workshop with Bank of Beijing in promoting the GFP and discussing business opportunities. | Achieved. Consultants were engaged to conduct sector reform and utility capacity building. Work has commenced in Federated States of Micronesia and the Republic of Marshall Islands. | Achieved. The International Forum on Low Carbon Development for Central Asia Regional Economic Cooperation Program Cities was held in Beijing, PRC on 4-6 December 2018. The main objective of the forum was to facilitate the exchange of knowledge and experiences from ongoing RETA’s pilot city experiences and international best practices. The Forum focused on cross-sectoral approaches for low carbon synergy creation, integrated planning, and emerging issues such as transforming old industrial towns into modern, liveable, low carbon, and climate resilient cities. A total of 235 participants from CAREC countries, including government representatives from Afghanistan, Azerbaijan, People’s Republic of China (PRC), Georgia, Kazakhstan, Kyrgyz Republic, Mongolia, Pakistan, Tajikistan, Turkmenistan, and Uzbekistan. From the PRC, representatives from Changsha, Dezhou, Dunhuang, Hanzhou, Jiaxing, Nanjing, Qingdao, Shanghai, Shenyang, Taiyuan, Wenzhou, Xiangtan, Zhenjiang, and Zhuzhou cities attended the forum. Workshop participants commented the range of innovative and effective ICT-based tools as highlights of the forum, such as greenhouse gas (GHG) online platform like ClearPath by ICLEI; (Climate) Adaptation Supporting Tool by Deltares; and Low-Carbon City Mapping tool by Kinesis. Using smart card system data, the detailed analysis made by World Resources Institute (WRI) also drew a lot of attention. The essential need to engage multi-stakeholders was discussed, particularly private sector engagement and activation and benefits of engaging young generation was emphasized. Green procurement policy was presented as one of the effective means of activating private sectors. Experiences from European countries and several PRC pilot cities were shared. Parallel meetings were held between DMC governments and forum speakers for further information exchange and collaboration. | Partially Achieved. Forum with 2 plenary seesion, 16 thematic track session and 16 deep dive workshops, 2 world café sessions, 1 networking day. | Achieved. TA approved in 2018 | 1 inception worskhop in AZe with participation from KGZ and AFG
|  | Planned 2019 |  | N/A | N/A | Following events being planned - 2nd Regional Knowledge Sharing Workshop on Energy Efficiency and Conservation (April 2019); and a deep dive workshop on EEC as part of 2019 Asia Clean Energy Forum. The TA is expected to be completed by November 2019. | One workshop with commercial banks and other financial institutions. | N/A. | One capacity building workshop on low-carbon economy development will be organized in Seoul, South Korea. | Forum with 3 plenary seesion, 16 thematic track session and 16 deep dive workshops, 2 world café sessions, 1 networking day. | To partly support the organization of the Asia Clean Energy Forum (ACEF) in June 2019. | 1 inception worskhop in AFG and KGZ. Possible study tour to Korea or Japan on floating solar.
Source
CEF TA annual result reporting and project completion reports
| Output Indicator 2.2 |  |  | Project 1: TA9085 | Project 2: TA9225 | Project 3: TA9266 | Project 4: TA9251 | Project 5: TA9242 | Project 6: TA9308 | Project 7: CEFPDC00069 | Project 8: TA0033 | Project 9: TA9564
|  |  |  | SRI: Wind Power Generation Project | RMI: Majuro Power Network Strengthening | REG: Improving Institutional Capacity on Preparing Energy Efficiency Investments | PRC: Strengthening Capacity in the Implementation of the Green Financing Platform for the Greater Beijing–Tianjin–Hebei Region | Pacific Renewable Energy Investment Facility | REG: Promoting Low-Carbon Development in Central Asia Regional Economic Cooperation Program Cities | REG: Asia Clean Energy Forum | REG: Integrated High Impact Innovation in Sustainable Energy Technology | REG: Floating Solar Energy Development
| Internal and external knowledge-sharing dissemination activities undertaken by the TA project (such as project outputs and lessons learned) | Planned 2016 |  | N/A | N/A | The TA will publish at least one energy efficiency report and provide trainings to energy profesionals during its project life. Target approval of TA for 2016. | Target approval of TA for 2016. TA target: develop an online application and data collection platform to allow GFP to become a one-stop, user-friendly knowledge and investment platform by 2017. Undertake knowledge-sharing and information dissemination through workshops and conferences from 2017-2019. Publish at least one knowledge product by 2019. | Target TA approval in 2016 | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Achieved 2016 |  | N/A | N/A | Achieved. The TA was approved December 2016. | TA approved in November 2016. The platform is currently under contract negotiation and contract will soon be awarded. | TA was approved in November 2016 | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2017 |  | N/A | N/A | N/A | 5 workshops on new technologies and international best practices and on low-carbon technologies, new business models to scale up low-carbon development and production of guidelines. | A Facility Support Unit (FSU) will be established in ADB headquarters. Its function includes supporting the national Project Implementation Units (PIUs) in each of the Pacific SIDS, including sharing of lessons learnt between PIUs. | N/A | The event should provide a mechanism for experiences and expertise to be shared both verbally (through presentations, panel discussions and networking sessions) and in written form (through the sharing of presentation slides and event materials) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Achieved 2017 |  | N/A | N/A | N/A | Achieved. 5 workshops held. | Achieved. FSU established. | N/A | Achieved. The 12th ACEF was held 5-8th June 2017. A final report prepared by Nexant and the ACEF 2017 Steering Committee evaluated the success of the conference, which included data from participant feedback forms, as well as reviews of each of the sessions. | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2018 |  | N/A (for TA completion in February 2019). | N/A (for TA completion in November 2018). | Energy audit training to be provided. | 2 workshops (meetings) with local guarantee agencies to be held in the greater BTH region. | FSU to be established and run. | Sourcebook on climate actions in the PRC cities for development and dissemination in 2018. A more extensive sourcebook will be developed and disseminated in 2019. | Provide evidence of the effectiveness of knowledge-sharing activities. | TA approval in 2018. | 1 inception worskhop in AZE with participation from KGZ and AFG.
|  | Achieved 2018 |  |  | TA was closed in 2018. | On-the-job energy audit training were carried out in Bangladesh for the local energy auditors recommended by SREDA. Organized a Policy Dialogue and Regional Knowledge Sharing Workshop on Energy Efficiency and Conservation (September 2018) for senior-level government officials from the 5 target DMCs. KEA, as knowledge partner for the TA, carried out an intensive training for energy audit trainers in Bangladesh (November-December 2018), as requested by SREDA. | Achieved. One workshop with Shanxi Province Financing Re-guarantee Group Co., Ltd. and one workshop with Shanghai SMEs Guaranty Fund Agency held. | Achieved. A consultant was engaged to run the FSU with the following undertaking: (i0 project processing and implementation support; (ii) supporting establishment of a regional training center; (iii) establishment of a regional regulatory center of excellence, and (iv) assisting in the administration of the facility. | The publication on ’50 Climate Solutions from Cities in the PRC’ was finalized and launched in the international low-carbon workshop in Beijing on December 2018. Both English and Chinese versions of the publications were distributed to the low-carbon workshop participants and also disseminated through ADB website. It was recorded that only after one month of disclosure at ADB website, this source book of ’50 Climate Solutions from Cities in the PRC’ became one of top 3 knowledge products downloaded both in year of 2018 and in the month of December 2018. We also received requested from many CAREC countries for its translation in Russian and Mongolian. | Forum with 2 plenary seesion, 16 thematic track session and 16 deep dive workshops, 2 world café sessions, 1 networking day - over 1300 participatns from 73 countries, 250 speakers | Achieved. TA approved in 2018 | Achieved. 1 inception worskhop in AZE with participation from KGZ and AFG.
|  | Planned 2019 |  | N/A | N/A | Knowledge sharing activities planned for 2019: -2nd Policy Dialogue and Regional Knowledge Sharing Workshop on Energy Efficiency and Conservation (April 2019) -A deep dive workshop on EE will be orgaized at the sidelines of the 2019 Asia Clean Energy Forum. The TA is expected to be completed by November 2019. | 2 workshops with SMEs on special and tailored financial products for SMEs. | Continue FSU operations. | A knowledge product from the workshop will be published on the Development Asia website. | Forum with 3 plenary seesion, 16 thematic track session and 16 deep dive workshops, 2 world café sessions, 1 networking day. | To partly fund the organization of the Asia Clean Energy Forum (ACEF) in June 2019. | 1 inception worskhop in AFG and KGZ. Possible study tour to Korea or Japan on floating solar.
Source
CEF TA annual result reporting and project completion reports
| Output Indicator 2.3 |  |  | Project 1: TA9085 | Project 2: TA9225 | Project 3: TA9266 | Project 4: TA9251 | Project 5: TA9242 | Project 6: TA9308 | Project 7: CEFPDC00069 | Project 8: TA0033 | Project 9: TA9564
|  |  |  | SRI: Wind Power Generation Project | RMI: Majuro Power Network Strengthening | REG: Improving Institutional Capacity on Preparing Energy Efficiency Investments | PRC: Strengthening Capacity in the Implementation of the Green Financing Platform for the Greater Beijing–Tianjin–Hebei Region | Pacific Renewable Energy Investment Facility | REG: Promoting Low-Carbon Development in Central Asia Regional Economic Cooperation Program Cities | REG: Asia Clean Energy Forum | REG: Integrated High Impact Innovation in Sustainable Energy Technology | REG: Floating Solar Energy Development
| Number and type of stakeholders that attended a stakeholder event organised / funded by the TA project | Planned 2016 |  | N/A | N/A | N/A | Workshops are planned for 2017 to 2019. Target TA approval in 2016. | Target TA approval in 2016. | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Achieved 2016 |  | N/A | N/A | N/A | TA was approved in November 2016. | TA was approved in November 2016. | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2017 |  | N/A | N/A | Two training events planned - one conference (ACEF) in June 2017 and one workshop in China in Q4 of 2017. | 5 workshops on new technologies and international best practices and on low-carbon technologies, new business models to scale up low-carbon development and production of guidelines. | 30 | N/A | Target of more than 800 participants. | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Achieved 2017 |  | N/A | N/A | Achieved. The TA sponsored senior government representatives to attend two capacity building events - (1) 12th Asia Clean Energy Forum in June 2017 and (2) PRC workshop for Senior Personel on Electric Power Sector in October-November 2017. | Achieved. 5 workshops held (at least 100 people). | Achieved. 30 people. | N/A | Achieved. 1440 participants from 71 countries attended 12th ACEF (2017). | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2018 |  | Complete TA project in February 2019 following extension. | Complete TA project in November 2018. | 3 training events planned - one in March 2018 (in Bangladesh), a deep dive workshop on EE as part of ACEF 2018, and one in Q4 of 2018 (location tbc). | At least 50 people attend the workshops. | At least 50 people attend the knowledge-sharing events. | 100 people attend per major workshop. | Target of more than 1000 participants. | TA to be approved in 2018. | At least 50 people attend the inception workshop.
|  | Achieved 2018 |  | The TA completion date extension up to end Feb 2019 paved the way to fulfill its objective and support the implementing agency in ensuring project readiness. | TA was closed in 2018. | Exceeded. Participation in events organized/sponsored by TA: 1. ADB – Korea Energy Storage System Conference and Technical Tour (28 May - 1 June 2018, Seoul): 6 participants from Sri Lanka 2. Asia Clean Energy Forum 2018 (5-8 June 2017, Manila): 5 participants (Bangladesh =1 and Sri Lanka = 4) 3. Regional Knowledge Sharing Workshop on Energy Efficiency and Conservation (24-28 September 2018, Tokyo): 13 participants (3 participants each from Bangladesh, Bhutan, Sri Lanka; and 2 each from Maldives and Nepal) 4. KEA organized training for energy audit trainers in Bangladesh | Achieved. The workshops held had at least 50 participants. | Not Achieved. 48 participants to two knowledge-sharing events. | Exceeded. A total of 235 participants jointed the low carbon workshop in Beijing in December 2018. | Achieved. Over 1300 participants from 73 countries. | Achieved. TA approved in 2018 | Achieved. 50 people attended inception workshop in AZB.
|  | Planned 2019 |  | N/A | N/A | 2 events being planned - 2nd Regional Knowledge Sharing Workshop on Energy Efficiency and Conservation (April 2019); and a deep dive workshop on EEC as part of 2019 Asia Clean Energy Forum (June 2019). The TA is expected to be completed by November 2019. | At least 60 people attend the stakeholder events. |  | 100 people attend per major workshop. | Target of more than 1300 participants. | To partly fund the organization of the Asia Clean Energy Forum (ACEF) in June 2019. | 50 people for inception workshop in AFG. Study tour - approx 10 people.
|  | Source | [10 empty] | RISK RATING
|  | CEF TA annual result reporting and project completion reports | [10 empty] | Low
OUTPUT 3 | Output Indicator 3.1 |  |  | Project 1: TA9085 | Project 2: TA9225 | Project 3: TA9266 | Project 4: TA9251 | Project 5: TA9242 | Project 6: TA9308 | Project 7: CEFPDC00069 | Project 8: TA0033 | Project 9: TA9564 | Assumptions
|  |  |  | SRI: Wind Power Generation Project | RMI: Majuro Power Network Strengthening | REG: Improving Institutional Capacity on Preparing Energy Efficiency Investments | PRC: Strengthening Capacity in the Implementation of the Green Financing Platform for the Greater Beijing–Tianjin–Hebei Region | Pacific Renewable Energy Investment Facility | REG: Promoting Low-Carbon Development in Central Asia Regional Economic Cooperation Program Cities | REG: Asia Clean Energy Forum | REG: Integrated High Impact Innovation in Sustainable Energy Technology | REG: Floating Solar Energy Development
Increased support and interest in clean energy (such as renewable energy and energy efficiency) (impact weighting 20%) [Not tracked from 2019-2021] | Number of stakeholder events which include a slot on RE/EE technologies [Not tracked from 2019-2021] | Planned 2016 |  | N/A | N/A | N/A | Workshops are planned for 2017 to 2019. Target TA approval in 2016. | Target TA approval in 2016 | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018) | Public and private sector are interested in investing in new technologies There is support for feasible innovative technologies
|  | Achieved 2016 |  | N/A | N/A | N/A | TA was approved in November 2016 | TA was approved in November 2016 | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2017 |  | N/A | N/A | Two training events planned - one conference (ACEF) in June 2017 and one workshop in China in Q4 of 2017. | 5 workshops on new technologies and international best practices and on low-carbon technologies and new business models to scale up low-carbon development | Dissemination of best practices and lessons learnt will be facilitated across the region (at least three events). | N/A | Forum with plenary sessions, thematic tracks and deep dives. | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Achieved 2017 |  | N/A | N/A | Achieved. The TA sponsored senior government representatives to attend two capacity building events - (1) 12th Asia Clean Energy Forum in June 2017 and (2) PRC workshop for Senior Personel on Electric Power Sector in October-November 2017. | Achieved. 5 workshops held. | Achieved. Three events which included slots on RE/EE technologies. | A small training event on low-carbon development concept and strategy was provided at Changsha, Xiangtan city government and Hunan province government (PRC pilot cluster city) in May 2017. | Achieved. The 12th ACEF (2017) had 3 plenary sessions, 20 thematic track sessions and 21 deep dive workshops. | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2018 |  | N/A (for TA completion in February 2019). | N/A (for TA completion in November 2018). | N/A | The 3 workshops funded by TA plan to include a slot on RE/EE technologies. | Dissemination of best practices and lessons learnt to be facilitated across the region through at least five events. | One major capacity building workshop on low-carbon economy development will be organized with CAREC cities; a range of institutional capacity buidling trainings and seminars would be organized at pilot cities. | Forum with plenary sessions, thematic tracks and deep dives. | TA approval in 2018. | 1 inception workshop.
|  | Achieved 2018 |  | TA completion date is 28 Feb 2019. | TA was closed in 2018. | -Organized 1st Policy Dialogue and Regional Knowledge Sharing Workshop on Energy Efficiency and Conservation (September 2018) - which included site visits to observe applications of EE technologies -Organized a one-day Deep Dive Workshop on Promoting Innovations for Energy Efficiency Technologies,Finance and Business Models in Developing Asian Countries on the sidelines of the 2018 Asia Clean Energy Forum. -Sponsored participants to attend the ADB-Korea Energy Storage System Conference and Technical Tour (May-June 2018). | Achieved. 3 Workshops were held to discuss the affecting factors, technologies and methodologies with experts from industries and universities and research institutes. | Consultants were engaged to conduct workshops on required sector reforms and utility capacity building activities. | (i) Five city government training workshops were organized at all pilot cities, discussing low carbon city concept and sectoral contributions to carbon intensity. At those training workshops, a range of suitable RE/EE technologies options suitable to different pilot ciites were extensively discussed.; (ii) CTF for Astana pilot city, was obtained to finance the pre-/feasibility studies on (i) upgrading and modernizing old and inefficient district heating systems in suburban districts in Astana; (ii) infrastructure provision to promote block-heater technology to reduce GHG emissions and other air pollutants due to the use of remote starter during winter, among other technologies. | Forum with 2 plenary seesion, 16 thematic track session and 16 deep dive workshops, 2 world café sessions, 1 networking day - over 1300 participatns from 73 countries, 250 speakers. | Achieved. TA approved in 2018 | 1 inception worskhop in AZB with participation from KGZ and AFG
|  | Planned 2019 |  | *Not tracked in 2019-2021 | *Not tracked in 2019-2021 | *Not tracked in 2019-2021 | *Not tracked in 2019-2021 | *Not tracked in 2019-2021 | *Not tracked in 2019-2021 | *Not tracked in 2019-2021 | *Not tracked in 2019-2021 | *Not tracked in 2019-2021
Source
CEF TA annual result reporting and project completion reports
| Output Indicator 3.2 |  |  | Project 1: TA9085 | Project 2: TA9225 | Project 3: TA9266 | Project 4: TA9251 | Project 5: TA9242 | Project 6: TA9308 | Project 7: CEFPDC00069 | Project 8: TA0033 | Project 9: TA9564
|  |  |  | SRI: Wind Power Generation Project | RMI: Majuro Power Network Strengthening | REG: Improving Institutional Capacity on Preparing Energy Efficiency Investments | PRC: Strengthening Capacity in the Implementation of the Green Financing Platform for the Greater Beijing–Tianjin–Hebei Region | Pacific Renewable Energy Investment Facility | REG: Promoting Low-Carbon Development in Central Asia Regional Economic Cooperation Program Cities | REG: Asia Clean Energy Forum | REG: Integrated High Impact Innovation in Sustainable Energy Technology | REG: Floating Solar Energy Development
| Number of EE/RE assessment studies undertaken to evaluate application potentials and market opportunities [Not tracked from 2019-2021] | Planned 2016 |  | US $150,000 allocated for surveys (environmental, social and other baseline condition studies and surveys) | CEF allocation for the TA authorized in September 2016. Target project approval for 2016. | Approve the TA and target at least five energy audits of buildings or industrial facilities from five countries. | N/A | Target TA approval in 2016 | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Achieved 2016 |  | Achieved. | TA was approved in November 2016 and became effective in December 2016. | Achieved. The TA was approved in December 2016. | N/A | TA was approved in November 2016 | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2017 |  | TA surveys conducted. | Target of one feasibility study in network and control systems for expanded renewable generation. | Undertake country consultations in the five countries regarding scope of technical asssitance. Energy audits in at least one of the targeted countries. | N/A | Three assessments undertaken. | N/A | N/A | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Achieved 2017 |  | Achieved. TA surveys conducated and the ensuing project has received a US $200 million loan from the ADB. | Achieved. Project (for metering and the provision of consultants) to be approved in September 2017 with implementation planned for early 2018. | Achieved. As per country consultations, only the Maldives and Bangladesh will undertake investment grade energy audits while Bhutan, Nepal and Sri Lanka have requested a review of their existing energy audits. Energy audits carried out for three buildings in the Maldives. Initial results of the energy audits for the Maldives have been drafted. | N/A | Not achieved. Assessments ongoing. | N/A | N/A | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2018 |  | The PPTA to be extended until February 2019 to accommodate an additional (environmental) survey requested by the implementing agency, the Ceylon Electricity Board. | The TA project to be extended until November 2018 to complete the phase two investment preparation for transformer and conductor replacement and renewable generation expansion. | Carry out energy audits in Bangladesh and initiate work on capacity building studies for Bangladesh, Bhutan, Nepal and Sri Lanka. | Complete an updated analysis of the market opportunities of various renewable energy technologies and complete an analysis report. | Three assessments to be undertaken. | At least three RE/EE city-level assessment studies to be carried out as part of city assessments among pilot cities under RETA. | N/A | N/A | N/A
|  | Achieved 2018 |  | Achieved. The additional inputs of experts (ornithologist and biodiversity management) provided the much needed surveys to ensure project readiness and full implementation of various activities. | Achieved. The Strategic Roadmap modeling done under the TA has identified five projects for RMI: (I) Diesel Power House Upgrade, (ii) Diesel Fuel Depot Refurbishment, (iii) Distribution Network Upgrade, (iv) Installation of 2MWp Solar PV, and (v) Installation of 1 MW Waste to Energy system. All environmental due diligence assessment were completed for each project. The TA was closed in 2018. | Achieved. Two investment grade energy audits completed in Bangladesh for a textile and garments, and a steel rod manufacturer. Draft final reports for EE capacity building studies for 4 countries prepared; and tripartite meetings held with government represenatives for 3 of the 4 countries (Bangladesh, Bhutan, Nepal) to discuss the draft reports. | Achieved. I&G preapared market reports seperately on PV, wind power, clean energy heating, high-efficient boilers, power storage, green transportation and Coal-electricity and coal-gas fields. | Not Achieved. Two assessments completed. | Exceeded. Five RETA pilot city assessment reports were prepared, which highlight the use and potential use of RE/EE technologies in relation to the GHG reduction and low carbon city development. | N/A | N/A | N/A
|  | Planned 2019 |  | *Not tracked in 2019-2021 | *Not tracked in 2019-2021 | *Not tracked in 2019-2021 | *Not tracked in 2019-2021 | *Not tracked in 2019-2021 | *Not tracked in 2019-2021 | *Not tracked in 2019-2021 | *Not tracked in 2019-2021 | *Not tracked in 2019-2021
|  | Source | [10 empty] | RISK RATING
|  | CEF TA annual result reporting and project completion reports | [10 empty] | Medium
OUTPUT 4 | Output Indicator 4.1 |  |  | Project 1: TA9085 | Project 2: TA9225 | Project 3: TA9266 | Project 4: TA9251 | Project 5: TA9242 | Project 6: TA9308 | Project 7: CEFPDC00069 | Project 8: TA0033 | Project 9: TA9564 | Assumptions
|  |  |  | SRI: Wind Power Generation Project | RMI: Majuro Power Network Strengthening | REG: Improving Institutional Capacity on Preparing Energy Efficiency Investments | PRC: Strengthening Capacity in the Implementation of the Green Financing Platform for the Greater Beijing–Tianjin–Hebei Region | Pacific Renewable Energy Investment Facility | REG: Promoting Low-Carbon Development in Central Asia Regional Economic Cooperation Program Cities | REG: Asia Clean Energy Forum | REG: Integrated High Impact Innovation in Sustainable Energy Technology | REG: Floating Solar Energy Development
Creating enabling environments (impact weighting 25%) | Number of ADB Developing Member Countries (DMCs) per year and cumulatively since 2015 that received CEF TA support to improve policies, regulations, etc. | Planned 2016 |  | N/A | N/A | Approve TA project and target five DMCs: BAN, BHU, MLD, Nep and SRI. | N/A | Target TA approval in 2016 | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018) | The public and private sector will utilise changes to policy / regulation The governments are keen to ensure they have effective policy in order to support RE/EE projects
|  | Achieved 2016 |  | N/A | N/A | Achieved. TA approved in December 2016 and five DMCs have been targeted for technical assistance support (Bangladesh, Bhutan, Maldives, Nepal and Sri Lanka). | N/A | TA was approved in November 2016 | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2017 (added in 2017) | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2017 |  | N/A | N/A | Complete consultations with the key institutions in the five targeted countries and identify areas for support. | N/A | Original text: 11 Pacific SIDS: tentative list includes COO, TON, RMI, SOL, FSM, NAU, TUV, SAM and PAL Planned: 3 DMC governments. | N/A | N/A | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Achieved 2017 |  | N/A | N/A | Achieved. In-country consultations undertaken for all identified institutions in the five countries. Countries conveyed their specific requests for assistance from the project (approval for changes in target activities for the project based on government requests was secured). | N/A | Achieved. 8-9 countries are interested in projects. ADB has successfully worked with 3 DMC governments so far. | N/A | N/A | *Not tracked in 2016-2018 (added in 2018) | *Not tracked in 2016-2018 (added in 2018)
|  | Planned 2018 |  | N/A (for TA completion in February 2019). | N/A (for TA completion in November 2018). | Finalise audit reports for the Maldives. Carry out energy audits for Bangladesh. In partnership with KEA, carry out a study to assess the energy efficiency market in Sri Lanka and a study to assess waste heat recovery technology in Bangladesh. Initiate work on capacity building studies for Bangladesh, Bhutan, Nepal and Sri Lanka. | N/A | 3 DMC governments. | N/A | N/A | *Not tracked in 2016-2018 (added in 2018) | 3 - AZB, AFG, KGZ.
|  | Achieved 2018 |  | N/A. The TA completion date is 28 Feb 2019. | N/A. The TA was closed in 2018. | Achieved. Energy audit reports for Maldives and Bangladesh presented to respective government representatives and finalized. Draft final reports for the EE capacity building studies for Bangladesh, Bhutan, Nepal and Sri Lanka completed. Tripartite meetings to discuss the results undertaken for Bangladesh, Bhutan and Nepal in November-December 2018. At the request of the Government of Bangladesh, KEA organized trainings for energy audit trainers. | N/A | Not Achieved. 2 DMCs. | N/A. (i) Hunan and Xiangtan, Zhuzhou government representatives attened the training workshop on Green Procurement Policy, which was organized by ICLEI-EastAsia; (ii) During the low carbon city development capacity building workshop, Green procurement policy was presented as one of the effective means of activating private sectors. Experiences from European countries and several PRC pilot cities were shared. Parallel meetings were held between DMC governments and forum speakers for further information exchange and collaboration. (iii) During the low carbon city development capacity building workshop, a range of innovative and effective ICT-based tools to support low carbon related decision making were presented and got great feedback from participants. Those low carbon decision making tools include greenhouse gas (GHG) online platform like ClearPath by ICLEI; (Climate) Adaptation Supporting Tool by Deltares; and Low-Carbon City Mapping tool by Kinesis; Smart card system use and analysis presented by World Resources Institute (WRI). | N/A | N/A | Achieved. 3 - AZB, AFG, KGZ.
|  | Planned 2019 |  | N/A | N/A | Tripartite meeting to discuss the results of the capacity building study for Sri Lanka scheduled on February 2019. The EE capacity building studies for Bangladesh, Bhutan, Nepal and Sri Lanka are expected to be finalized by the first quarter of 2019. At the request of the governments of Bangladesh and Bhutan, KEA will undertake: 1. Bangladesh: (i) Development of online application for energy auditors; (ii) Procurement of energy audit equipment. 2. Bhutan: Energy audit of 2 large facilities. The TA is expected to be completed by November 2019. | N/A | 4 DMCs | 5 cities in 3 countries. | N/A | Engage consultants for analyzing technological issues, prevailing barriers and constraints impeding the formulation, adoption or implementation of broader and stronger low-carbon energy policies, strategies, interventions and measures in prioritized target subsectors. | 3 - AZB, AFG, KGZ.
Source
CEF TA annual result reporting and project completion reports
OUTPUT 5 | Output Indicator 5.1 |  | CEF TA portfolio 2015 | 2016 | 2017 | 2018 | 2019 | 2020 |  |  |  |  | Assumptions
Overall commitments and performance of the CEF TA programme (impact weighting 25%) | Number of committed CEF TA projects | Planned | 33 | 18 | 5 TAs and 2 DCs | 4 | 1 TA and 1 DC | [5 empty] | The public and private sector will utilise changes to policy / regulation The governments are keen to ensure they have effective policy in order to support RE/EE projects
|  | Achieved | Achieved. 33 TAs and 48 DCs | Not Achieved. 17 (11 TAs and 6 DCs) (In 2017, one of the PPTA. The IND project, was withdrawn from the portfolio. The schedule for the investment project will be delayed (for 2019) so the allocation for the PPTA was reverted to the Facility) | Achieved. 5 TAs and 2 DCs (In 2018, the additional financing for PRC: Developing Cost-Effective Policies and Investments to Achieve Climate and Air Quality Goals in the Beijing-Tianjin-Hebei Region was withdrawn from the portfolio (the funding was part of 2017 allocations). Revised end of 2018: 4 TAs and 2 DCs | Exceeded. 10 TAs and 2 DCs
Source
CEF TA annual results
| Output Indicator 5.2 |  | CEF TA portfolio 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Total amount ($) allocated to each type of TA project (in US $'000) | Allocations | 29144 | 17001.15 | 3425 | 10700
|  | CDTA | 17603 | 4690 | N/A | N/A | N/A | N/A
|  | PATA | 1842 | 4000 | N/A | N/A | N/A | N/A
|  | PPTA | 5575 | 7725 | N/A | N/A | N/A | N/A
|  | DCs | 4124 | 586.15 | 225 | 300 | N/A | N/A
|  | KSTA | N/A | N/A | 1800 | 6950
|  | TRTA | N/A | N/A | 1400 | 3450
CEF TA annual results
| Output Indicator 5.3 |  | CEF TA portfolio 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Percentage of TA project completion reports rated successful | Planned |  | 100% | 100% | 100% | 100%
|  | Achieved |  | Achieved. 100% (4 / 4 projects due for completion in 2016-2017 rated as successful) | Not Achieved. 8/9 or 89% of projects completed in 2017 were rated successful. Closed projects with 2016 allocation (CEF with UK contribution) 1 TA and 3 DCs with allocation from 2016 were financially closed in 2017. All were rated successful. These are: (1) TA-REG: Supporting the Asia solar energy Forum to Scale Up Solar energy Development in Asia and the Pacific (under TA REG: Empowering the Poor Through Increasing Access to Energy); and the direct charges (2) REG: 11th Asia Clean Energy Forum 2016; (3) REG: CAREC ESCC Investment Forum ; and (4) KAZ: Introducing the Auction Mechanism for Renewable Energy Projects. Closed projects with allocation before 2016 (CEF without UK contribution): 3 TAs and 2 DCs with funding before 2016 were financially closed in 2017. Two TAs and the 2 DCs were rated successful. These are: (1) REG: Asia Energy Efficiency Accelerator; (2) REG: Empowering the Poor through Increasing Access to Energy; (3) REG:External Evaluation of CEFPF and (4) REG: 10th Asia Clean Energy Forum. The PPTA outputs for the AZE: RE Development (Biomass Cogeneration) were achieved as envisaged. However, the government of AZE intends to postpone implementation of the proposed investment project to optimize government investment plan in consideration of fiscal constraints. The completion report cites "The completed feasibility study and due diligence conducted paved the road for project implementation in the future. Notwithstanding, the proposed project did not progress into a loan project as planned. Considering that, the PPTA is rated less than successful." | Achieved. Four TAs were financially closed in 2018; 2 TAs and 2 TALLs. 1 TA had a completion report by end of 2018 as planned (rated successful), 1 TA does not require a completion report due to being a PPTA and 2 TAs are due to submit their completion reports in 2019 as planned (due to be rated successful). The TA for AFG: Renewable Energy Development Project was financed in 2014 and was completed successfully in 2018. Eight DCs have completed their activities and were financially closed. All were rated successful.
|  | Source | [10 empty] | RISK RATING
|  | CEF TA annual results | [10 empty] | Low
| Output Indicator 5.4 |  | CEF TA portfolio 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Number, type and effectiveness of internal and external knowledge-sharing dissemination activities undertaken by the CEF TA portfolio as a whole (such as project outputs, fund-level impacts and lessons learned) | Planned | N/A (indicator implemented in 2019) | N/A (indicator implemented in 2019) | N/A (indicator implemented in 2019) | N/A (indicator implemented in 2019)
|  | Achieved | N/A (indicator implemented in 2019) | N/A (indicator implemented in 2019) | N/A (indicator implemented in 2019) | N/A (indicator implemented in 2019)
Source
CEF TA annual results
| Output Indicator 5.5 |  | CEF TA portfolio 2015 | 2016 | 2017 | 2018 | 2019 | 2020
| Number and percentage of women employed and/or supported by CEF TA projects per year and cumulatively since 2015, and the types of employment and support | Planned | N/A (indicator implemented in 2019) | N/A (indicator implemented in 2019) | N/A (indicator implemented in 2019) | N/A (indicator implemented in 2019)
|  | Achieved | N/A (indicator implemented in 2019) | N/A (indicator implemented in 2019) | N/A (indicator implemented in 2019) | N/A (indicator implemented in 2019)
Source
CEF TA annual results
Note on C139: C9C: knowledge support technical assistance
Note on C140: C9C: transaction technical assistance