## Logframe
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
FOREST CLIMATE LEADERS PARTNERSHIP (FCLP) SECRETARIAT
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Milestone 5 (2028) | Milestone 6 (2029) | Target (2030)
FCLP, as a government-led, policy-driven platform, leads to transformational change by facilitating and increasing members' ambition on tackling forest loss & land degradation in line with the Glasgow Leaders' Declaration and COP28 Global Stocktake Outcomes. FCLP makes a contribution toward halting and reversing forest loss and land degradation by 2030 while delivering sustainable development and promoting an inclusive rural transformation. | Level of increased ambition on actions to halt and reverse forest loss increased, measured on a qualitative scale: 0 - No increased ambition from FCLP member country on forests 1 - Increased ambition announced (within FCLP policy workstreams or cross-cutting elements such as country package, NDC, NBSAP) 2 - Increased ambition announced and implementation plans developed 3 - Increased ambition, implementation plan and initial actions taken to implement | Planned | 0 | 0 | 1 - 2 countries 2 - 0 countries 3 - 0 countries | 1 - 4 countries 2 - 2 countries 3 - 0 countries | 1 - 6 countries 2 - 4 countries 3 - 2 countries | 1 - 8 countries 2 - 6 countries 3 - 4 countries | 1 - 10 countries 2 - 8 countries 3 - 6 countries | 1 - 12 countries 2 - 10 countries 3 - 8 countries
|  | Achieved |  | NA | 1 - 7 countries 2 - 0 countries 3 - 0 countries |  |  |  | 1 - 10 countries 2 - 8 countries 3 - 6 countries
Source
Qualitative assessment of FCLP members' national policies, planning and engagement with FCLP workstreams.
| Impact Indicator 2 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Milestone 5 (2028) | Milestone 6 (2029) | Target (2030)
| Extent to which FCLP activity has led to transformational change (ICF KPI 15), assessed qualitatively. | Planned |  | NA
|  | Achieved |  | NA
Source
Member outreach; engagement tracker, annual member survey
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Milestone 5 (2028) | Milestone 6 (2029) | Target (2030) | Assumptions
High level political attention on forests & climate maintained | # commitments to GLD target (i.e. 2030 target to halt and reverse forest loss) in high-level communiques (cumulative). | Planned | 2 (G7 And UAE Consensus) | 4 | 6 | 8 | 10 | 12 | 14 | 14 (2 per year) | -Continued political will and support for FCLP at highest level. - Sufficient support and engagement of Global South members. - Sufficient funding for Secretariat. - Effective governance and governmental ownership.
|  | Achieved |  | NA | 8
Source
Internal tracking; Annual Progress Report; Audit of key global communiques related to climate and nature
High ambition outcomes driven across global policy action areas | Outcome Indicator 2 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Milestone 5 (2028) | Milestone 6 (2029) | Target (2030)
| # Members with Ministerial level demonstrations of renewed ambition on forests (cumulative) | Planned | 17 in 2023 | 17 | 20 | 30 | 40 | 60 | 80 | 100% of members
|  | Achieved |  | NA | 37
Source
Press Review; Event Review from COPs, Annual Progress Report
National forests & climate action advanced | Outcome Indicator 3 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Milestone 5 (2028) | Milestone 6 (2029) | Target (2030)
| Number of countries supported by TA (ICF TA KPI 1) through ringfenced funding for "Country Packages for Forests, Nature and Climate", to be disbursed between 2024-2026 (cumulative) | Planned | 0 | 1 | 3 | 5 | 5 | 5 | 5 | 5 | Ringfenced funding to support national "Country Packages for Forests, Nature and Climate" is to be disbursed in 2024-2026, therefore after this no further increase in the number of countries supported is envisaged.
|  | Achieved |  | NA | 7
Source
NDC submissions; Internal tracking
FCLP impact demonstrated | Outcome Indicator 4 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Milestone 5 (2028) | Milestone 6 (2029) | Target (2030)
| Number of commitments made by FCLP members (revised NDCs, announcements, policy reform) judged to have a positive impact on the 2030 GLD target which are actioned by member governments (cumulative) | Planned | 0 | 2 | 4 | 6 | 8 | 10 | 12 | 14
|  | Achieved |  | NA | 37
Source
FCLP annual reports; FCLP secretariat data on member action
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Milestone 5 (2028) | Milestone 6 (2029) | Target (2030) | Assumptions
FCLP members engage at highest level on forests, including at COP | Number of external-facing leader and ministerial-level FCLP meetings (cumulative). | Planned | 2 in 2023 (NYCW, UNFCCC COP) | 5 (NYCW, CBD COP 16 Cali, COP 29 Baku) | 7 (NYCW, COP 30 Belém) | 10 | 12 | 15 | 17 | 20 (2.5 per year) | Output 1.1 - Assumption that FCLP will host an extra event in every odd-numbered year due to CBD COPs in addition to annual UNFCCC COPs.
|  | Achieved |  | NA | 15
Source
Reports from high level meetings, including steering committee, mid-year ministerial, COP29/COP30 press package/press release
| Output Indicator 1.2 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Milestone 5 (2028) | Milestone 6 (2029) | Target (2030)
| # FCLP member announcements at COP featuring forests and land use (cumulative) | Planned | 10 (COP28 Press Releases) | 20 | 30 | 40 | 50 | 60 | 70 | 80 (10 per year)
|  | Achieved |  | NA | 37
Source
COP press releases; Government websites
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Milestone 5 (2028) | Milestone 6 (2029) | Target (2030)
40 | % of speakers of FCLP organised events who are women, global south, and/or indigenous peoples representatives (non-cumulative) | Planned | 30% (Public Ministerial event) | 35% | 40% | 45% | 50% | 50% | 50% | 50%
|  | Achieved |  | NA | 70%
|  | Source | [8 empty] | RISK RATING
FCLP Secretariat review of events and speakers
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Milestone 5 (2028) | Milestone 6 (2029) | Target (2030) | Assumptions
FCLP members deliver reforms focusing on the six policy action areas | Progress against policy action areas, measured on a qualitative scale: 0 - Progress against annual workplan not made in action area. 1 - Progress against annual workplan meets expectations in action area. 2 - Progress against annual workplan exceeds expectations in action area. Qualitative score to be calculated for each active policy action area (4 out of 6 as of 2025) and totalled for each year (non-cumulative). | Planned | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
|  | Achieved |  | NA | 3
Source
2024 Policy Plan signed off by Steering Committee; Co-chair letters to countries asking to co-lead
| Output Indicator 2.2 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Milestone 5 (2028) | Milestone 6 (2029) | Target (2030)
| % members actively participating in at least one working group throughout year | Planned | ?? | 50% | 55% | 60% | 75% | 80% | 85% | 90%
|  | Achieved |  | NA | 70%
Source
Working Group reports; Internal Tracking
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Milestone 5 (2028) | Milestone 6 (2029) | Target (2030)
25 | % of policy initiatives that mainstream gender and social inclusion (e.g. inclusion of Indigenous Peoples and Local Communities) | Planned | 20% (1 initiative) | 30% | 40% | 50% | 60% | 70% | 80% | 90%
|  | Achieved |  | NA | 80%
|  | Source | [8 empty] | RISK RATING
Feedback from GATC and other IP + LC organisations ; policy workplans and reports; IP & LC Engagement Plans
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Milestone 5 (2028) | Milestone 6 (2029) | Target (2030) | Assumptions
FCLP members advance national actions to achieve 2030 target of “halt and reverse deforestation” | Number of countries supported by UK TA for "Country Packages for Forests, Nature and Climate" (non-cumulative). | Planned | N/A | 1 | 3 | 5 | 5 | 5 | 5 | 5
|  | Achieved |  | NA | 7
Source
Internal Tracker; annual progress report
| Output Indicator 3.2 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Milestone 5 (2028) | Milestone 6 (2029) | Target (2030)
| Number of climate policies informed by UK TA for "Country Packages for Forests, Nature and Climate" (ICF TA KPI 3) (non-cumulative) | Planned | 0 | 0 | 2 | 4 | 4 | 4 | 4 | 4
|  | Achieved | NA | NA | 0
Source
Internal Tracker; annual progress report; press releases
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Milestone 5 (2028) | Milestone 6 (2029) | Target (2030)
25 | Public and private finance (ICF KPI 11 and 12) mobilised through the Country Packages for Forests, Nature and Climate (cumulative) | Planned | 0 | £10m | £15m | £20m | £25m | £30m | £35m | £40m
|  | Achieved |  | NA | £9.9m
|  | Source | [8 empty] | RISK RATING
Annual assessment of Country Packages progress through FCLP International Working Group on Country Packages
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Milestone 5 (2028) | Milestone 6 (2029) | Target (2030) | Assumptions
FCLP members demonstrate impact and accountability | Number of commitments made by FCLP members (revised NDCs, announcements, policy reform) judged to have a positive impact on the 2030 GLD target which are actioned by member governments (cumulative) | Planned | 3 | 2 | 4 | 6 | 8 | 10 | 12 | 14
|  | Achieved |  | NA | 7
Source
Internal tracking
| Output Indicator 4.2 |  | Baseline | Milestone 1 (2024) | Milestone 2 (2025) | Milestone 3 (2026) | Milestone 4 (2027) | Milestone 5 (2028) | Milestone 6 (2029) | Target (2030)
| # progress reports tracking 2030 goals developed or supported by FCLP (non-cumulative). | Planned | NA | 2 | 2 | 2 | 2 | 2 | 2 | 2
|  | Achieved | NA | 2 | 2
Source
Accountability framework, monitoring reports
IMPACT WEIGHTING (%)
10
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
Note on A6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We will need to develop a KPI15 methodology which has separate standardised scoring. I would suggest having this as a separate indicator
Note on A43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In the FCLP BC, it states that you’ll report against TA KPIs 1, 2 and 3. Do you want to include any of these as indicators within the logframe?