## Logframe
PROJECT TITLE | Forest Carbon Partnership Facility (FCPF) Carbon Fund
IMPACT | Impact Indicator 1 |  | Baseline: FY11 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | Target 2028
Reduction in global deforestation rates (REDD+ contributing to climate change mitigation keeping 2° within reach) | Forest area conserved or restored (million hectares/year) | Planned
|  | Achieved |  |  | N/A
Source
| Impact Indicator 2 |  | Baseline: FY11 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | Target 2028
| Net change in GHG Emissions (GTCO2e) | Planned
|  | Achieved |  |  | N/A
Source
| Impact Indicator 1 (previously 3) |  | Baseline: FY11 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | Target 2028
| Extent to which FCPF is likely to lead to transformational change | Planned | [9 empty] | 5
|  | Achieved |  |  | N/A |  | 4 | 4
Source
KPI15 - methodology defined in Results Note Collection
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline: FY11 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | Target 2028 | Assumptions
The FCPF Carbon Fund has strengthened governance, built institutional capacity and mobilised investment for sustainable forest management in participant countries, to equitably support Reduced Emissions from Deforestation and forest Degradation (REDD+), and has contributed to the creation of global standards for REDD+ | Number of Participant countries where learning, evidence and knowledge products generated through the FCPF has influenced other REDD+ programmes and practice | Planned |  | None set | [Targets to be set post-FY23, post influence evaluation] | [Targets to be set post-FY23, post influence evaluation] | 6: Countries indicate that other REDD+ programmes and practices have used FCPF knowledge products, and provide tangible examples of such influence (e.g. specific national processes or policies, benefit sharing, methodological framework). | 10: Countries indicate that other REDD+ programmes and practices have used FCPF knowledge products, and provide tangible examples of such influence (e.g. specific national processes or policies, benefit sharing, methodological framework). | 14: Countries indicate that other REDD+ programmes and practices have used FCPF knowledge products, and provide tangible examples of such influence (e.g. specific national processes or policies, benefit sharing, methodological framework). | 15: Countries indicate that other REDD+ programmes and practices have used FCPF knowledge products, and provide tangible examples of such influence (e.g. specific national processes or policies, benefit sharing, methodological framework). | 15: Countries indicate that other REDD+ programmes and practices have used FCPF knowledge products, and provide tangible examples of such influence (e.g. specific national processes or policies, benefit sharing, methodological framework). | 15: Countries indicate that other REDD+ programmes and practices have used FCPF knowledge products, and provide tangible examples of such influence (e.g. specific national processes or policies, benefit sharing, methodological framework). | Global climate change negotiations under UNFCCC remain supportive Suffcient programmes are entered into the pipeline and progress to ERPA stage Other REDD+ phase II programmes are in operation. Carbon Fund programmes are successfully implemented (see outputs 1 and 3) The incentives provided by REDD+ schemes are sufficient to motivate continued engagement from forest countries
|  | Achieved |  |  | N/A | N/A | N/A | Knowledge and communication products generated by FCPF developed to communicate lessons, experiences, tools and methods to a wide global audience represents a public good of clear added value | Knowledge and communication products generated by FCPF developed to communicate lessons, experiences, tools and methods to a wide global audience represents a public good of clear added value
Source
WB: 4.A - WB do not set targets NOTES Progress measured through 'influence' evaluation (results from evaluation will be ready end of FY23). Questions asked will be e.g.: Who has used FCPF knowledge products? How have FCPF knowledge products been used (tanglible examples of influence e.g. specific national processes or policies)?
| Outcome Indicator 1.2 |  | Baseline: FY11 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | Target 2028
| Number of Participant countries where FCPF has influenced REDD+ Country Participants' national approaches to sustainable forest resource management (including among women, women's groups, IPs, CSOs, local communities) | Planned |  | None set | [Targets to be set post-FY23, post influence evaluation] | [Targets to be set post-FY23, post influence evaluation] | 6: Countries indicate and provide evidence for FCPF influencing national approaches to sustainable forest resource management, provide evidence for specific governance approaches to support/deliver this, provide substantive evidence for engagement of CSOs, IPs and women's groups influencing national REDD+ processes. | 10: Countries indicate and provide evidence for FCPF influencing national approaches to sustainable forest resource management, provide evidence for specific governance approaches to support/deliver this, provide substantive evidence for engagement of CSOs, IPs and women's groups influencing national REDD+ processes. | 14: Countries indicate and provide evidence for FCPF influencing national approaches to sustainable forest resource management, provide evidence for specific governance approaches to support/deliver this, provide substantive evidence for engagement of CSOs, IPs and women's groups influencing national REDD+ processes. | 15 Countries indicate and provide evidence for FCPF influencing national approaches to sustainable forest resource management, provide evidence for specific governance approaches to support/deliver this, provide substantive evidence for engagement of CSOs, IPs and women's groups influencing national REDD+ processes. | 15 Countries indicate and provide evidence for FCPF influencing national approaches to sustainable forest resource management, provide evidence for specific governance approaches to support/deliver this, provide substantive evidence for engagement of CSOs, IPs and women's groups influencing national REDD+ processes. | 15 Countries indicate and provide evidence for FCPF influencing national approaches to sustainable forest resource management, provide evidence for specific governance approaches to support/deliver this, provide substantive evidence for engagement of CSOs, IPs and women's groups influencing national REDD+ processes.
|  | Achieved |  |  | N/A | N/A | N/A | (From FCPF evaluation) By August 2023, with 13 countries reporting emission reductions, there is initial evidence of behavior change regarding the improved management of forests, including strengthened protection and conservation of high-biodiversity forests and sustainable forest management practices by businesses, communities and households. | (From FCPF evaluation) By August 2023, with 13 countries reporting emission reductions, there is initial evidence of behavior change regarding the improved management of forests, including strengthened protection and conservation of high-biodiversity forests and sustainable forest management practices by businesses, communities and households.
Source
WB: OV.1.a (WB do not set targets) NOTES Qualitative progress measured through evaluation (results will be ready end of FY23. Questions such as: How has FCPF influenced national approaches to sustainable forest resource management? What specific governance approaches are most effective for delivering and supporting sustainable forest resource management? How does the engagement of certain stakeholder groups (CSOs, IPs, women's groups) influence national REDD+ processes? Is this influence substantive (if so, why)? Are there notable differences between countries with broad representation and countries with limited representation?
| Outcome Indicator 1.3 |  | Baseline: FY11 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | Target 2028
| Net change in Greenhouse Gas Emissions (tCO2e) – tonnes of GHG emissions reduced or avoided from CF programmes | Planned | 0 | 0 | 14 million | 30.5 million | 47 million | 88 million | 121625000 | 137750000 | 153875000 | 170000000
|  | Achieved |  |  | No data available | 5 million | 76.56 million | 105.5 million | 123700000
Source
WB: Indicator I.1.A NOTES For FY22 and FY24, interim milestones were set by DESNZ using a linear trend approach with WB-set milestones/target, and are not formally set from WB milestones (which have not been set for these years). These are to aid UK Annual Review reporting. For FY25, FY26 and FY27 (after the programme was extended to 2028), interim milestones were set by DESNZ based on FY24 achieved results and the WB 2028 target through a simple linear trajectory to aid with scoring components for Annual Review processes.
| Outcome Indicator 1.4 |  | Baseline: FY11 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | Target 2028
| Volume of finance mobilised for climate change purposes as a result of ICF funding (disaggregated by non-ODA public finance and private finance) | Planned | 0 | None set | N/A | N/A | N/A | N/A | $592.25 million | $621.5 million | $650.75 million | $680 million
|  | Achieved |  |  | N/A | $229 million (99% public, 1% private, 3% ERPs, 22% grants) | $432 million (99% public, 1% private, 30% ERPs, 24% grants, 6% loans, 0.1% equity) | $574 million (99% public, 1% private, 42% ERPs, 25% grants, 5% loans, 0.5% equity) | $859 million (96% public, 4% private, 41% ER programmes, 30% grants, 6% loans and 0.4% equity)
Source
WB: 2B for Carbon Fund (WB will not set targets). KPI 11/12 NOTES In FY25, the World Bank revised previous achieved results due to an error found in the calculations. For FY25, FY26 and FY27, milestones have been set by DESNZ using a linear trend approach ustilising the (revised) FY24 achieved result and the end of programme target.
OUTPUT 1 | Output Indicator 1.1 |  | Baseline: FY11 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | Target 2028
Emissions Reductions Programmes planned and implemented/ progressing through the Carbon Fund process | a) Amount of disbursements for ER payments ($, cumulative) b) Actual ERs purchased by CF as % of originally committed ERs (as per ERPA) - Percentage progress | Planned | a) 0 b) N/A | a) None set b) None set | a) To be set in FY22 b) 9% | a) 11.3m b) *19% | a) 32.6m b) 3% | a) 94.0m b) 8% | a) 271.3m b) 22% | a) 441.7m b) 35% | a) 612.2m b) 47% | a) $782.7m - available for purchases of ERs (incl Call Options) b) $721.3m - total ERPA contract b) 60% of expected the 145mtCO2EQ of Ers from ERPAs
|  | Achieved |  | a) 0 b) | a) N/A b) N/A | a) $11.3m (including advance payments) b) 1% | a) $53.2m (including advance payments) b) 3.8% | a) $164.5m (including advance payments) b) 12.6% | a) $235.45m b) 30%
Source
For 1.1.a WB will not include this indicator. Target to be equivalent to the fund size less all costs, what is shown in our Portfolio Update presentations as "Available for Purchase of ERs''. For 1.1.b) WB: 2.4.c The indicator is calculated by comparing ERs actually purchased by the Carbon Fund with indicator 2.A (Number of tons of CO2e emission reductions and removals committed through signed ERPAs). NOTES FY22, FY24 and FY25 milestones are set by UK BEIS to aid UK annual review reporting. These are not formally set by the WB. - these have been calculated using a growth with trend approach derived from WB set milestones and target. Initially, we tried to use a regression approach to calculate targets but discovered that variables were not yielding statistically significant results. Developing a sophisticated econometric approach would take up disproportionate resources. Thus, for FY22–FY25, we assumed constant growth rates to set milestones based on achieved results and final targets. For FY26 and FY27 (after the programme was extended to 2028), interim milestones were set by DESNZ by applying a linear interpolation method, ensuring a steady progression toward the final 2028 target value.
| Output Indicator 1.2 |  | Baseline: FY11 | Milestone 1: FY19 | Milestone 2: FY20 | FY21 | FY22 |  |  | Target: FY23
| Number of Participant countries that have fulfilled conditions of effectiveness and are monitoring ERs | Planned | 0 | None set | 4 | 16 | 14 |  |  | 15
|  | Achieved |  |  | 2 | 3 | 12 |  |  | 15
Source
Monthly CF portfolio reports, CF dashboard, Annual Meeting Portfolio Updates. Re-baselined to account for ERPAs signed (15)
| Output Indicator 1.3 |  | Baseline: FY11 | Milestone 1: FY19 | Milestone 2: FY20 | FY21 | FY22 |  |  | Target: FY23
| Percentage (%) of Participant countries which have fulfilled conditions of effectiveness within 12 months of ERPA signature (/ the agreed timeframe set out in the country’s ERPA). | Planned | 0 | None set | 50% | 80% | 80% |  |  | 80%
|  | Achieved |  |  |  | 33% | 16% (2 out of 12 countries) Ghana, Indonesia DR, Fiji, Madagascar, Mozambique missed by 1 month
Source
Monthly CF portfolio reports, CF dashboard (cumulative) NOTE: we have decided ‘grey-out’ 1.3 to keep the history of what data we have collected and why, shows transparency going forwards and there is not a strong rationale to remove it just because target is now unachievable
| Output Indicator 1.4 |  | Baseline: FY11 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | Target: FY26
| Actual ERs purchased by CF as % of originally committed ERs (as per ERPA) | Planned | N/a | None set | 9% | * 19% | 29% | * 39% | * 50% | 60%
|  | Achieved |  |  | N/A | 1% |  | 12.6%
bb
2.4.c - The indicator is calculated by comparing ERs actually purchased by the Carbon Fund with indicator 2.A (Number of tons of CO2e emission reductions and removals committed through signed ERPAs). * NOTE: FY22, FY24 and FY25 milestones are set by UK BEIS to aid UK annual review reporting. These are not formally set by the WB. - these have been calculated using a linear trend approach derived from WB set milestones and target NOTE: This indicator has been combined with Output 1.1.
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline: FY11 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | Target 2028 | RISK RATING
40 | Efficient implementation of ER programmes. a) Number of Monitoring Reports submitted (cumulative) b) Number of Monitoring Reports successfully verified/validated (cumulative) | Planned |  |  | a) N/A b) N/A | a) N/A b) N/A | a)18 b) 5 | a) 23 b)12 | a) 31 b) 27 | a) 44 b) 29 | a) 45 b) 44 | a) EOP: 45 b) EOP: 45 | Output depends on a significant number of assumptions and external factors. ERPAs are innovative, and there is a lack precedents on which to base projections
|  | Achieved |  |  | a) 5 b) N/A | a) 11 b) 1 | a) 15 (13 first MRs and 2 second MRs) b) 5 [from Sept quarterly - CR, Ghana, Madagascar, Mozambique x2] | a) 19 b) 7 | a) 22 b) 15
Source
WB do not currently report on this indicator (it is a UK indicator) Source: Quarterly portfolio report milestones dashboard. For b), the portfolio reports provide the number of monitoring reports concluded and published by 30 June. NOTES Assumption countries will submit for each reporting period outlined in ERPA - may not materialise. After the extension of the programme to 2028, DESNZ set FY25-FY27 milestones based on expected and achieved dates outlined in the WB July 2024 Portfolio Report
OUTPUT 2 | Output Indicator 2.1 |  | Baseline: FY11 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | Target 2028 | Assumptions
Countries implement programmes that conserve biodiversity and contribute positively to local socio-economic development, as well as generating emission reductions | Number of Participant countries and extent to which FCPF has supported country efforts to sustain and enhance livelihoods within REDD+ interventions areas (including among women, women's groups, IPs, CSOs, and local communities) | Planned | TBD | None set | [Targets to be set post-FY23, following non-carbon benefits evaluation] | [Targets to be set post-FY23, following non-carbon benefits evaluation] | 6: Countries provide evidence that REDD+ interventions have changed livelihoods for people living and working in project area, including different groups (women, IP, CSO), with evidence of specific FCPF processes/requirements having a signficant influence, and such FCPF processes being applied beyond intervention areas | 10: Countries provide evidence that REDD+ interventions have changed livelihoods for people living and working in project area, including different groups (women, IP, CSO), with evidence of specific FCPF processes/requirements having a signficant influence, and such FCPF processes being applied beyond intervention areas | 12: Countries provide evidence that REDD+ interventions have changed livelihoods for people living and working in project area, including different groups (women, IP, CSO), with evidence of specific FCPF processes/requirements having a signficant influence, and such FCPF processes being applied beyond intervention areas | 13: Countries provide evidence that REDD+ interventions have changed livelihoods for people living and working in project area, including different groups (women, IP, CSO), with evidence of specific FCPF processes/requirements having a signficant influence, and such FCPF processes being applied beyond intervention areas | 14: Countries provide evidence that REDD+ interventions have changed livelihoods for people living and working in project area, including different groups (women, IP, CSO), with evidence of specific FCPF processes/requirements having a signficant influence, and such FCPF processes being applied beyond intervention areas | 15: Countries provide evidence that REDD+ interventions have changed livelihoods for people living and working in project area, including different groups (women, IP, CSO), with evidence of specific FCPF processes/requirements having a signficant influence, and such FCPF processes being applied beyond intervention areas | External context remains supportive and conducive to implementation of programmes
|  | Achieved |  |  | N/A | N/A | N/A | (From FCPF evaluation) By August 2023, ER-Ps have directly supported livelihoods improvements in six countries. These have been achieved through enhanced revenues from agriculture, tree nurseries, non-timber forest products, timber products, and tourism. Clarified land tenure and improved access to basic services have also been reported. At least three countries are likely to have generated climate change adaptation benefits. | (From FCPF evaluation) By August 2023, ER-Ps have directly supported livelihoods improvements in six countries. These have been achieved through enhanced revenues from agriculture, tree nurseries, non-timber forest products, timber products, and tourism. Clarified land tenure and improved access to basic services have also been reported. At least three countries are likely to have generated climate change adaptation benefits.
Source
WB: 3A - WB will not set targets - these are DESNZ set targets NOTES This indicator will be formally assessed at each programme-wide third-party evaluation. WB results from external 'non-carbon benefits' evaluation will be included and reflected. Questions asked such as: How have REDD+ interventions changed livelihoods for people living and working in project areas? How have different groups been affected (women, IPs, local communities)? What specific FCPF processes or requirements had a significant influence on livelihoods in project areas? What was the nature of this influence? Have FCPF processes or FCPF-related learning been applied beyond intervention areas to sustain or enhance livelihoods?
| Output Indicator 2.2 |  | Baseline: FY11 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | Target 2028
| % of carbon benefits paid from CF programs shared with beneficiaries (disaggregated by gender, CSOs, IPs, Local Communities) | Planned | 0% | 0% | To be set once all final BSPs published | To be set once all final BSPs published | To be set once all final BSPs published | To be set once all final BSPs published | To be set in FY26 |  |  | 72%
|  | Achieved |  | 0 | N/A | 0% | 0% | 35% (of which 34% government entities; 55% local communities) | 26% (of which 34% government entities; 52% local communities)
Source
WB: 2D - WB will set milestones/target from BSPs in FY22. Will be reported annually NOTES In FY25, this indicator was revised by indicator and updated by DESNZ accordingly. It was previously "% of monetary benefits from CF programmes shared with beneficiaries (disaggregated by gender, CSOs, IPs, Local Communities)"
| Output Indicator 2.3 |  | Baseline: FY11 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | Target 2028
| Number of benefit sharing plans implemented & types of benefits being shared with a diverse range of beneficiaries (gender, CSOs, IPs, LCs) | Planned | 0% |  |  |  | 3 BSPs implemented with evidence of benefits (monetary and non-monetary) being shared with a diverse range of beneficaries (gender, CSOs, IPs, LCs) | 11 BSPs implemented with eivdence of benefits (monetary and non-monetary) being shared with a diverse range of beneficaries (gender, CSOs, IPs, LCs) | 15 BSPs implemented with evidence of benefits (monetary and non-monetary) being shared with a diverse range of beneficiaries (gender, CSOs, IPs, LCs) | 15 BSPs implemented with evidence of benefits (monetary and non-monetary) being shared with a diverse range of beneficiaries (gender, CSOs, IPs, LCs) | 15 BSPs implemented with evidence of benefits (monetary and non-monetary) being shared with a diverse range of beneficiaries (gender, CSOs, IPs, LCs) | 15 BSPs implemented with evidence of benefits (monetary and non-monetary) being shared with a diverse range of beneficaries (gender, CSOs, IPs, LCs)
|  | Achieved |  |  |  |  | 3 being implemented - Mozambique, Ghana, Costa Rica | 3 being implemented - Mozambique, Ghana, Costa Rica | 12 being implemented - Chile, Costa Rica, Côte d'Ivoire, DRC, Dominican Republic, Ghana, Guatemala, Indonesia, Lao PDR, Madagascar, Mozambique and Vietnam
Source
UK qualitative Indicator - miletones set through ERPA payment projections from Portfolio Reports (BSPs should be implemented within six months of first ER payments). NOTES In FY25, after the FCPF was extended to 2028, milestones for FY25-FY27 were updated using projected and achieved payments from June 2024 Portfolio Report. BSP implementation can be tracked from Quarterly progress calls and Carbon Fund Meetings. Types of benefits shared can be tracked from Monitoring Report Submissions (starting from 2nd MR submissions)
| Output Indicator 2.4 |  | Baseline | Milestone 1 FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | Target 2028
| Number of Carbon Fund Programmes that test ways to sustain and enhance livelihoods. | Planned | 0 | 4 | 9 | 12 | 14 | 15 | 15 | 15 | 15 | 15
|  | Achieved |  |  | 18 | 18 ; 2 | 18 ; 7 | 18 ; 8 | 15
Source
WB: 3.2.a NOTES In the results, the first number refers to the programmes with planned tests, and the second number refers to the programmes that are actually testing ways to sustain and enhance livelihoods. FY22, FY24, FY25, FY26, FY27 milestones are set by DESNZ and do not align with WB milestones (which are not set). From FY25, DESNZ will report only on the 15 countries currently in the pipeline. Previously, we reported on all 18 countries originally in the FCPF Carbon Fund pipeline. As a result, the DESNZ EOP target does not align with the WB EOP target.
IMPACT WEIGHTING (%) | Output Indicator 2.5 |  | Baseline | Milestone 1 FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | Target 2028 | RISK RATING
50 | Number of Carbon Fund Programmes that test ways to conserve biodiversity | Planned | 0 | 14 | 16 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | Design of programme documents should ensure that these aspects of a programme are considered and delivered
|  | Achieved |  |  | 18 | 18 ; 2 | 18 ; 7 | 18 ; 8 | 15
Source
WB: 3.3.a NOTES In the results, the first number refers to the programmes with planned tests, and the second number refers to the programmes that are actually testing ways to conserve biodiversity. FY22, FY24, FY25, FY26, FY27 milestones are set by DESNZ and do not align with WB milestones (which are not set). From FY25, DESNZ will report only on the 15 countries currently in the pipeline. Previously, we reported on all 18 countries originally in the FCPF Carbon Fund pipeline. As a result, the DESNZ EOP target does not align with the WB EOP target.
OUTPUT 3 | Output Indicator 3.1 |  | Baseline: FY11 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | Target 2028 | Assumptions
Knowledge gained in the development of the FCPF and implementation of ER programmes are broadly shared and used by international REDD+ practitioners within and beyond FCPF country participants | Number of non-FCPF programmes and countries that have adopted elements of the FCPF Methodological Framework within their own REDD+ processes | Planned | N/A | None set | Reporting begins set post-FY23 evaluation | Reporting begins set post-FY23 evaluation | Reporting begins set post-FY23 evaluation | Reporting begins set post-FY23 evaluation | N/A | N/A | N/A | N/A | Other mechanisms to support REDD+ exist
|  | Achieved |  |  | N/A | N/A | N/A | (From FCPF evaluation) There is strong evidence of a growing number of users of FCPF knowledge products as evidenced by the increase in website visitors, interviews indicating influence on other REDD+ mechanisms, and improvements in FREL estimates by some countries due to their experience with the FCPF process. | (From FCPF evaluation) There is strong evidence of a growing number of users of FCPF knowledge products as evidenced by the increase in website visitors, interviews indicating influence on other REDD+ mechanisms, and improvements in FREL estimates by some countries due to their experience with the FCPF process.
Source
WB: 4.3b (note: not setting targets but quantities and examples are reported annually) NOTES Progress measured through periodic evaluation - as part of influence evaluations, program documentation of other major REDD+ donors, and the national REDD+ Strategies, NDCs and BURs of non-participant countries should be reviewed to identify whether and where FCPF Methodological Framework elements have been adopted. This systematic process is likely to be augmented through informal channels, e.g. FCPF stakeholders (FMT, Participants) hearing about a specific country’s usage of the Methodological Framework.
| Output Indicator 3.2 |  | Baseline: FY11 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | Target 2028
| Number of (a) FCPF-supported South-South learning acitivites and/or events connecting FCPF countries; & (b) Participants in such activities (disaggregated by gender, CSOs, IPs) | Planned |  | (a) 8 (b) 300 (105; 30; 30) | (a) 10 (b) 400 (160; 40; 40) | (a) 12 (b) 425 (170; 43; 43) | (a) 14 (b) 450 (180; 45; 45) | (a) 14 (b) 466 (186; 47; 47) | (a) 75 (b) 5351 (1934; 778; 550) | (a) 78 (b) 5467 (1989; 785; 557) | (a) 81 (b) 5584 (2045; 793; 563) | a) 84 b) 5700 (2100; 800; 570)
|  | Achieved |  |  | (a) 29 (b) 1500+ (650; 210; 220) | (a) 45 (b) 3400+ (of which 1300 women; 640 CSOs; 350 IPs) | (a) 61 (b) 4100+ (of which 1450+ female; 732 CSO; 382 IP) | (a) 72 (b) 5234+ (of which 1878+ female; 770 CSO; 543 IP) | (a) 78 (b) 5,588+ (of which 2,027+ female; 783 CSO; 555 IP)
|  | Source | [10 empty] | RISK RATING
|  | WB 4.2.a and 4.2.b NOTES For milestones FY22; FY24; FY25; FY26; FY27, these have been calculated by the BEIS team using a linear trend approach utilising WB-set milestones and end of programme target. These FYs do not align with WB milestones (which have not been set for these years). These are to aid UK Annual Review reporting. In FY24, the WB revised the EOP target upwards as it had already been achieved. DESNZ updated the FY25 milestones and added FY26 and FY27 milestones using a linear trend from achieved FY24 result and the EOP target. | [10 empty] | Transparency of the fund is widely recognised facilitating the sharing of knowledge gained
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline: FY11 | Milestone 1: FY19 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | Target 2028
10 | Percentage (%) of participants in South-South learning activities indicating that they will apply the new knowledge or skills in their work | Planned | N/A | 50 | 60 | 65 | 70 | 71 | 72 | 73 | 74 | 75%
|  | Achieved |  | 94 | 88% (of which 49% female, 44% CSO, 32% IPs) | 81% (of which 35% women; 30% CSOs; 22% IPs) | 82% (of which 35% female; 30% CSO; 22% IP) | 82% (of which 33% female; 25% CSO; 21% IP) | 83% (of which 35% female; 19% CSO; 19% IP)
Source
WB 4.2C NOTES Disaggregations will be reported For milestones FY22, FY24 and FY25, these have been calculated by the BEIS team using a linear trend approach utilising WB-set milestones and end of programme target. These do not align with WB milestones (which have not been set for these years). These are to aid UK Annual Review reporting.