## NDCP Support Logframe
IMPACT | Impact Indicator 1 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target (2031)
Countries successfully reduce emissions, improve climate resilience, and advance sustainable development, with strong international support consistent with the achievement of the Paris Agreement and the 2030 agenda for Sustainable Development | The extent to which the NDC Support package is likely to lead to transformational change (ICF KPI 15) | Planned | 3 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5
|  | Achieved |  | 3
Source
NDC Support KPI 15 assessment
| Impact Indicator 2 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target (2031)
| Number of member countries, receiving Partnership support, with reduced GHG emissions reported between 2021 and 2025 (compared on a year-on-year basis) (Partnership level indicator) | Planned | 31 | 70 | 70
|  | Achieved |  | 28
Source
The Support Unit provided data when the programme team commissioned them.
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target (2031) | Assumptions
Accelerated NDC Implementation - Developing country members on track or ahead of schedule to implement NDCs. | % of member countries receiving Partnership support that reported being on track or ahead of schedule in meeting their NDC mitigation and adaptation targets (Partnership level indicator) | Planned | 60% | 60% | 80% | [6 empty] | Countries continue to align with and engage with the Paris Agreement, and NDCs remain the key tool to enable countries to plan for and deliver emissions reductions.
|  | Achieved |  | 80%
Source
Latest NDC Partnership Work Programme Annual Progress Report.
| Outcome Indicator 1.2 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target (2031)
| % of member countries receiving support through the UK NDC support package that reported being on track or ahead of schedule in meeting their NDC mitigation and adaptation targets (UK level indicator), diaggregated by: i) total ii) PAF iii) CEF iv) FR | Planned | a) 60% b) 87% c) 100% d) 90% | a) 60% b) 60% c) 60% d) 60% | a) 60% b) 87% c) 100% d) 90%
|  | Achieved |  | a) 60% b) 87% c) 100% d) 90% | a) b) c) d) | a) b) c) d) | a) b) c) d) | a) b) c) d) | a) b) c) d) | a) b) c) d)
Source
a) Latest NDC Partnership Work Programme Annual Progress Report. b-d) Commission SU for full list then calculate
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target (2031) | Assumptions
Raised ambition and quality of climate action - Developing country members communicate new NDCs reflecting increased quality and ambition by 2030 | (a) % of developing country members submitting an NDC with increased ambition. (Partnership level indicator) | Planned | 0% | N/A | 70% | N/A | N/A | N/A | N/A |  |  | Political engagement and use of NDC Partnership as a platform/vehicle for support in developing member countries is sustained and expanded leading to increased mitigation ambition and strengthening national ownership. To note: As NDCs are only published on a five year cycle, this outcome will only be measured through the logfram in FY 25/26 and FY 30/31.
|  | Achieved |  | N/A |  | N/A | N/A | N/A | N/A
| (b) % of developing country members supported by the UK submitting an NDC with increased ambition (UK level indicator), disaggregated by: i) total ii) PAF iii) CEF iv) FR | Planned | 0% | N/A | a) 70% b) 70% c) 70% d) 70% | N/A | N/A | N/A | N/A
|  | Achieved |  | N/A | a) b) c) d) | N/A | N/A | N/A | N/A | a) b) c) d)
Source
a) Latest NDC Partnership Work Programme Annual Progress Report. b-d) Commission SU for full list then calculate
| Outcome Indicator 2.2 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target (2031)
| (a) % of developing country members that submit an updated NDC with improved quality. (Partnership level indicator) | Planned - Partnership | 0% | N/A | 100% | N/A | N/A | N/A | N/A
|  | Achieved - Partnership |  | N/A |  | N/A | N/A | N/A | N/A
| (b) % of developing country members supported by the UK that have submitted an updated NDC with improved quality (UK level indicator) diaagregated by: i) total ii) PAF iii) CEF iv) FR | Results - UK | a) 100% b) 100% c) 100% d) 100% | N/A | a) 100% b) 100% c) 100% d) 100% | N/A | N/A | N/A | N/A | a) b) c) d) | a) b) c) d)
|  |  |  | N/A | a) b) c) d) | N/A | N/A | N/A | N/A | a) b) c) d)
Source
a) Latest NDC Partnership Work Programme Annual Progress Report. b-d) Commission SU for full list then calculate
INTERMEDIATE OUTCOME 1 | Int. Outcome Indicator 1.1 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target (2031) | Assumptions
Increased Access to Climate Finance - Developing countries receive increased investment flows towards climate action. | Total values of technical assistance disbursed to support NDC Partnership member requests (cumulative). (Partnership level indicator) | Planned - Partnership | USD 0.7bn | USD 1.5bn | [7 empty] | Climate finance is supporting countries appropriately to develop, enhance and implement their NDCs. Planned spend updated in AUG 2025 allowing for ODA cuts and change to spend profile from original business case.
|  | Achieved - Partnership |  | USD 1.8bn
Source
Latest NDC Partnership Work Programme Annual Progress Report.
INTERMEDIATE OUTCOME 2 | Int. Outcome Indicator 2.1 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target (2031) | Assumptions
NDCs are mainstreamed into development plans and budgets - Developing countries integrate NDCs into development plans alongside SDGs. | (a) % of developing country members that have integrated NDC measures into the next cycle of national/subnational/sectoral development plans and/or budgets. (Partnership level indicator) | Planned | 30% | 60% | 70% |  |  |  |  | 100% | 100% | Plans developed which include NDC and SDG goals are deliverable and able to support countries to reduce emissions in line with the Paris Agreement.
|  | Achieved |  | 61%
Source
Latest NDC Partnership Work Programme Annual Progress Report.
| (b) % of developing country members supported by the UK’s first response (both bilateral and through institutional members), that have integrated NDC measures into the next cycle of national/subnational/sectoral development plans and/or budgets (UK level indicator) | Planned | 60% | 60% | 70% | 76% | 82% | 88% | 94% | 100% | 100%
|  | Achieved |  | 40%
Source
Latest NDC Partnership Work Programme Annual Progress Report.
| Int. Outcome Indicator 2.2 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target (2031)
| (a) % of developing country members that have mainstreamed low carbon climate resilient investment projects in their development plans and/or budgets. (Partnership level indicator) | Planned - Partnership | 60% | 60% | 70% |  |  |  |  | 100% | 100%
|  | Achieved - Partnership |  | 72%
Source
Latest NDC Partnership Work Programme Annual Progress Report.
| (b) % of developing country members supported by the UK (via the Country Engagement Fund, Institutional member 'First Response), that have mainstreamed low carbon climate resilient investment projects in their development plans and/or budgets. (UK level indicator) | Planned - UK | 60% | 60% | 66% | 74% | 80% | 86% | 92% | 100% | 100%
|  | Achieved - UK |  | 48%
Source
Latest NDC Partnership Work Programme Annual Progress Report. The Support Unit provided the data and rationale when commissioned by the programme team.
FY 24/25 'planned' vlaues not included as delivery was set up during this period and estimations on delviery were not made.
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target | Assumptions
Improved coordination and quality of demand and supply of support. | 1.1 Number of developing country members who have received support via the Partnership in the previous review period, disaggregated by, (i) Total supported by the Partnership (ii) Those supported by the Country Engagement Fund. (TA KPI 1) (iii) Those supported by institutions funded though the UK’s institutional first response element. (TA KPI 1) (iv) those supported by the Partnership Action Fund (TA KPI 1) | Planned | (i) 101 (ii) 21 |  | (i) 100 (ii) 20 (iii) 20 (iv) 75 | (i) 100 (ii) 20 (iii) 10 (iv) 75 | (i) 100 (ii) 20 (iii) 20 (iv) 75 | (i) 100 (ii) 20 (iii) 10 (iv) 75 | (i) 100 (ii) 20 (iii) 40 (iv) 75 | (i) 100 (ii) 20 (iii) 10 (iv) 75 | (i) 100 (ii) 20 (iii) 10 (iv) 75 | The Partnership’s country engagement processes continue to enable countries to request and then access support from development and institutional members.
|  | Achieved |  | (i) 101 (ii) 21 | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii)
Source
(i) Latest NDC Partnership Work Programme Annual Progress Report (ii) CEF tracker (iii) The Climate Promise Pledge to impact Annual Report and the CSF Annual Report (iv) PAF Annual report
| Output Indicator 1.2 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target
| 1.2 Number of partners providing support to requests made by developing country members in the previous review period, disaggregated by; (i) members of the partnership (ii) non-members of the partnership | Planned | (i) 81 (ii) 229 |  | (i) 80 (ii) 230 | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii)
|  | Achieved |  | (i) 81 (ii) 229 | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii)
Source
Latest NDC Partnership Work Programme Annual Progress Report.
| Output Indicator 1.3 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target
| 1.3 % of implementing and development partner members (who repsonded to the members survey) that have used Partnership data and insights (from kNook, peer exchanges, knowledge products or the Knowledge Portal) to programme support and make decisions in the previous review period. | Planned | 94% |  | 60%
|  | Achieved |  | 94%
IMPACT WEIGHTING (%) |  | Source
30% |  | Latest NDC Partnership Work Programme Annual Progress Report.
| Output Indicator 1.4 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target
| 1.4 Number of knowledge and learning products or convenings created/delivered by the Partnership’s Support Unit in the previous review period that make use of the knowledge gaps identified though the partnership. | Planned | 298 |  | 300
|  | Achieved |  | 298
Source
Latest NDC Partnership Work Programme Annual Progress Report.
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target (2031) | Assumptions
Capacity and capability of developing countries increases. | 2.1 Number of individual embedded advisors and NDC Partnership facilitator roles funded by the Partnership (including PAF, the Country Engagement Fund and other mechanisms) disaggregated by, (i) those funded within the previous review period (based on ‘active contracts’) (ii) those funded over the lifetime of the Partnership (cumulative) | Planned - Partnership | (i) 92 (ii) 239 |  | (i) 92 (ii) 250 | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) 90 (ii) 350 | (i) 90 (ii) 350 | Technical assistance provided is relevant, suitable to the context and results in developing sustainable institutional knowledge and capacity which catalyses further behaviour change.
|  | Achieved - Partnership |  | (i) 92 (ii) 239 | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii)
Source
Latest NDC Partnership Work Programme Annual Progress Report.
| Output Indicator 2.2 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target (2031)
| 2.2 Number of individual embedded advisors and NDC Partnership facilitator roles funded by the UK Country Engagement Fund disaggregated by, (i) those funded in the previous review period (based on ‘active contracts’) (ii) those funded over the lifetime of the Country Engagement Fund (cumulative) | Planned | (i) 11 (ii) 11 |  | (i) 20 (ii) 20 | (i) 20 (ii) 24 | (i) 20 (ii) 28 | (i) 20 (ii) 32 | (i) 20 (ii) 36 | (i) 20 (ii) 40 | (i) 20 (ii) 40
|  | Achieved |  | (i) 11 (ii) 11 | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii)
Source
(i) CEF Tracker (ii) CEF Tracker
| Output Indicator 2.3 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target (2031)
| 2.3 Gender identity split (%man /%woman) of embedded advisors and NDC Partnership facilitator roles funded by: (i) The Partnership (including PAF, the Country Engagement Fund and other mechanisms) (ii) the UK Country Engagement Fund | Planned | (i) 68% male, 32% female (ii) 46.6% male 53.3% female |  | (i) 68% male, 32% female (ii) 50/50 | (i) 64 (ii) 50/50 | (i) 60 (ii) 50/50 | (i) 57 (ii) 50/50 | (i) 53 (ii) 50/50 | (i) 50/50 (ii) 50/50 | (i) 50/50 (ii) 50/50
|  | Achieved |  | (i) 68% male, 32% female (ii) 46.6% male, 53.3% female | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii)
Source
(i) Latest NDC Partnership Work Programme Annual Progress Report or commission SU data if total EA and F is not provided (ii) Comission SU
| Output Indicator 2.4 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target (2031)
| 2.4 Number of countries with multiple embedded advisors and or NDC partnership facilitator roles being funded by the Country Engagement Fund within the previous review period. | Planned | 1 |  | 3 | 3 | 4 | 4 | 5 | 6 | 6
|  | Achieved |  | 1
Source
CEF Tracker
| Output Indicator 2.5 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target
| 2.5 Number of developing country members with embedded advisors and/or NDC Partnership facilitator roles funded reporting that they have increased knowledge and/or capacity for NDC implementation, disaggregated by, (i) Those funded by the Country Engagement Fund (ii) Those funded by the Partnership Action Fund (PAF) | Planned | (i) 8 (ii) 30 |  | (i) 20 (ii) 75 | (i) 20 (ii) | (i) 20 (ii) | (i) 20 (ii) | (i) 20 (ii) | (i) 20 (ii) | (i) 20 (ii)
|  | Achieved |  | (i) 8 (ii) 30 | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii)
Source
(i) Comission SU (ii) Comission SU/ PAF team
| Output Indicator 2.6 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target (2031)
| 2.6 Number of developing country members with embedded advisors and/or NDC Partnership facilitator roles funded reporting that they have increased whole of government and whole of society engagement, disaggregated by, (i) Those funded by the Country Engagement Fund (ii) Those funded by the Partnership Action Fund (PAF) | Planned | (i) 7 (ii) 27 |  | (i) 20 (ii) 75 | (i) 20 (ii) | (i) 20 (ii) | (i) 20 (ii) | (i) 20 (ii) | (i) 20 (ii) | (i) 20 (ii)
|  | Achieved |  | (i) 7 (ii) 27 | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii)
Source
(i) Comission SU (ii) Comission SU/ PAF team
IMPACT WEIGHTING (%) | Output Indicator 2.7 (KPI 2.2) |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target (2031)
30% | Number of organisations (ministries/government institutions) supported by the UK, disaggregated by: (i) Those funded by the Country Engagement Fund (ii) Those funded by the Partnership Action Fund (PAF | Planned | (i) 10 (ii) 69 |  | (i) 20 (ii) 69 | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii)
|  | Achieved |  | (i) 10 (ii) 69 | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii)
Source
(i) CEF Tracker (ii) Comission SU/PAF team
OUTPUT 3 | Output Indicator 3.1 (KPI 15) |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target
Developing countries establish and enhance climate plans, Policies and processes | 3.1 Number of NDCs submitted to the UNFCCC from developing country members supported through the Partnership disaggregated by, (i) total number supported through the partnership. (ii) number supported specifically through UK funded interventions including the Country Engagement Fund, Institutional first response, and the PAF. | Planned | (i) 0 (ii) 0 |  | (i) 105 (ii) 50 |  |  |  |  | (i) 105 (ii) 50 | (i) 105 (ii) 50
|  | Achieved |  |  | (i) (ii) |  |  |  |  | (i) (ii)
Source
| Output Indicator 3.2 (KPI 15) |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target
| 3.2 Number of developing country members, supported by the Partnership, that have NDC Implementation plans and/or NDC-aligned investment plans, disaggregated by, (i) total number supported through the partnership. (ii) number supported specifically through UK funded interventions including the Country Engagement Fund, Institutional first response, and the PAF. | Planned | (i) 65 (ii) 49 |  | (i) 65 (ii) 49 | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii)
|  | Achieved |  | (i) 65 (ii) 49 | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii)
Source
(i) Latest NDC Partnership Work Programme Annual Progress Report or commission SU for data as WP tends to separate investment and implentation plans (ii) Comission SU for total list of countries then work out based on overlap with countries we are supporting through CEF, IFR and PAF Can only be measured in FY25/26 and FY30/31. Baseline cannot be set for (ii) as the internventions listed were not in place in 2020 when this baseline is set to.
| Output Indicator 3.3 (KPI 15) |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target
| 3.3 Number of developing country members, supported by the Partnership, that report to have mainstreamed climate in development planning and budgeting, disaggregated by, (i) total number supported through the partnership. (ii) number supported specifically through UK funded interventions including the Country Engagement Fund, Institutional first response, and the PAF. | Planned | (i) 56 (ii) 50 |  | (i) 56 (ii) 50 | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii)
|  | Achieved |  | (i) 56 (ii) 50 | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii)
Source
(i) Latest NDC Partnership Work Programme Annual Progress Report or commission SU for data as WP tends to separate investment and implentation plans (ii) Comission SU for total list of countries then work out based on overlap with countries we are supporting through CEF, IFR and PAF
IMPACT WEIGHTING (%) | Output Indicator 3.4 (KPI 15) |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target
30% | 3.4 Number of developing country members, supported by the Partnership that have developed a policy, regulation and/or law that drives the climate transition, disaggregated by, (i) total number supported through the partnership. (ii) number supported specifically through UK funded interventions including the Country Engagement Fund, Institutional first response, and the PAF. | Planned | (i) 68 (ii) 56 |  | (i) 68 (ii) 56 | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii)
|  | Achieved |  | (i) 68 (ii) 56 | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii) | (i) (ii)
Source
(i) Latest NDC Partnership Work Programme Annual Progress Report or commission SU for data as WP tends to separate investment and implentation plans (ii) Comission SU for total list of countries then work out based on overlap with countries we are supporting through CEF, IFR and PAF
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target | Assumptions
More effective and joined up UK support driven by/supported by the Partnership | Number of FCDO embassy teams who report that they understand what the partnership is and what it can offer they country they work in. | Planned | 10 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | UK delivery of ICF continues into future years, and support to developing countries for climate action remains a priority.
|  | Achieved |  | 10
Source
Annual embassy survey
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline | FY 2024/25 | FY 2025/26 | FY 2026/27 | FY 2027/28 | FY 2028/29 | FY 2029/30 | FY 2030/31 | Target
10% | Number of awareness raising sessions/outreach products delivered by DESNZ NDC Partnership programme team. | Planned | 15 |  | 5 | 5 | 5 | 10 | 10 | 10 | 10
|  | Achieved |  | 15
Source
NDC Support team management information
Note on D85: Hampton-Ball, Simon (Energy Security): Baseline to 24/25 value
Note on G85: Daruvalla-Davies, Jordanna (Energy Security): Need to set with SU