## REM
This is DESNZ' own International Climate Finance logical framework for its £73.3m (GBP) investment in the REDD for Early Movers Programme
(It is not an official product of the REDD for Early Movers Programme)
| PROJECT TITLE | REDD for Early Movers (REM)
Indicator of additional benefits beyond the core result-based payment objective | IMPACTS | Indicator 1 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25 | Assumptions
| REM's early demonstration of the rewards and lessons of REDD+ : 1) bridges the finance gap to future REDD+ finance mechanisms 2) provides lessons that other REDD+ initiatives learn from 3) increases the motivation of stakeholders to take part in REDD+ initaitives | Value of implemented REDD+ programmes in Colombia and Brazil, including technical assistance programmes. Indicator: annual financing volumes "committed" or "disbursed" to REDD+ programmes across Brazil and Colombia, additional to the initial committment of REM funds. | Planned | $10,700,000/year | $12,000,000/year | $18,000,000/year |  | $21,400,000/year | $21,400,000/year | $21,400,000/year | $21,400,000/year | $21,400,000/year | Significant sources of REDD+ finance develop, and country/state is eligible for them. Country/state seeks to acccess these sources. New REDD+ programmes in country/state and/or elsewhere seek to learn and apply lessons from earlier ones.
Achieved
Source
Baseline is the 2009-2014 annual average of "committed" and "disbursed" funding from REDDX Analysis - "REDD+ Finance Flows 2019-2014". Excludes finance not firmly committed i.e. just "pledged". Potential sources: Vision Amazonia, UN-REDD, ENREDD+, GCF (FP 100 and FP134), FIP, LEAF Window B funding Rationale for this: We are measuring the context of REDD+, and how this has changed over time, surrounding the programmes. We can use the narrative around this to understand if REM has impacted this or not, for example if the states receive less REDD+ readiness funding than other states, or access other RBP more quickly. This will be useful to understand the overall context of REM.
|  | Indicator 2 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25
|  | Qualitative evidence that the REM programme is having a transformational impact in its jurisdiction - As demonstarted by poltitical will/local ownership and assessed by relevant country posts in KPI15 methodology | Planned | Assume no lessons assimilated by other initiatives at the outset |  |  |  | 3 | 3 | 4 | 4 | 4
|  |  | Achieved |  | not measured | not measured | not measured | 3 | 3 | 5 | 4
Source
KPI 15 as source- score of the 25% weighting of KPI 15 - Political will/local ownership - “fostering political will to act on climate change” . This was first decided and measured in 2021, and this indicator has changed to suit evidence availability in 2022, therefore first reporting period is 2021. Key: 1: No evidence yet available, 0; Transformation judged unlikely, 2: Some early evidence suggests transformation likely , 4: Clear evidence of change – transformation judged very likely. Explanation for 20-21: averaged at a 3, with 4 for Colombia, 3 for MT and 2 for Acre for year 2021.
Indicator of additional benefits beyond the core result-based payment objective | OUTCOME 1 | Indicator 3 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25 | Assumptions
| Greenhouse gas emissions resulting from deforestation in the relevant Amazon (biome) reduced. | The amount of emission reductions resulting from reduced deforestation financed through REM (tonnes CO2 equivalent) - cummulative - UK only. | Planned | 0 | 1m | 14.03m |  | 34.2m | 34.2m | 34.2m | 34.2m | 34.2m | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry which we would expect the programme to be able to control. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation. Other exogenous factors do not lead to significant increases in deforestaiton drivers e.g. a rise in international agricommodity prices. Exchange rates do not deviate significantly from starting assumptions.
|  |  | Achieved |  |  | 20.14m |  | 28.57mt CO2eq | 31.16mt CO2eq | 31.16mt CO2eq | 31.16mt CO2eq | 34.9
Source
Country/state's REDD+ registry information showing corresponding retirement of emission reductions (ERs). Validation report of ERs achieved resulting from reduced deforestation. Not including the emissions reductions withdrawn by partner government as part of the risk mechanism. NB: the 2021 target appears to be vaguely (not exactly) congruent with the amount you get if you add outstanding payments (MT3, Acre 2, Acre 3, MT remaining) together; but TBC whether it's based on a model or something else (ie: that congruence is just a coincidence..) 2021-22: 2 further disbursments were made to Mato Grosso by UK and BMZ. UK rewarded 1,633,830 and retired the same amount totalling 3,297,660 BMZ rewarded 960,000 and retired the same amount for buffer totalling 1,920,000. The total amount for both countries is 5,217,660, but only half of this will be added to this, as this mechanism does not take into account the reitrement of credits, but it is important to mention. Therefore and this has been added to last years total. 22-23: No progress against this. 23-24 : No progress 24-25: Acre disbursement made for 1,123,104.61 tonnes. Germany made disbursement for 326,040 tonnes. Total = 1, 449, 144.61.
| OUTCOME 2 | Indicator 4 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25
| Generation of multiple benefits, resulting from reduction in deforestation, that improve the livelihoods of local communities and indigenous groups. | Percentage of REM finance disbursed to activities taking place "at the local level", i.e. rather than used in the operational framework of implementation | Planned | 0 | 50% | 55% | 55% | 60% | 60% | 60% | 60% | 60%
|  |  | Achieved |  |  | 18% |  | no data available | no data available | 56% | 62% | 62%
Source
Colombia = 60% (achieved in report from 2021-22) MT = 60% Acre - no data avilable. 22/23 update: 22/23: 60% Colombia, 60% Mato Grosso, 47% ACre 23/24: 65% Colombia, 60% Mato Grosso, 61% Acre 34/25 : 60%, 60%, 65% in Acre
|  | Indicator 5 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25 | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry which we would expect the programme to be able to control. External politicla factors, such as presence or resolution of armed conflict or change in political parties, does no dramatically affect the ability to implement the programme or lead to significant inrease in drivers of deforestation. Other exogenous factors do not lead to signficiant increases in deforesatsion drivers eg. a rise in international agricommodity prices.
|  | Number of rural families, farming families and Indigenous peoples benefitting from the partnership ('Benefitting' = Forming part of the community or family receiving the funding or likely to be directly affected by the receipt of the funding) | Planned | 0 | 0 | At least 13,000 |  | 69000 | 69000 | 69000 | 69000 | 69000
|  |  | Achieved |  |  | 27464 | 38122 | 48780 | 68324 | 91, 630 | 121, 081 | 121, 574
Source
Annual reports of the project. Acre: Mato Grosso: Source: https://remmt.com.br/pt/ shows 15, 053 are the amount of families benefitted under the programme as a whole. https://remmt.com.br/index.php/pt/atuacao-2/ti-2 shows that 28,700 people are benefitted by the Indigenous Programme, however this does not seem to be originally included in the log frame, so has been calculated by the UK as a total amount.
As a results-based payment programme this is the key REM indicator | OUTPUT 1 (performance weighting 50%) | Indicator 6 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25 | Assumptions
| Results-based payments from REM to country/state. | Volume of results-based payments made by REM to country/state, cumulative, in millions of US Dollars (m USD) (Fluctuations in exchange rate to be taken into consideration, this corresponds to all donors) | Planned | 0 | 5 | 67.75 |  | 173.84 | 173.84 | 173.84 | 173.84 | 173.84 | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry (MADS) which we would expect the programme to be able to control. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation. Other exogenous factors do not lead to significant increases in deforestaiton drivers e.g. a rise in international agricommodity prices. Exchange rates do not deviate significantly from starting assumptions.
|  |  | Achieved |  |  | 100.7 | 124.6m | 145m | $160M | $160M | $160M | 163.7
Source
Country/state's REDD+ registry information showing corresponding retirement of emission reductions (ERs). Validation report of ERs achieved resulting from reduced deforestation. Demands for payment from KfW to BEIS. Encashment of BEIS' promissory note. Annual report of programme progress.
Indicator of additional benefits beyond the core result-based payment objective | OUTPUT 2 (performance weighting 12.5%) | Indicator 7 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25 | Assumptions
| Establishing and maintaining the capacity of implementing Ministry, the finance mechanism and implementing entities to effectively and efficiently implement the results-based payment scheme/REDD+ in the Amazon region. Remove from annual review - indicator 7 | REM Implementation Unit established (this is a team working on REM specifically as part of the government department). | Planned | 0 | 0 | 1 |  | 3 | 3 | 3 | 3 |  | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry (MADS) which we would expect the programme to be able to control. Other forrms of financial and technical support for building the capacity of the implementing Ministry, the finance mechanism and implementing entities, that are not in the direct control of the REM partnership, continue to be available and effective as planned. Stakeholders willing to participate in consultation and dissemination events. Country/state generates sufficient emission reductions and demonstrated capacity for implementation that it accessess the full sum of committed REM finance. If disbursements are lower less progress on capacity strengthening would be expected. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation.
|  |  | Achieved |  |  | 3 | 3 | 3 | 3 | 3 | 3
Source
Work plans of the technical teams. Contracts of the project implementation Unit's personnel. Annual programme progress report. Quarterly progress reports. Independent mid-term evaluation on the Project's social and environmental impacts. Project accounts annual financial statements of FPN. Yearly independent financial audit reports. The REM implementation unit's work plans.
|  | Indicator 8 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25
|  | Information on safeguards presented biannually and publically available | Planned | 0 | 1 | 1 |  | 3 | 3 | 3 | 3 | 3
|  |  | Achieved |  |  | 1 | 2 | 2* | 1 | 2 | 2 | 2
Source
Biannual safeguard summaries of information prepared for KfW (or the UNFCCC once the country submits those reports).
|  | Indicator 9 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25
|  | Carbon accounting system for reduced emissions established and running. | Planned | 0 | 0 | 1 |  | 3 | 3 | 3 | 3 | 3
|  |  | Achieved |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3
Source
Validation report of ERs resulting from reduced deforestation: all reporting (In Brazil on Infohub).
|  | Indicator 10 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25
|  | Number of subnational REDD+ instruments integrated into the national system. | Planned | 0 | 0 | 0 |  | 4 | 4 | 4 | 4 | 4
|  |  | Achieved |  |  | 2 | 3 | 3* | 4 | 4 | 4 | 4
Source
Yearly reports published by reporting body available eg on Infohub Brasil. Reports prepared by state government for REM. Validation report of achieved emission reductions from reduced deforestation.
Indicator of additional benefits beyond the core result-based payment objective | OUTPUT 3 (performance weighting 12.5%) | Indicator 11 (Colombia only) |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25 | Assumptions
| Forest and territorial governance implemented and consolidated. | Number of hectares of new and updated land with land use planning applied in an inclusive and transparent way in conformity with existing legislation. | Planned | 0 | 0 | 1000000 |  | 2400000 hectares | 2400000 hectares | 2400000 hectares |  |  | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry which we would expect the programme to be able to control. Country/state generates sufficient emission reductions and demonstrated capacity for implementation that it accessess the full sum of committed REM finance. If disbursements are lower less progress on forest and territiorial governance would be expected. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation.
|  |  | Achieved |  |  | 0 | 0 | 1,944,849 hectares | 16291 | 16291 | 6, 489, 604 | Closed - as before
Source
Land use plans and territorial governance scheme, decrees produced by regional environmental authorities (CARs). Expert opinions (reports) by public prosecutors and environmental authorities. CARs administrative rulings. Annual progress reports of the project. Underatken planimetric studies. Quarterly progress reports. Independent mid-term evaluation on the project's environmental and social impacts.
|  | Indicator 12 (Colombia only) |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25
|  | Number of intersectoral agreements for legal timber in place. | Planned | 0 | 0 | 1 |  | 4 | 4 | 4 | 4 | 4
|  |  | Achieved |  |  | 2 | 3 | 3 | 4 | 4 | 4 | 4
Source
Annual reports.
|  | Indicator 13 (Colombia only) |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25
|  | Number of territorial and/or sectorial policy agreements signed and in operation. | Planned | 0 | 0 | 0 |  | 2 | 2 | 2 | 2 | 2
|  |  | Achieved |  |  | 0 | 2 | 2 | 2 | 2 | 2 | 2
Source
Annual report from implementing body (eg state or national government) to REM
|  | Indicator 14 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25
|  | Number of a) command and control interventions in priority deforestation areas and b) hectares of avoided deforestation due to command and control activities. | Planned | 0 | 0 | a) 4; b) 0 |  | a) 73; b) 30,000 | a) 73; b) 30,000 | a) 73; b) 30,000 | a) 73; b) 30,000
|  |  | Achieved |  |  | a) 24; b) 0 | a) 1400; b) 0 | a) 1,400, b) 0 | a) 0 b) 0 | Removed
Source
Notes: Will be reviewed and edited for next year.
Indicator of additional benefits beyond the core result-based payment objective | OUTPUT 4 (performance weighting 12.5%) | Indicator 15 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25 | Assumptions
| Sustainable agro-environmental activities consolidated and expanded in the intervention areas | Number of farming families benefitting from agro-environmental activitites, including women and young people | Planned | 0 | 0 | 6000 |  | 46500 | 46500 | 46500 | 46500 | 46500 | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry which we would expect the programme to be able to control. Country/state generates sufficient emission reductions and demonstrated capacity for implementation that it accessess the full sum of committed REM finance. If disbursements are lower less progress on agro-environmental activities would be expected. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation.
|  |  | Achieved |  |  | 4439 | 14198 | 20757 | 21, 312 | 20, 023 | 34, 044
Source
Annual progress reports of the project. Quarterly progress reports. Independent mid-term evaluation on the projects social and environmental impacts. The projects accounts and annual financial statements. 2021-22: Annual reports of all three programmes.
|  | Indicator 16 (MT and Col only) |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25
|  | Number of hectares a) subject to agro-environmental production activities and b) protected by agreements made between national/local authorities and farmer/producer associations, guilds and the private sector. | Planned | 0 | 0 | a) 5,000 ha; b) 75,000 ha |  | a) 47,500 ha; b) 200,000 ha | a) 47,500 ha b) 278,400 ha | a) 47,500 ha b) 278,400 ha | a) 47, 500 b) 278,400 ha | a) 47,500 ha b) 278,400 ha
|  |  | Achieved |  |  | a) 2285; b) 96,177 | a) 8507; b) 115,348 | a) 19,931 ha (42%) b) 213,432 (107%) | a) 426, 760 ha b) 296,441 ha | a) 439, 341 (878%) b) 298,405 (107%) | a) 670, 132 (1,340%) b) 298,405 (107%) | a) 139, 489 b) 298, 405
Source
Annual progress reports of the project. Quarterly progress reports. Independent mid-term evaluation on the projects social and environmental impacts. The project's accounts and annual financial statements. 20
Indicator of additional benefits beyond the core result-based payment objective | OUTPUT 5 (performance weighting 12.5%) | Indicator 17 (Col only) |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25 | Assumptions
| Environmental governance with indigenous peoples improved. | a) Number of hectares of Indigenous territories benefitting from the programme. | Planned | 0 | 0 | 30000 |  | a) 14,000,000 ha b) 11,000 | a) 14,000,000 ha b) 11,000 | a) 14,000,000 ha b) 11,000 |  |  | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry which we would expect the programme to be able to control. Country/state generates sufficient emission reductions and demonstrated capacity for implementation that it accessess the full sum of committed REM finance. If disbursements are lower less progress on environmental governance with indigenous peoples would be expected. Stakeholders willing to participate in consultation and dissemination events. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation.
|  |  | Achieved |  |  | 6647674 | 14004903 | 16.48 million ha (118%) | 18.8 million ha (134%) | A) 19.3 million ha (137%) | A) 19.3 million ha (137%)
[9 empty] | b) 25, 780 | b) 25, 480 | b) 25, 480
|  | 17B) Number of indigenous families benefited (Colombia only) | Source
Annual progress reports of the project. Quarterly progress reports. Independent mid-term evaluation on the projects social and environmental impacts. The projects accounts and annual financial statements. Not measured currently for Acre, but there is data for Acre: 2.2 million hectares of land covered by IP interventions,
|  | Indicator 18 (MT and Col only) |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25
|  | Number of projects led by Indigenous women | Planned | 0 | 0 | 5 |  | 12 | 74 | 75 | 75 | 75
|  |  | Achieved |  |  | 5 | 8 | 69 (575%) | 76 | 80 | 82 | 82
Source
Annual progress reports of the project. Quarterly progress reports. Independent mid-term evaluation on the projects social and environmental impacts. The projects accounts and annual financial statements.
|  | Indicator 19 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25
|  | Number of indigenous projects supported by programme | Planned | 0 | 0 |  |  |  | 100 | 100 | 100 | 100
|  |  | Achieved | [5 empty] | 229 | 285 | 273 | 289
21/22 Colombia: 140, Acre: 16 (of 29 target), Mato Grosso: 73 running, 8 being established

## Colombia specific indicators
| PROJECT TITLE | REDD for Early Movers (REM)
Indicator of additional benefits beyond the core result-based payment objective | OUTCOME 1 | Indicator 3 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | Assumptions
| Greenhouse gas emissions resulting from deforestation in the relevant Amazon (biome) reduced | The amount of emission reductions resulting from reduced deforestation financed through REM (tonnes CO2 equivalent) - cummulative | Planned | 0 | 1m |  | 5.23m |  | 18m | 18m | 18m | 18m | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry which we would expect the programme to be able to control. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation. Other exogenous factors do not lead to significant increases in deforestaiton drivers e.g. a rise in international agricommodity prices. Exchange rates do not deviate significantly from starting assumptions.
|  |  | Achieved |  |  |  | 13.87m | 17.46m | 17,47 Mill. | 17,47 Mill. | 17,47 Mill. | 17,47 Mill.
Source
Country/state's REDD+ registry information showing corresponding retirement of emission reductions (ERs). Independent verification report of ERs achieved resulting from reduced deforestation.
|  | Indicator 4 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-24
|  | Percentage of REM finance disbursed to activities taking place "at the local level", i.e. rather than used in the operational framework of implementation | Planned | 0 | 50% | 50% | 55% | 55% | 60% | 60% | 60% | 60%
|  |  | Achieved |  |  |  | 31% | 51% | 55% | 60% | 60% | 65%
Source
The project account's annual financial statements and Annual reports. Target 2022 already achieved in half year report. and page 23 of full year report.
| OUTCOME 2 | Indicator 5 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-24
| Generation of multiple benefits, resulting from reduction in deforestation, that improve the livelihoods of local communities and indigenous groups. | Number of peasant families, farming families and indigenous peoples benefitting from the partnership | Planned | 0 | 0 |  | At least 13,000 |  | At least 26,500 | 38500 | 38500 | 38500
|  |  | Achieved |  |  |  | 7871 | 22080 | 27430 | 37110 | 37, 890 | 37, 945
Source
Annual reports of the project. Quarterly progress reports. Independent mid-term evaluation of the Project's social and environmental impacts. Post-implementation evaluation. In the annual report for Col, this is measured with an aim for 14,500 peasant families benefitting and 11,000 indigenous families benefitting (of which the first was underachieved and the second overachieved). 2021-22: 37.110 in Colombia according to VA presentations in Bogota October 2022 and annual report June 2021-December 2021.
As a results-based payment programme this is the key REM indicator | OUTPUT 1 (performance weighting 50%) | Indicator 6 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | Assumptions
| Results-based payments from REM to country/state. | Volume of results-based payments made by REM to country/state, cummulative, in millions of US Dollars (m USD) (Fluctutations in exchange rate to be taken into consideration) | Planned | 0 | 5 |  | 26.15 |  | 90 | 90 | 90 | 90 | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry (MADS) which we would expect the programme to be able to control. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation. Other exogenous factors do not lead to significant increases in deforestaiton drivers e.g. a rise in international agricommodity prices. Exchange rates do not deviate significantly from starting assumptions.
|  |  | Achieved |  |  |  | 69.35 | 71.25 | 79.2 | 79.2 | 79.2 | 79.2
Source
Country/state's REDD+ registry information showing corresponding retirement of emission reductions (ERs). Independent verification report of ERs achieved resulting from reduced deforestation. Demands for payment from KfW to BEIS. Encashment of BEIS' promissory note. Annual report of programme progress. This corresponds to all donors. Norway withheld some of their funding for poor performance from Colombia. and this is unlikely to get paid out. They withheld approx 7 million euros (amounyt in NOK approximate) and so the total will always be short of the end target.
Indicator of additional benefits beyond the core result-based payment objective | OUTPUT 2 (performance weighting 10%) | Indicator 7 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | Assumptions
| Establishing and maintaining the capacity of implementing Ministry, the finance mechanism and implementing entities to effectively and efficiently implement the results-based payment scheme/REDD+ in the Amazon region. | REM Implementation Unit established. | Planned | 0 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry (MADS) which we would expect the programme to be able to control. Other forrms of financial and technical support for building the capacity of the implementing Ministry, the finance mechanism and implementing entities, that are not in the direct control of the REM partnership, continue to be available and effective as planned. Stakeholders willing to participate in consultation and dissemination events. Country/state generates sufficient emission reductions and demonstrated capacity for implementation that it accessess the full sum of committed REM finance. If disbursements are lower less progress on capacity strengthening would be expected. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation.
|  |  | Achieved |  |  |  | 1 | 1 | 1 | 1 | 1 | 1
Source
Work plans of the technical teams. Contracts of the project implementation Unit's personnel. Annual programme progress report. Quarterly progress reports. Independent mid-term evaluation on the Project's social and environmental impacts. Project accounts annual financial statements of FPN. Yearly independent financial audit reports. The REM implementation unit's work plans.
|  | Indicator 8 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-24
|  | Information on safeguards presented annually and publically available | Planned | 0 | 1 |  | 1 |  | 1 | 1 | 1 | 1
|  |  | Achieved |  |  |  | 1 | 1 | 1 | 1 | 1 | 1
Source
Yearly safeguard summaries of information prepared for KfW (or the UNFCCC once the country submits those reports). Reports produced by the SIS. Annual project progress report. Quarterly progress reports. Independent mid-term evaluation on the Project's social and environmental impacts.
|  | Indicator 9 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-24
|  | Carbon accounting system for reduced emissions established and running. | Planned | 0 | 0 |  | 1 |  | 1 | 1 | 1 | 1
|  |  | Achieved |  |  |  | 1 | 1 | 1 | 1 | 1 | 1
Source
Independent verification report of emission reductions resulting from reduced deforestation. Operational REDD+ registry. Documents dealing with registration and retirement of financed as well as non-financed (units to address risks) emission reductions.
Indicator of additional benefits beyond the core result-based payment objective | OUTPUT 3 (performance weighting 10%) | Indicator 11 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | Assumptions
| Forest and territorial governance implemented and consolidated. | Number of hectares of new and updated land with land-use planning applied in an inclusive and transparent way in conformity with existing legislation. | Planned | 0 | 0 |  |  |  | 2,400,000 hectares | 2,400,000 hectares | 2,400,000 hectares | 2,400,000 hectares | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry which we would expect the programme to be able to control. Country/state generates sufficient emission reductions and demonstrated capacity for implementation that it accessess the full sum of committed REM finance. If disbursements are lower less progress on forest and territiorial governance would be expected. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation.
|  |  | Achieved |  |  |  | 0 | 0 | 1,944,849 hectares | 16,291 ha | 16,291 ha | 6, 489, 605
Source
Land use plans and territorial governance scheme, decrees produced by regional environmental authorities (CARs). Expert opinions (reports) by public prosecutors and environmental authorities. CARs administrative rulings. Annual progress reports of the project. Underatken planimetric studies. Quarterly progress reports. Independent mid-term evaluation on the project's environmental and social impacts. In 2021/22: In various stages of planning: Specifically, 1,586,500 ha is being mapped, 48,093 ha contracted, and 310,256 ha awarded prior to contract. If the progress completes 80% of target could be achieved next year. In 23-24, these agreements were finalised, overachieving the targets.
|  | Indicator 12 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-24
|  | Number of intersectoral agreements for legal timber in place. | Planned | 0 | 0 |  | 1 |  | 4 | 4 | 4 | 4
|  |  | Achieved |  |  |  | 2 | 3 | 3 | 4 | 4 | 4
Source
Land use plans and territorial governance scheme, decrees produced by regional environmental authorities (CARs). Expert opinions (reports) by public prosecutors and environmental authorities. CARs administrative rulings. Annual progress reports of the project. Underatken planimetric studies. Quarterly progress reports. Independent mid-term evaluation on the project's environmental and social impacts.
|  | Indicator 13 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-24
|  | Number of territorial and/or sectorial policy agreements signed and in operation. | Planned | 0 | 0 |  | 0 |  | 2 | 2 | 2 | 2
|  |  | Achieved |  |  |  | 0 | 2 | 2 | 2 | 2 | 2
Source
Annual reports
|  | Indicator 14 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-24
|  | Number of a) command and control interventions in priority deforestation areas and b) hectares of deforestation avoided due to command and control activities | Planned |  |  |  | 4 | 4 | a) 4 | a) 4 | Removed
|  |  | Achieved | 0 | 0 |  | b) ? | B? | b) ?
[7 empty] | 4 | 10 | a) 10 | a) 4 (100% | Removed
b) No robust data available
Notes:
Indicator of additional benefits beyond the core result-based payment objective | OUTPUT 4 (performance weighting 10%) | Indicator 15 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | Assumptions
| Sustainable agro-environmental activities consolidated and expanded in the intervention areas | Farming families benefit from agro-environmental activities, including women and young people | Planned | 0 | 0 |  | 6000 |  | 12000 | 12000 | 14, 500 | 14, 500 | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry which we would expect the programme to be able to control. Country/state generates sufficient emission reductions and demonstrated capacity for implementation that it accessess the full sum of committed REM finance. If disbursements are lower less progress on agro-environmental activities would be expected. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation.
|  |  | Achieved |  |  |  | 2744 | 3264 | 6488 | 8, 168 | 12, 465 | 12, 465
Source
Annual progress reports of the project. Quarterly progress reports. Independent mid-term evaluation on the projects social and environmental impacts. The projects accounts and annual financial statements.
|  | Indicator 16 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-24
|  | Number of hectares a) subject to agro-environmental production activities and b) protected by agreements made between national/local authorities and farmer/producer associations, guilds and the private sector. | Planned | 0 | 0 |  | a) 5,000 ha; b) 75,000 ha |  | a) 12,500 ha; b)200,000 ha | a) 12,500 ha; b)200,000 ha | a) 12,500 ha; b)200,000 ha | a) 12,500 ha; b)200,000 ha
|  |  | Achieved |  |  |  | a) 2285; b) 96,177 | a) 8507; b) 115,348 | a) 13,999 ha (112% of 12,500 ha target) b) 213,432 ha | a) 39, 705 ha b) 295,563 | a) 44, 187 ha b) 298, 405 | a) 44, 187 ha b) 298, 405
Source
Annual progress reports of the project. Quarterly progress reports. Independent mid-term evaluation on the projects social and environmental impacts. The project's accounts and annual financial statements.
Indicator of additional benefits beyond the core result-based payment objective | OUTPUT 5 (performance weighting 10%) | Indicator 17 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | Assumptions
| Environmental governance with indigenous peoples improved. | a) Hectares of indigenous territories benefitting from the programme. b) Number of indigenous families benefited (Colombia only) | Planned | 0 | 0 |  | 30000 |  | a) 14,000, 000 b) 11,000 | a) 14,000, 000 b) 11,000 | a) 14,000, 000 b) 11,000 | a) 14,000, 000 b) 11,001 | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry which we would expect the programme to be able to control. Country/state generates sufficient emission reductions and demonstrated capacity for implementation that it accessess the full sum of committed REM finance. If disbursements are lower less progress on environmental governance with indigenous peoples would be expected. Stakeholders willing to participate in consultation and dissemination events. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation.
|  |  | Achieved |  |  |  | 6647674 | 14004903 | 16.48 million ha (118%) | a) 18.8 million ha (134%) b) 25, 780 | A) 19.3 million ha (137%) b) 25, 480 | A) 19.3 million ha (137%) b) 25, 481
Source
Annual progress reports of the project. Quarterly progress reports. Independent mid-term evaluation on the projects social and environmental impacts. The projects accounts and annual financial statements.
|  | Indicator 18 |  | Baseline | June 2016-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-24
|  | Number of projects led by indigenous women | Planned | 0 | 0 |  | 5 |  | 12 | 70 | 70 | 70
|  |  | Achieved |  |  |  | 5 | 8 | 69 (575%) | 72 | 72 | 72
Source
Annual progress reports of the project. Quarterly progress reports. Independent mid-term evaluation on the projects social and environmental impacts. The projects accounts and annual financial statements.
|  | Indicator 19 |  | Baseline | June 16-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-24
|  | Number of indigenous projects supported through REM funding | [6 empty] | 10 | 50 | 50 | 50
[9 empty] | N/A |  | 140 | 140
Source
Annual reports
Note on C33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove from log frame weighting

## Acre specific indicators
Indicator of additional benefits beyond the core result-based payment objective | OUTCOME 1 | Indicator 3 |  | Baseline | 2016 | 2018 | 2019/20 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25 | Assumptions
| Greenhouse gas emissions resulting from deforestation in the relevant Amazon (biome) reduced | The amount of emission reductions resulting from reduced deforestation financed through REM (tonnes CO2 equivalent) - cummulative | Planned | 0 | 0 | 2.9m |  | 5.2m | 5.2 M | 5.2 M | 5.2 M | 5.2 M | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry which we would expect the programme to be able to control. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation. Other exogenous factors do not lead to significant increases in deforestaiton drivers e.g. a rise in international agricommodity prices. Exchange rates do not deviate significantly from starting assumptions.
|  |  | Achieved | 0 | 0 | 3.07m | 4.5m | 4.5m | 4.5m | 4.5m | 4.5m | 5.6m
Source
Country/state's REDD+ registry information showing corresponding retirement of emission reductions (ERs). Independent verification report of ERs achieved resulting from reduced deforestation.
|  | Indicator 4 |  | Baseline | 2016 | 2018 | 2019/20 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25
|  | Percentage of REM finance disbursed to activities taking place "at the local level", i.e. rather than used in the operational framework of implementation | Planned | 0 | 70% | 70% |  | 70% | 70% | 70% | 70% | 70%
|  |  | Achieved |  |  | 22% |  | 24 | N/A | 47% | 62% | 65%
Source
The project account's annual financial statements and Annual reports.
| OUTCOME 2 | Indicator 5 |  | Baseline | 2016 | 2018 | 2019/20 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25 | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry which we would expect the programme to be able to control. External politicla factors, such as presence or resolution of armed conflict or change in political parties, does no dramatically affect the ability to implement the programme or lead to significant inrease in drivers of deforestation. Other exogenous factors do not lead to signficiant increases in deforesatsion drivers eg. a rise in international agricommodity prices.
| Generation of multiple benefits, resulting from reduction in deforestation, that improve the livelihoods of local communities and indigenous groups. | Number of peasant families, farming families and indigenous peoples benefitting from the partnership | Planned | 0 | 0 | 0 |  | 28500 | 28500 | 28500 | 28500 | 28500
|  |  | Achieved |  |  | 19593 | 16042 | cannot tell from reporting | 1090 | 9, 987 | 39, 383 | 39, 383
Annual reports of the project. Quarterly progress reports. Independent mid-term evaluation of the Project's social and environmental impacts. Post-implementation evaluation.
As a results-based payment programme this is the key REM indicator | OUTPUT 1 (performance weighting 50%) | Indicator 6 |  | Baseline | 2016 | 2018 | 2019/20 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25 | Assumptions
| Results-based payments from REM to country/state. | Volume of results-based payments made by REM to country/state, cummulative, in millions of US Dollars (m USD) (Fluctutations in exchange rate to be taken into consideration) | Planned | 0 | 0 | 19 |  | 34.04 | 17.4 | 21.9 | 26.4 | 34.4 | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry (MADS) which we would expect the programme to be able to control. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation. Other exogenous factors do not lead to significant increases in deforestaiton drivers e.g. a rise in international agricommodity prices. Exchange rates do not deviate significantly from starting assumptions.
|  |  | Achieved |  |  | 15.35m | 15.35m | $20.5 | $20.5 | $20.5 | $20.5 | 26.1
Country/state's REDD+ registry information showing corresponding retirement of emission reductions (ERs). Independent verification report of ERs achieved resulting from reduced deforestation. Demands for payment from KfW to BEIS. Encashment of BEIS' promissory note. Annual report of programme progress.
Indicator of additional benefits beyond the core result-based payment objective | OUTPUT 2 (performance weighting 10%) | Indicator 7 |  | Baseline | 2016 | 2018 | 2019/20 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25 | Assumptions
| Establishing and maintaining the capacity of implementing Ministry, the finance mechanism and implementing entities to effectively and efficiently implement the results-based payment scheme/REDD+ in the Amazon region. | REM Implementation Unit established. | Planned | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 1 | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry (MADS) which we would expect the programme to be able to control. Other forrms of financial and technical support for building the capacity of the implementing Ministry, the finance mechanism and implementing entities, that are not in the direct control of the REM partnership, continue to be available and effective as planned. Stakeholders willing to participate in consultation and dissemination events. Country/state generates sufficient emission reductions and demonstrated capacity for implementation that it accessess the full sum of committed REM finance. If disbursements are lower less progress on capacity strengthening would be expected. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation.
|  |  | Achieved |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
Source
Annual reporting to REM/KfW
|  | Indicator 8 |  | Baseline | 2016 | 2018 | 2019/20 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25
|  | Information on safeguards presented biannually and publically available | Planned | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 1
|  |  | Achieved |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Source
Yearly safeguard summaries of information prepared for KfW (or the UNFCCC once the country submits those reports). Reports produced by the SIS. Annual project progress report. Quarterly progress reports. Independent mid-term evaluation on the Project's social and environmental impacts.
|  | Indicator 9 |  | Baseline | 2016 | 2018 | 2019/20 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25
|  | Carbon accounting system for reduced emissions established and running. | Planned | 0 | 0 | 0 |  | 1 | 1 | 1 | 1 | 1
|  |  | Achieved |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
Source
Independent verification report of emission reductions resulting from reduced deforestation. Operational REDD+ registry. Documents dealing with registration and retirement of financed as well as non-financed (units to address risks) emission reductions.
|  | Indicator 10 |  | Baseline | 2016 | 2018 | 2019/20 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25
|  | Number of subnational REDD+ instruments integrated into the national system. | Planned | 0 | 0 | 0 |  | 2 | 2 | 2 | 2 | 2
|  |  | Achieved |  |  | 1 | 2 | 2 | 2 | 1 | 1 | 2
Source
Yearly reports published. Reports prepared for REM. Independent verification of the annual report of achieved emission reductions from reduced deforestation.
Indicator of additional benefits beyond the core result-based payment objective | OUTPUT 3 (performance weighting 10%) | Indicator 14 |  | Baseline | June 16-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25
| Forest and territorial governance implemented and consolidated. | Number of a) command and control interventions in priority deforestation areas and b) hecatres under control of command and control | Planned | 0 | 0 | a) 0; b) 0 |  | a) 69; b) 0 | a) 69; b) 0 | removed | removed | removed | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry which we would expect the programme to be able to control. Country/state generates sufficient emission reductions and demonstrated capacity for implementation that it accessess the full sum of committed REM finance. If disbursements are lower less progress on forest and territiorial governance would be expected. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation.
|  |  | Achieved |  |  | a) 20; b) 0 | a) 1390 | a) 1390 (2014%) since ‘19 b) Not reporting | a) unclear b) unclear
Source
Annual reporting to REM/KfW Indicator will be revised.
Indicator of additional benefits beyond the core result-based payment objective | OUTPUT 4 (performance weighting 10%) | Indicator 15 |  | Baseline | 2016 | 2018 |  | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25 | Assumptions
| Sustainable agro-environmental activities consolidated and expanded in the intervention areas | Number of farming families benefitting from agro-environmental activities, including women and young people | Planned | 0 | 0 | 0 |  | 20500 | 20500 | 20500 | 20500 | 20500 | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry which we would expect the programme to be able to control. Country/state generates sufficient emission reductions and demonstrated capacity for implementation that it accessess the full sum of committed REM finance. If disbursements are lower less progress on agro-environmental activities would be expected. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation.
|  |  | Achieved |  |  | 1695 | 10934 | 14, 269 | 1090 | 1108 | 17, 383 | 17, 383
Source
Annual progress reports of the project. Quarterly progress reports. Independent mid-term evaluation on the projects social and environmental impacts. The projects accounts and annual financial statements. 2021 was incorrectly calculated
|  | Indicator 19 |  | Baseline | June 16-17 | June 17-18 | June 18-19 | June 20-21 | June 21-22 | June 22-23 | June 23-24 | June 24-25
|  | Number of indigenous projects supported through REM funding | [6 empty] | 29 | 40 | 40 | 40
[9 empty] | 16 | 29 | 29 | 45
Source
For Acre this includes: This includes: 60 Territorial Implementation Plans (Goal 40) and 80 Indigenous schools (goal 132). 24-25: This includes 40 territorial Implemntation plans (PGTIs) which are being implemented, and 5 other programmes being executed by the sub-organs, including agroforestry agents, school foods, traditional culture, and education. Within these, there are many smaller subprogrammes that are not accounted for.
Note on C62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sarah I have added this indicator, think we can report on it and it is similar to the Colombia one, is that ok? Will it change thw weighting?

## MT specific indicators
Indicator of additional benefits beyond the core result-based payment objective | OUTCOME 1 | Indicator 3 |  | Baseline | June 16-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-June 24 | June 24-25 | Assumptions
| Greenhouse gas emissions resulting from deforestation in the relevant Amazon (biome) reduced | The amount of emission reductions resulting from reduced deforestation financed through REM (tonnes CO2 equivalent) - cummulative | Planned | 0 | 0 |  | 5.9m |  | 11m | 11m | 11m | 11m | 11m | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry which we would expect the programme to be able to control. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation. Other exogenous factors do not lead to significant increases in deforestaiton drivers e.g. a rise in international agricommodity prices. Exchange rates do not deviate significantly from starting assumptions.
|  |  | Achieved |  |  |  | 3.2m |  | 10091830 | 10091830 | 10091830 | 10091830 | 11839393
Source
Country/state's REDD+ registry information showing corresponding retirement of emission reductions (ERs). Independent verification report of ERs achieved resulting from reduced deforestation.
|  | Indicator 4 |  | Baseline | June 16-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-June 24 | June 24-25
|  | Percentage of REM finance disbursed to activities taking place "at the local level", i.e. rather than used in the operational framework of implementation | Planned | 0 | 50% |  | 55% |  | 60% | 60% | 60% | 60% | 60%
|  |  | Achieved |  |  |  | 0% |  |  | 60% | 60% | 60% | 60%
Source
The project account's annual financial statements and Annual reports.
| OUTCOME 2 | Indicator 5 |  | Baseline | June 16-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-June 24 | June 24-25 | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry which we would expect the programme to be able to control. External politicla factors, such as presence or resolution of armed conflict or change in political parties, does no dramatically affect the ability to implement the programme or lead to significant inrease in drivers of deforestation. Other exogenous factors do not lead to signficiant increases in deforesatsion drivers eg. a rise in international agricommodity prices.
| Generation of multiple benefits, resulting from reduction in deforestation, that improve the livelihoods of local communities and indigenous groups. | Number of peasant families, farming families and indigenous peoples benefitting from the partnership ('Benefitting' = Forming part of the community or family receiving the funding or likely to be directly affected by the receipt of the funding) | Planned | 0 | 0 |  | 0 |  | 14000 | 14000 | 14000 | 14000 | 14000
Achieved
|  |  | Achieved |  |  |  | 0 | 0 | 0 | 21625 | 43, 753 | 43, 754 | 44, 246
Source
Annual reports of the project. Quarterly progress reports. Independent mid-term evaluation of the Project's social and environmental impacts. Post-implementation evaluation. MT not reporting: to find out why and how to ensure reporting in mid term review SB 18/11. MT: 4,927 benefitting from the family agriculture sub-programme. Close to 6,000 estimated to be benefitted from the most recent AFCPT programme. 22/23: Source: https://remmt.com.br/pt/ shows 15, 053 are the amount of families benefitted under the programme as a whole. https://remmt.com.br/index.php/pt/atuacao-2/ti-2 shows that 28,700 people are benefitted by the Indigenous Programme, however this does not seem to be originally included in the log frame, so has been calculated by the UK as a total amount. 24/25:
As a results-based payment programme this is the key REM indicator | OUTPUT 1 (performance weighting 50%) | Indicator 6 |  | Baseline | June 16-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-June 24 | June 24-25 | Assumptions
| Results-based payments from REM to country/state. | Volume of results-based payments made by REM to country/state, cummulative, in millions of US Dollars (m USD) (Fluctutations in exchange rate to be taken into consideration) | Planned | 0 | 0 |  | 26.6 |  | 49.8 | 49.8 | 49.8 | 49.8 | 49.8 | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry (MADS) which we would expect the programme to be able to control. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation. Other exogenous factors do not lead to significant increases in deforestaiton drivers e.g. a rise in international agricommodity prices. Exchange rates do not deviate significantly from starting assumptions.
|  |  | Achieved |  |  |  | 16m | 38m | $38m | $49.8 | $49.8 | $49.8 | 58.3774
Source
Country/state's REDD+ registry information showing corresponding retirement of emission reductions (ERs). Independent verification report of ERs achieved resulting from reduced deforestation. Demands for payment from KfW to BEIS. Encashment of BEIS' promissory note. Annual report of programme progress. Fully disbursed as of June 2021, some small differences for exchange rates need to be considered.
Indicator of additional benefits beyond the core result-based payment objective | OUTPUT 2 (performance weighting 10%) | Indicator 7 |  | Baseline | June 16-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-June 24 | June 24-25 | Assumptions
| Establishing and maintaining the capacity of implementing Ministry, the finance mechanism and implementing entities to effectively and efficiently implement the results-based payment scheme/REDD+ in the Amazon region. | REM Implementation Unit established. | Planned | 0 | 0 |  | 0 |  | 1 | 1 | 1 | 1 | 1 | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry (MADS) which we would expect the programme to be able to control. Other forrms of financial and technical support for building the capacity of the implementing Ministry, the finance mechanism and implementing entities, that are not in the direct control of the REM partnership, continue to be available and effective as planned. Stakeholders willing to participate in consultation and dissemination events. Country/state generates sufficient emission reductions and demonstrated capacity for implementation that it accessess the full sum of committed REM finance. If disbursements are lower less progress on capacity strengthening would be expected. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation.
|  |  | Achieved |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
Source
Work plans of the technical teams. Contracts of the project implementation Unit's personnel. Annual programme progress report. Quarterly progress reports. Independent mid-term evaluation on the Project's social and environmental impacts. Project accounts annual financial statements of FPN. Yearly independent financial audit reports. The REM implementation unit's work plans.
|  | Indicator 8 |  | Baseline | June 16-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-June 24 | June 24-25
|  | Information on safeguards presented annually and publically available | Planned | 0 | 0 |  | 0 |  | 1 | 1 | 1 | 1 | 1
|  |  | Achieved |  |  |  | 0 | 0 | 1 | 0 | 1 | 1 | 1
Source
Yearly safeguard summaries of information prepared for KfW (or the UNFCCC once the country submits those reports). Reports produced by the SIS. Annual project progress report. Quarterly progress reports. Independent mid-term evaluation on the Project's social and environmental impacts.
|  | Indicator 9 |  | Baseline | June 16-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-June 24 | June 24-25
|  | Carbon accounting system for reduced emissions established and running. | Planned | 0 | 0 |  | 0 |  | 1 | 1 | 1 | 1 | 1
|  |  | Achieved |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
Source
Independent verification report of emission reductions resulting from reduced deforestation. Operational REDD+ registry. Documents dealing with registration and retirement of financed as well as non-financed (units to address risks) emission reductions.
|  | Indicator 10 |  | Baseline | June 16-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-June 24 | June 24-25
|  | Number of subnational REDD+ instruments integrated into the national system. | Planned | 0 | 0 |  | 0 |  | 2 | 2 | 2 | 2 | 2
|  |  | Achieved |  |  |  | 1 | 1 | 1 | 1 | 2 | 2 | 2
Source
Yearly reports published. Reports prepared for REM. Independent verification of the annual report of achieved emission reductions from reduced deforestation. 2021/22 - MT the Infohub for ERs achieved, safeguard instrument being finalised. 1/2 target reached.
Indicator of additional benefits beyond the core result-based payment objective | OUTPUT 3 (performance weighting 10%) | Indicator 14 |  | Baseline | June 16-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-June 24 | June 24-25 | Assumptions
| Forest and territorial governance implemented and consolidated. | Number of a) command and control interventions in priority deforestation areas and b) hectares of deforestation avoided due to command-and-control activities | Planned |  | 0 |  | 0 | 0 | a) 0 | removed | removed | removed | removed
|  |  | Planned | [5 empty] | b) 30,000 |  |  |  |  | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry which we would expect the programme to be able to control. Country/state generates sufficient emission reductions and demonstrated capacity for implementation that it accessess the full sum of committed REM finance. If disbursements are lower less progress on forest and territiorial governance would be expected. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation.
|  |  | Achieved | 0 | 0 |  | 0 |  | a) 0
|  |  | Achieved |  |  |  | 0 |  | b)n/a
Source
Annual reporting to REM/KfW MT: hecatres under command and control/areas embargoed by monitoring of illegal deforestation = 548,233 hectares in 2021 (but can not be applied to indicator)
Indicator of additional benefits beyond the core result-based payment objective | OUTPUT 4 (performance weighting 10%) | Indicator 15 |  | Baseline | June 16-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-June 24 | June 24-25 | Assumptions
| Sustainable agro-environmental activities consolidated and expanded in the intervention areas | Number of farming families benefitting from agro-environmental activitites, including women and young people | Planned | 0 | 0 |  | 0 |  | 14000 | 14000 | 14000 | 14000 | 14000 | There are no substantial conflicts of interest between policies aimed at forest protection and measures to promote extractive industries such as mining, oil and gas and cattle ranching - excludes issues in the direct control of the implementing Ministry which we would expect the programme to be able to control. Country/state generates sufficient emission reductions and demonstrated capacity for implementation that it accessess the full sum of committed REM finance. If disbursements are lower less progress on agro-environmental activities would be expected. External political factors, such as presence or resolution of armed conflict or change in political parties, does not dramatically affect the ability to implement the programme or leave to signficant increase in drivers of deforestation.
|  |  | Achieved |  |  |  | 0 | 0 | 0 | 12054 | 6, 668 | 4, 196 | 5715
Source
Annual progress reports of the project. Quarterly progress reports. Independent mid-term evaluation on the projects social and environmental impacts. The projects accounts and annual financial statements.
|  | Indicator 16 |  | Baseline | June 16-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-June 24 | June 24-25
|  | Number of hectares a) subject to agro-environmental production activities and b) protected by agreements made between national/local authorities and farmer/producer associations, guilds and the private sector. | Planned | 0 | 0 |  | 0 |  | a) 35000 ha; b) 0 ha | a) 35000 ha; b) 0 ha | a) 35000 ha; b) 0 ha | a) 35000 ha; b) 0 ha | a) 35000 ha; b) 0 ha
|  |  | Achieved |  |  |  | 0 | 0 | a) 5932 ha (17% of 35,000 ha target) b) Not reporting | a) 387.055 ha b) 0 | a) 395, 154 ha | a) 625, 945 ha | a) 95, 302
Source
Annual reporting to REM/KfW. Mato Grosso reports for Sub programme A (family farming, 4, 232 ha) and sub programme B (sustainable production, 91, 070). in 2025 there has been a more accurate calculation of this. See text from delivery partner: during Phase I, the indicator was calculated based on the total area of the territories benefited, including Indigenous Lands (IL), due to limitations in spatial monitoring. With the change in methodology, the projects began reporting primary data through monitoring spreadsheets. However, since the projects in IL did not provide the corresponding polygons, these areas were not included in the current calculation.
|  | Indicator 18 |  | Baseline | June 16-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-June 24 | June 24-25
|  | Indicator 18: Number of projects led by Indigenous women (Colombia and Mato Grosso) | Planned | [7 empty] | 10 | 10 | 10
|  |  | Achieved | [7 empty] | 8 | 10 | 10
|  | Indicator 19 |  | Baseline | June 16-17 | June 17-18 | June 18-19 | June 19-20 | June 20-21 | June 21-22 | June 22-23 | June 23-June 24 | June 24-25
|  | Number of indigenous projects supported through REM funding | [6 empty] | 10 | 10 | 10 | 10 | 10
[10 empty] | 73 | 105 | 104 | 104
Source
Annual reporting to REM/KfW

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined e.g. DRF, OP, ICF KPIs, MDG indicators
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.