## Logframe - SIP LA
SIP-LA Logical Framework (Logframe) 2018
PROJECT NAME | Sustainable Infrastructure Programme - Latin America
IMPACT 1 | Impact Indicator 1.1 |  | Baseline | 2018 | 2019 | 2020 | 2021 | Target (2022) | Lifetime
Blended finance and TA from UK deliver transformational change to attract long-term private investment in sustainable infrastructure while generating inclusive growth and access to clean energy, thereby contributing to SDG Goal 13: Climate Action. | Extent to which SIP intervention is likely to have a transformational impact (ICF KPI 15). | Planned
Achieved
Source
SIP will annually report on this indicator with a qualitative assessment and on a two-yearly basis of the quantitative assessment of the type and nature of the expected transformational change. It tracks the key criteria that were identified outputs in the Theory of Change, in particular: a) Programme accelerates and enables climate action, specifically: GHG emissions avoided/reduced, increased supply of renewable energy, energy savings, improved access to sustainable transport systems, total number of Renewable Energy and other clean energy projects at a national level. b) Greater UK visibility from the programme improves strength of UK country partnerships, and demonstrates flows of climate finance encouraging increasing climate ambition on climate c) Increased ambition on sustainable infrastructure encourages inclusive growth, creates jobs and access to clean energy d) Enhanced investment by private actors at scale in sustainable infrastructure in target sectors
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline | 2018 | 2019 | 2020 | 2021 | Target (2022) | Lifetime | Assumptions
Support helps break down partner x-government barriers while Institutions and framework strengthened. | Level of integration of climate change in national, sectoral or institutional planning as a result of ICF support (ICF KPI 13). | Planned | [7 empty] | 1. Partner governments positively recognize the contribution of the UK-IDBG SIP towards the achievement of their NDCs. 2. The SIP works with (not against) other donor and UK funding (e.g. TTA programme). 3. The TA is good enough, and targeted at the right country specific barriers. 4. Project specific TA has a knock-on benefit for other developers. 5. That change is sustainable without continued intervention.
Achieved
Source
The SIP Manager will provide qualitative responses based on the following questions - 1. Is there a climate change plan or strategy set out in a dedicated strategy document and/or embedded in the principal planning documents at the level being assessed (e.g. national, sector, ministry)? 2. Has an authoritative body been budgeted and staffed with coordinating climate change planning, and actions? 3. Have specific measures to address climate change (adaptation/mitigation) been identified? 4. Are climate-relevant initiatives routinely screened for climate risks? 5. Is there a formal climate safeguards system in place that integrates climate risk screening, climate risk assessment (where required), climate risk reduction measures (identification, prioritisation, implementation), evaluation and learning into planning?
INPUTS (£) |  |  | Govt (£) | Other (£) | Total (£) |  |  | BEIS SHARE (%)
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline | 2018 | 2019 | 2020 | 2021 | Target (2022) | Lifetime | Assumptions
Increased availability of bankable projects which leads to commercial sustainability of low-carbon market initiatives |  | Planned | [7 empty] | 1. Private sector see benefits and invest in low-carbon sector. 2. That there are projects in all sectors, including transport.
| Total energy generated from clean energy sources in LAC as a result of SIP supported interventions (GWh) (Could be disaggregated by type of energy: solar, wind, waste, other). |  | Planned figures are cumulative. The SIP Manager will annually report on energy generated during the year as well as cumulative energy generated for the review period. Since ICF is only financing part of the SIP projects the benefits (MW) will be calculated as a pro-rata share of the funding. The stipulated baseline is that none of the SIP projects would have been realized during the review period. The data will be disaggregated to distinguish on-grid vs. off-grid, rural vs. urban, by type of technology and by type of funding (debt/equity/PCG, etc.).
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%) | DFID SHARE (%)
OUTCOME 3 | [9 empty] | Assumptions
Climate and social benefits: reduced GHG emissions, increased energy security and energy access | Outcome Indicator 3.1 |  | Baseline | 2018 | 2019 | 2020 | 2021 | Target (2022) | Lifetime
| Greenhouse Gas (GHG) emissions avoided as a result of SIP supported interventions (ICF KPI 6) (CO2eq) (Could be disaggregated by the type of sector or project: transport, energy, waste management, other). | Planned
Achieved
Source
The SIP Manager will annually report on the emission reduction volumes that were generated during the year as well as the cumulative volumes for the review period. In addition the SIP will provide a forecast for the remaining expected emission savings over the lifetime of the SIP projects. The emission reductions are expected to be mostly from the energy supply sector due to changes in power generation. They are calculated as the product of the net energy produced by the SIP projects and the applicable baseline carbon emission factor reflecting the carbon intensity of the electricity generation that is replaced by the SIP projects. The level of emission reductions will be reported on a project level and then aggregated across all SIP projects. The SIP Manager will collect the data from those implementing the project. For Quality Assurance purposes, the data will be substantiated via relevant documents, such as invoices for power generation or meter readings, or site visits. The SIP Manager will collect regular project reports, and prepare regular overviews on the status of the KPI.
| Outcome Indicator 3.2 |  | Baseline | 2018 | 2019 | 2020 | 2021 | Target (2022) | Lifetime
| Net change in energy consumption (MWh). Only Applicable if SIP approves an energy efficiency project. | Planned
Achieved
Source
The indicator will report on the net change in energy consumption (in the form of heat or electricity depending on the intervention) measured in MWh, estimated relative to the assumed business as usual energy consumption. Only to be used in energy efficiency projects: Energy savings is the difference between the energy required to provide the same products or services using energy efficient technology or behaviour as compared to the original technology or behaviour.
| Outcome Indicator 3.3 |  | Baseline | 2018 | 2019 | 2020 | 2021 | Target (2022) | Lifetime
| Volume of waste treated in LAC as a result of SIP supported interventions (tonnes). Only applicable if SIP approves a waste management project. | Planned
Achieved
Source
IDB would report on the total tonnes of waste treated for waste treatment projects. Only applicable if SIP approves a waste management project.
INPUTS (£) |  |  | Govt (£) | Other (£) | Total (£) |  |  | BEIS SHARE (%)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | 2018 | 2019 | 2020 | 2021 | Target (2022) | Lifetime | Assumptions
Context specific (country level/project level) TA is delivered. | Number of high level dialogues conducted in LAC involving IDBG. | Planned | [7 empty] | 1. Partner governments and developers have a demand for technical support. 2. The mandate fits the requirement in partner countries. 3. The Fund is able to meet the tailored demands.
Achieved
Source
The SIP Manager will report annually on the number of country dialogues conducted involving IDBG, the donor and a partner government. Planned figures are cumulative. The information will be disaggregated by partner country and level of funding.
| Output Indicator 1.2 |  | Baseline | 2018 | 2019 | 2020 | 2021 | Target (2022) | Lifetime
| Number of capacity building activities undertaken in LAC by IDBG and its contractors. | Planned
Achieved
Source
The SIP Manager will report annually on the number of capacity building activities undertaken by the IDB and its contractors. Capacity building activities may include, but is not limited to: institutional development plans; management information systems; operation manuals; institutional strengthening; training products; training institutions; capacity building for new project preparation. Planned figures are cumulative. Information will be disaggregated by partner country and level of funding. [Target to be determined by year, on the basis of country dialogue and annual meeting]
| Output Indicator 1.3 |  | Baseline | 2018 | 2019 | 2020 | 2021 | Target (2022) | Lifetime
| Number of technical assistance activities implemented in LAC in relation to policy and regulatory assessment and reform. | Planned
Achieved
Source
The SIP Manager will report annually on the number technical cooperation activities in relation to policy or regulatory assessment and reform. These activities may include but is not limited to: diagnostics and assessments; policies, strategies and plans; legislation; new governance models; pilot interventions; impact evaluations. Planned figures are cumulative. Information will be disaggregated by partner country and level of funding. [Target to be determined by year, on the basis of country dialogue and annual meeting]
| Output Indicator 1.4 |  | Baseline | 2018 | 2019 | 2020 | 2021 | Target (2022) | Lifetime
| Number of studies or activities implemented in LAC supporting private sector investments such as pre-feasibility and/or feasibility, design of financial instruments, project structuring. | Planned
Achieved
Source
The SIP Manager will report annually on the number technical studies or activities supporting private sector investment. These activities may include but is not limited to pilot interventions, developing bankable projects, new financial instruments, project structuring etc. Information will be disaggregated by partner country and level of funding. [Target to be determined by year, on the basis of country dialogue and annual meeting]
IMPACT WEIGHTING (%)
INPUTS (£) |  |  | Govt (£) | Other (£) | Total (£) |  |  | BEIS SHARE (%)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | 2018 | 2019 | 2020 | 2021 | Target (2022) | Lifetime | Assumptions
Capital Investment in sustainable infrastructure project is able to leverage the requisite private finance, increase energy efficiency and create jobs. | Private finance leveraged in investments. | Planned | [7 empty] | 1. Projects recognize IDB as a viable partner. 2. Suitable pool of projects.
Achieved
Source
The SIP Manager will report annually on the amounts that were legally committed in that year as well as cumulative amounts for the review period. Private finance includes finance from IDB, IIC as well as other institutional investors. If other sources of public finance, e.g. other MDB donors, are contributing to a SIP project the benefits (£ in private co-financing) should be calculated as a pro-rata share of the funding. The stipulated baseline is that none of the SIP projects would have been realized during the review period. Data will be disaggregated by origin of finance (Mexico/Colombia/Brazil/Peru), type of finance (equity, debt, grants etc.) and by the supported theme (renewable energy, energy efficiency, transport, etc.). The level of mobilised private finance will be reported on a project level and then aggregated across all SIP projects. The SIP Manager will collect the data from IDB, who will obtain regular updates from those implementing the project. In order to identify which sources of funding can be classified as having been mobilised by ICF funding, the Monitoring and Evaluation Team will assess: a. ICF’s share among the sources of public finance and any rationale for a heavier weighting of certain sources of public finance b. the extent to which each investment of private finance was additional, i.e. would not have been made without the initial funding provided by ICF. c. whether any of the private funding was for non-climate change-related purposes d. how to calculate the volume of private finance for innovative financing instruments, in particular risk mitigation instruments provided by IDB/IIC e. The SIP Manager will collect regular project reports, and prepare regular overviews on the status of the KPI.
| Output Indicator 2.2 |  | Baseline | 2018 | 2019 | 2020 | 2021 | Target (2022) | Lifetime
| Direct jobs created on infrastructure projects. | Planned
Achieved
Source
Planned figures here show cumulative figures and both construction phase (temporary) and operation phase (permanent) jobs. The SIP Manager will report annually on the number of jobs created and the cumulative number for the review period. The stipulated baseline is that none of the SIP projects would have been realized and no such jobs created during the review period. The data will be disaggregated by gender, by skill level, by whether employees have contracts and by whether the job is temporary (construction phase) or permanent (operational phase).
| Output Indicator 2.3 |  | Baseline | 2018 | 2019 | 2020 | 2021 | Target (2022) | Lifetime
| Level of installed capacity of clean energy in LAC generated as result of SIP supported interventions (ICF KPI 7) (MW). | Planned
Achieved
Planned figures are cumulative. The SIP Manager will annually report on capacity installed during the year as well as cumulative installed capacity for the review period. Since ICF is only financing part of the SIP projects the benefits (MW) will be calculated as a pro-rata share of the funding. The stipulated baseline is that none of the SIP projects would have been realized during the review period. The data will be disaggregated to distinguish on-grid vs. off-grid, rural vs. urban, by type of technology and by type of funding (debt/equity/PCG, etc.). As a complementary indicator, the SIP Manager will also collect data on the annual generation of clean energy from these projects. The installed capacity will be reported on the project level and then aggregated across all SIP projects. The SIP Manager will collect the data from those implementing the project. For Quality Assurance purposes, the data will be substantiated via project documents (e.g. specifications of the installed turbines) or site visits by the SIP Manager or qualified third party.
| Output Indicator 2.4 |  | Baseline | 2018 | 2019 | 2020 | 2021 | Target (2022) | Lifetime | Assumptions
| Public finance leveraged in Investment. | Planned
Achieved
The SIP Manager will report annually on the amounts that were legally committed in that year as well as cumulative amounts for the review period. Public finance includes finance from public (i.e. government) sources outside of the UK. This includes finance from other donors and partner governments, UN agencies and multilateral or regional development banks and investment agencies such as CDC or DEG.
IMPACT WEIGHTING (%)
INPUTS (£) |  |  | Govt (£) | Other (£) | Total (£) |  |  | BEIS SHARE (%)