UKCI

Programme Completion Review

© Crown copyright 2023

This publication is licensed under the terms of the Open Government Licence v3.0 except where otherwise stated. To view this licence, visit nationalarchives.gov.uk/doc/open-government-licence/version/3 or write to the Information Policy Team, The National Archives, Kew, London TW9 4DU, or email: psi@nationalarchives.gsi.gov.uk.

Where we have identified any third-party copyright information you will need to obtain permission from the copyright holders concerned.

Any enquiries regarding this publication should be sent to us at:

ODA-Transparency@beis.gov.uk

Contents

Section A: Summary and Overview	4

Description of the programme	4

Summary of progress and supporting narrative for the overall score	5

Progress against recommendations from the last review	6

Major lessons learned, evidence generated, evaluations completed and recommendations	6

Actions following approval of this report	9

Section B: Theory of Change and Outcome Assessment	10

Overall assessment of programme impact, outcomes and sustainability	11

Summary of the programme’s theory of change and results framework	12

Section C: Output Assessment	14

Output 1	14

Output 2	17

Section D: Performance not captured by outputs	19

Section E: Value for Money	19

VfM assessment and performance compared to the original VfM proposition in the business case	19

Section F: Risk	21

Overall Risk Rating	21

Overview of programme risk during the past year and over the life of the programme	21

Section G: Programme Management: Commercial and Financial Performance	24

Performance of partners and DESNZ, notably on commercial and financial issues	24

Section H: Monitoring and Evaluation	25

Programme-level approach to monitoring and evaluation	25

Section A: Summary and Overview

| Title: UK Climate Investments (UKCI) |  |  |
| --- | --- | --- |
| Final Programme Spend £ (full life): £200m | Overall Programme Score: B | Review Date: November 2023 |
| Programme Code: Found here | Start Date: June 2015 | End Date: October 2023 |

| Year | June 2015 - Nov 2016 | Dec 2016 - Nov 2017 | Dec 2017 - Nov 2018 | Dec 2018 - Nov 2019 | Dec 2019 - Nov 2020 | Dec 2020 - Nov 2021 | Final Year Score |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Score | B | B | B | B | B | A | A |
| Risk Rating | Major | Major | Major | Major | Major | Minor | Minor |

| Link to Business Case (and any addendum(s)): | DevTracker Programme GB-GOV-13-ICF-0015-UKCI Documents (fcdo.gov.uk) |
| --- | --- |
| Links to all logframes used during programme lifetime: | DevTracker Programme GB-GOV-13-ICF-0015-UKCI Documents (fcdo.gov.uk) |
| Links to all annual reviews during programme lifetime: | DevTracker Programme GB-GOV-13-ICF-0015-UKCI Documents (fcdo.gov.uk) |

Description of the programme

UK Climate Investments (UKCI) is a joint venture between the Green Investment Group, now part of Macquarie, and the UK Government. The programme was established by the Department for Environment and Climate Change (DECC), which then merged to become the Department for Business, Energy, and Industrial Strategy (BEIS). The programme subsequently moved to control by the Department for Energy Security and Net Zero (DESNZ) upon its creation following the break-up of BEIS in June 2023. This report will reference the responsible department depending on the timeline of the information supplied.

UKCI invests in Renewable Energy (RE) and Energy Efficiency (EE) projects across sub-Saharan Africa and India to demonstrate that low carbon development is possible, replicable at scale, commercially viable and capable of lowering carbon emissions and supporting economic growth. UKCI provides £200m of UK International Climate Finance investments on a commercial basis to get projects off the ground that would not otherwise reach financial close. UKCI delivers development outcomes consistent with the conditions of UK Overseas Development Assistance.

UKCI was originally set up as a three-year joint venture (2015-2018) with the Green Investment Bank (GIB). Following the privatisation of the Green Investment Bank and its acquisition by the Macquarie Group in September 2017, BEIS extended UKCI’s investment period to account for delays incurred during privatisation. A further extension of the programme’s investment phase to November 2021 was agreed in 2020 to allow the realisation of UKCI’s pipeline of expected results. From November 2021 to November 2023 UKCI operated in its commitment phase, where the programme continued to spend against remaining undrawn commitments made during the investment phase. The asset management is expected to continue up to 2040, until which UKCI is expected to hold its investments until their realisation (if earlier), the conclusion of the programme, or until BII determines an alternative course for the fund.

It was expected that from 1 April 2022, UKCI would transfer to FCDO and become an FCDO managed and delivered programme. The expected move was part of a broader move of some of the BEIS ICF programming into FCDO. The decision was based on the Spending Review 2021, delivering on the Prime Minister’s ambition for aligning our international effort, bringing greater coherence and strategic oversight to the UK aid budget. FCDO made the strategic decision to transfer UKCI to BII to improve economy, efficiency, and effective oversight of the mature investment fund. Transfer of control took place on 31 March 2023 before legally transferring in October 2023. This report considers performance of UKCI to March 2023 given thereafter HMG had ceded control.

UKCI consists of a portfolio of the following investments:

| Project | Country | Sector | Size | Description |
| --- | --- | --- | --- | --- |
| Bolt | India | Renewable Energy (PV) | GBP 5m | 50MW utility-scale solar project |
| Lakeside | India | Renewable Energy (PV) | GBP 31m | First unlisted renewable Yield Company (YieldCo) for international investors |
| Dazzle | S. Africa | Renewable Energy (wind, PV) | GBP 21m (+GBP 15m follow-on) | First listed BEE renewable energy YieldCo |
| Apollo | India | Renewable Energy (PV) | GBP 31m | Investment in solar farm company for commercial and industrial clients |
| Oslo | S. Africa | Renewable Energy (wind, hydro) | GBP 14m | Innovative structure enabling BEE investment in two wind and one hydro project |
| Kijani | Kenya | Energy Efficiency | GBP 30m | Energy and water efficient housing (10,000 units) with EDGE building standards |
| Etna2 | S. Africa | Renewable Energy (wind) | GBP 35m | Largest BEE renewable energy platform with minority equity in 5 wind projects |

Summary of progress and supporting narrative for the overall score

Despite scoring two consecutive As in its final years, UKCI’s overall programme score is a B to reflect the historical performance of the programme with five consecutive Bs.

There were notable increases in both private finance mobilisation targets and MWs of clean energy installed during the programme. This is unsurprising in hindsight as the cost of renewables technology declined overall while the commercial interest in investing in the sector increased during the life of the programme. As such conditions evolved – the programme responded by increasing its ambition, ensuring that UKCI remained successfully positioned at the cusp of commercial viability during its durations.

It's important to note that the programme achieved these results in a longer time frame than originally envisaged. Several extensions were granted to the programme partly for reasons outside of the programme’s control. These include the privatisation of the Green Investment Bank and COVID-19 linked disruption. The 2021 annual review also highlighted that the initial 3-year window for investments was relatively short compared to commercial investment funds generally. It is likely that the programme could have fully invested earlier if the investment criteria had been more flexible, but this would have come with trade-offs (this point is explored further in the major lessons learned section below).

Progress against recommendations from the last review

| Recommendation | Progress |
| --- | --- |
| With UKCI’s investment budget now fully committed and the LLP having entered its commitment phase, no new investments will be made and all work on pipeline has ceased. The LLP is already pivoting towards a slower tempo management approach focused on the performance of existing assets, for example with ICs reduced in frequency from monthly to quarterly. It is recommended that FCDO, as the incoming HMG members of the LLP, should review planning and expectations for the remainder of the LLP (set to run until 2040) for their fit with HMG strategy and best use of resources. Target: by November 2022. | Achieved – FCDO made the strategic decision to transfer UKCI to BII to improve economy, efficiency, and oversight; and then liaised with BII on decisions related to the future of UKCI ahead of the programme’s formal transfer in October 2023. |
| BEIS and FCDO should work to complete the evaluation of UKCI and ensure best efforts are made to disseminate and learn from the evaluation report and broader experiences of the programme to the benefit of future programming and funding through private finance delivery channels. Target: Evaluation complete by March 2022. Dissemination plan put in place and underway by November 2022. | Partially Achieved – The review required significant additional and unexpected work and was completed in May 2023. Dissemination of the report and learning activities for HMG need to be planned to follow the PCR. |

Major lessons learned, evidence generated, evaluations completed and recommendations

As detailed in Section H on Monitoring and Evaluation, UKCI notably included an independent evaluation which produced a series of independent reports. A final report was concluded in 2023 which highlighted the following major findings (emphasis from bolding copied from the report):

Additionality

UKCI investments, overall, were relevant in their context and contributed to addressing some key market barriers:

- In India, UKCI contributed to reducing the perceived risk of investing in the C&I sector, and the market has grown considerably since UKCI invested. UKCI also provided cornerstone investment to the first YieldCo investing in renewable energy in the country, which was a very relevant concept in the Indian context.

- In South Africa, UKCI supported the first YieldCo investing exclusively in renewable energy, potentially providing a new exit route for project developers so that they could re-invest the funds in new assets. Given the strong pipeline of new renewable energy assets in the country, this investment is very relevant. UKCI also developed a new instrument to improve BEE parties’ access to finance.

- In Kenya, UKCI invested in a fund that aims to provide a new route for institutional investors to invest in affordable housing. Currently, institutional investors do not have the scale and capacity to invest in green infrastructure. The investment also has the potential to help develop a niche market with high GHG emission reduction potential.

There were three main aspects that enabled UKCI to address market barriers: (a) the fact that investments were analysed as per the additionality and transformational change criteria set in the mandate, (b) UKCI’s capacity to shoulder more risk in operations where the private sector would have been unlikely to invest, and (c) the UKCI/Macquarie team’s expertise to structure complex operations. Some barriers, however, remain, especially for international investors to invest in India and Kenya.

Overall, the evaluation has found that the UKCI investments were additional, as most of the investments would not have proceeded at the same scale and within the same timelines without support from UKCI. UKCI invested in sectors where private investors were reluctant to invest as they were very niche or new, and it was a lever to structure certain operations using innovative structures (e.g., YieldCo). Overall, the additionality criteria were effective at ensuring UKCI was additional; the very detailed investment criteria in the mandate, however, came at the cost of slower deployment of funds than would have been the case with a more flexible mandate.

UKCI helped the invested companies to crowd-in additional (public and private) capital. It did so by supporting innovative financial structures that met investors’ needs, by helping companies in new sectors to grow and become attractive to private investors, and through the positive influence of the UKCI brand, which successfully combined the soft power of the UK Government with Macquarie’s reputation.

Effectiveness

At programming level, UKCI took longer than expected to commit all its funds. This can be partly explained by reasons external to UKCI, but also by reasons linked to the design of the programme. The main reasons external to UKCI are the privatisation of the GIB and the COVID-19 pandemic. The internal reasons are the following:

- Very specific additionality and transformational change criteria: These criteria made it difficult for the UKCI team to source deals that would meet all the requirements. While they were mostly useful to ensure additionality of the investments, they slowed down the speed at which UKCI could commit its funds.

- Low adaptation to changes in context in target geographies: The target geographies were reviewed and expanded after UKCI was launched, but even so, UKCI was delayed partly due to some contextual aspects in its key geographies: In South Africa, the REIPPP was put on hold for several years (2014-2021), limiting investments in renewable energy; and in India, the GBP 30 million threshold for investments per project/firm was relatively low for the market.

- Learning curve: With the move of UKCI to Macquarie, the UKCI team and IC had to get up to speed on concepts that are less familiar to commercial investors (e.g., transformational change), meaning that processes to approve deals took longer at the beginning.

One of the UKCI key aims is to communicate the vision and successes of the pilot and, in so doing, contribute to a positive reputation for UK climate finance among governments, investors and other stakeholders. The evaluation found that there is widespread awareness of the UKCI Pilot in the investor and wider stakeholder community in target geographies, that fund managers and investors are also disseminating information about the deals, and that the partnership between BEIS and Macquarie gives a strong reputation to UKCI.

Transformational Change

UKCI has already achieved, or is likely to achieve, transformational change through some of the investments:

- The new BEE instrument has been replicated by a co-investor and there are early signs that the BEE parties who participated in Oslo and Etna2 and replicating the equity structure with other DFIs.

- The yieldcos are showing that they are useful instruments to attract institutional investors towards green infrastructure in emerging economies. In India, more yieldcos are proliferating, including one in the renewable energy sector. However, it uses a different structure (InvIT, an onshore structure) and UKCI’s contribution to this outcome is limited. In South Africa, stakeholders consulted believe that Dazzle has strong potential to be replicated, and market conditions for replication exist.

- UKCI has contributed to de-risking the C&I sector in India and to leverage capital towards the sector.

On the other hand, there are some objectives that have not been met yet:

- Project Bolt aimed to attract more quality project developers to India. However, as the project developer did not undertake their planned pipeline of projects (for reasons external to UKCI), UKCI has not contributed to attract more developers. This investment is the smallest in the UKCI portfolio (GBP 5 million) and, although it will not achieve the objectives set at the outset, it helped UKCI to start building its own track record and it has provided some learning that can inform future ICF programmes (see chapter 7 on lessons learned).

- The yieldcos have not yet fully demonstrated that they are a viable instrument to upscale renewable energy generation capacity. In Dazzle, Revego acquired their assets from an investor that did not participate in REIPPP Bid Window 5 (although it invested some funds in a renewable energy company in Sub-Saharan Africa); and in Lakeside, Fortum reinvested the proceeds from the sale in new renewable energy infrastructure, but when it became operational it sold it to another investor, instead of the yieldco.

GESI

Although there was not a GESI a strategy from the outset in UKCI, over time, GESI gained more importance in the UK Government and across policies and programmes.

Four of the UKCI investments directly sought to achieve GESI objectives: Oslo, Etna2 and (to a lesser extent) Dazzle, as they support BEE parties (a disadvantaged group) to access funding, and Kijani, as it invests in green affordable housing. In addition to this, Macquarie promoted the development of diversity and inclusion (D&I) policies among their invested companies, including the UKCI portfolio. All companies have initiatives or policies to promote D&I, such as supporting broader diversity at board level focusing on the promotion of the diversity attributes of gender, race, culture, age, field of knowledge (Revego), and bringing in more women in the workforce (non-EPC roles) (Apollo).

Overall, the invested companies sought objectives in terms of poverty reduction and equity that went beyond climate change mitigation. The GESI outcomes at the underlying asset level are noticeable and, in some cases, very impactful (although UKCI’s contribution is minor). Some of them conducted specific activities to this end, including, for instance: infrastructure projects to improve access to education, investments in employment and training opportunities, and initiatives to improve education and health in the local communities where the projects operate. UKCI’s invested companies also reported having helped the local communities during COVID-19.

The evaluation has not found any negative unintended effects from UKCI activity; however, there may have been missing opportunities of further supporting GESI outcomes. As GESI was not fully monitored from the beginning, it has not been possible in this evaluation to identify such opportunities.

Efficiency

Overall, the evaluation found that the LLP model has worked well: There was a perception of a shared understanding of the investment mandate within both BEIS and Macquarie and the facilitation of constructive discussions during Board and Committee meetings. The model of using a commercial investor to deliver UKCI worked well due to a number of factors: (a) The UKCI team was thought to be benefiting from the resources available at Macquarie, providing breadth and depth of management experience; (b) Macquarie had a good understanding of government requirements and risk appetite; (c) its knowledge of the target geographies (with physical presence in some target countries); (d) Macquarie’s strong reputation in infrastructure investment and asset management; (e) a shared understanding of the mandate and constructive communication between Macquarie and BEIS.

The challenges mentioned by stakeholders, on the other hand, included: (a) Lack of flexibility in the mandate; (b) negotiations being lengthier than what is normal in the market; and (c) Macquarie’s lack of resources and expertise to monitor ODA compliance.

Actions following approval of this report

The key actions following approval of the PCR relate to the socialisation of the learnings and findings of the independent evaluations of UKCI (as detailed in Section H on Monitoring and Evaluation). These will benefit specialists across HMG who are working on investment programming – particularly as it relates to UKCI’s geographies and sectors.

Section B: Theory of Change and Outcome Assessment

|  | Starting point | Final result |
| --- | --- | --- |
| Budget | £200m in the investment fund + £2m for independent evaluations | £200m + £653k for independent evaluations |
| Timeframe | 3 years | ~8.5 years |
| Outcomes | The business case set outcomes as: - Strong climate and development outcomes secured from projects; - GIB investments have a demonstration effect, signalling the attractiveness of the sector to a wider market; - GIBI is established as a vehicle that efficiently identifies, assesses and places financially viable climate investments in priority countries; - GIB’s credibility as world like climate focussed development institution enhanced. | The indicator changed to the following: UKCI demonstrates commercial viability and strengthens RE and EE markets in target geographies, leading to climate change mitigation and wider developmental impacts. The indicator consisted of three sub-indicators: Gross change in GHG emissions – million tonnes of GHG reduced or avoided by projects supported by UKCI investments (MtCO2e, cumulative) – 42.6-52.1 expected lifetime Gross level of installed capacity of clean energy supported by UKCI investments (MW, cumulative) – 923-1129 expected lifetime Weighted average (expected) internal rate of return for UKCI investments in local currency (cumulative) – 12% for local currency returns (8% for GBP) Outcomes as they relate to GIB became redundant when the GIB was privatised and acquired by Macquarie. There is evidence that UKCI projects have demonstrated commercial viability and strengthened RE markets (Apollo, Oslo, and Etna2) or show early promise (Dazzle and Kijani (for EE)). Lakeside and Bolt have not successfully contributed to the outcome. Climate change mitigation and wider developmental impacts were achieved. |

Overall assessment of programme impact, outcomes and sustainability

The logframe outcomes and impacts were achieved in 8.5 years against an initial expectation of 3 years for the programme. The budget did not change during the programme. The reasons for this extension are discussed elsewhere in this document including in section A.

Of the subcomponents in the outcome indicator, both gross change in GHG emissions and gross level of clean energy capacity installed outperformed targets (64m tC02e cumulative achieved vs. 42.6-52.1 targeted and 1,403MW cumulative achieved vs. 923-1129 targeted). The weighted average rate of return at ~11.5% only slightly underperforms the 12% target.

There is evidence of demonstration of commercial viability, strengthening of RE markets, and replication as described in Section A’s ‘Major Lessons Learned’. These findings are for most but not all of UKCI’s investments.

It is therefore judged as reasonable that UKCI has achieved its outcome indicator: “UKCI demonstrates commercial viability and strengthens RE and EE markets in target geographies, leading to climate change mitigation and wider developmental impacts.”

The final outcome indicator reflects those elements of the outcomes expected in the business case which remained relevant following GIB’s privation. Those are:

- Strong climate and development outcomes secured from projects;

- GIB investments have a demonstration effect, signalling the attractiveness of the sector to a wider market;

The programme’s impact indicator is “UKCI contributes to replication at scale of innovative low-carbon investment models.” It would be impossible to determine the true extent of UKCI’s contribution to any current or future innovative low-carbon investment models in its target geographies. Nevertheless, as outlines in section A’s ‘Major Lessons Learned’ there is evidence of replication. As a result, we can tentatively assert that UKCI may achieve its intended impact.

While the outcome indicators were largely achieved – output indicators related to private and public finance mobilised slightly underperformed. Market conditions negatively impacted UKCI’s performance in these areas as outlined in the following sections on outputs.

Given the trajectory of the programme with results achieved in line with expectations in outer years, it seems reasonable to have seen an uptick in annual review scores from B during the investment period to A following its completion.

Summary of the programme’s theory of change and results framework

UKCI is expected to demonstrate commercial viability and strengthen renewable energy and energy efficiency markets in target geographies, leading to climate change mitigation and wider development impacts. Overall, the evidence from UKCI provides growing support for the steps included in the Theory of Change (ToC) leading to the stated outcomes and impacts. However additional flexibility in the programme design may have allowed UCKI to achieve a greater impact. In practice the original business case provided a narrow and highly defined scope for how and where the programme could invest, which was rapidly superseded by events in desired markets and proved unworkable. This suggests a more fluid ToC may be useful for future programming which needs to be responsive to market dynamics.

UKCI’s ToC underwent a review conducted by IPSOS Mori in April 2019 to validate or update the mechanisms expected to lead to delivery of the programme's desired impact. The ToC was largely validated, and most changes resulted in simplification. No new causal mechanisms expected to achieve transformational change were considered necessary to introduce. UKCI logframe outcome indicators either directly monitor examples of replication or have a clear rationale for contributing to replication and transformational effects through their achievement. There have been no changes to UKCI’s theory of change since those reported in the previous review.

Figure 1: UKCI Theory of Change

The results framework is underpinned by the logical framework for UKCI and its metrics at the output, outcome and impact levels. At each level in turn these metrics are:

- Output 1 – New finance Directly Mobilised into clean energy projects

  - Gross volume of private finance committed to UKCI investments by other financiers (£m, cumulative)

  - Gross volume of public finance committed to UKCI investments by other financiers (£m, cumulative)

- Output 2 – Innovative Renewable Energy and Energy Efficiency measures are installed in priority markets

  - Number of innovative low-carbon energy projects in India and South Africa (cumulative)

  - Number of innovative low-carbon energy projects outside of India and South Africa (cumulative)

  - Total level of clean energy capacity UKCI investments are committed to install (MW, cumulative)

  - Total lifetime GHG emissions expected to be reduced or avoided directly by UKCI’s committed investments (Million tCO2e, cumulative)

- Outcome – UKCI demonstrates commercial viability and strengthens RE and EE markets in target geographies, leading to climate change mitigation and wider developmental impacts.

  - Gross Change in Greenhouse Gas Emissions – million tonnes of GHG reduced or avoided by projects built by UKCI investments (MtCO2e, cumulative).

  - Gross level of installed capacity of clean energy from UKCI investments (MW, cumulative).

  - Weighted average (expected) internal rate of return for UKCI investments in GBP (cumulative).

- Impact – UKCI contributes to replication at scale of innovative low-carbon investment models.

  - Extent to which UKCI contributes to replication at scale of innovative low-carbon investment models.

During the life of the programme, the decision to invest in YieldCos made effective measurement of the benefits attributable to UKCI more complex. This is because UKCI was originally expected to invest primarily in companies creating new productive assets or improving energy efficiency. YieldCos are companies formed to own already operating assets. They are beneficial to the development of renewable energy production as they allow developers to off-load operational assets and thus free up capital to invest in further productive assets. Performance indicators had to be updated to take into account UKCI’s investments in YieldCos and to reflect the positive contributions that these new structures could bring to target geographies.

Section C: Output Assessment

Output 1

| Output Title | New finance directly mobilised into clean energy projects |  |  |
| --- | --- | --- | --- |
| Output Score | B |  |  |
| Impact Weighting (%) | 50% | Revised since last AR? | No |
| Risk Rating | Major | Revised since last AR? | No |

| Output Indicator | Starting Target | Final Logframe Target | Final Result Achieved (March 2023) |
| --- | --- | --- | --- |
| 1.1 Gross volume of private finance committed to UKCI investments by other financiers (£m, cumulative). | 1:2.02 leverage ratio – originally an outcome – implies £360m | 1,311 – 1,603 (Gross, Cumulative) | Not achieved (moderately did not meet expectation) 994-1,215 (Gross, Cumulative) Project; Private finance committed (£m). Bolt; 33. Lakeside; 101. Apollo; 233. Kijani; 23. Etna 2; 592. Oslo; 205. Dazzle; 52. Total (Cumul.); 1,105. |
| 1.2 Gross volume of public finance committed to UKCI investments by other financiers (£m, cumulative) | 1:0.39 leverage ratio – originally an outcome – implies £69.6m | 64-78 (Gross, Cumulative) | Not achieved (moderately did not meet expectation) 49.7-60.8 (Gross, Cumulative) Project; Public finance committed (£m). Etna 2; 34. Kijani; 21. Total (Cumul.); 55. |

Output summary and supporting narrative for the score

Private finance and public finance mobilisation figures moderately did not meet expectations. Investments faced varying market conditions during UKCI’s lifetime. Market conditions for the target markets worsened because of covid’s negative economic shock, periods of heightened inflation, and emerging market currency devaluation. International capital tended to become risk averse as a result leading to more difficult fundraising conditions for UKCI’s investees. As a result, MDB financing became more important in the financing mix than initially expected. It can be concluded therefore that macroeconomic and country risk were primarily responsible for missed targets as opposed to risks to projects and assets.

As the goal of the programme was to overcome market barriers and demonstrate commercial viability – greater weight is placed on the private finance result than the public finance mobilisation scores. The significantly higher private finance mobilisation (relative to public financing) figures reflect the successful positioning of UKCI – which entered investments on commercial terms under clear additionality criteria. UKCI was effectively positioned at the point at which investments were on the cusp of commercial viability as a means of shifting the dial towards commercial viability for similar deals in the future. A relatively larger public finance mobilisation figure would arguably suggest that UKCI had failed on this objective.

We can go beyond the headline figures using the findings of the final independent review of UKCI. UKCI contributed to crowding in investors of several types: commercial banks (Bolt, Dazzle), institutional investors (Dazzle, Kijani), private equity funds (Apollo, Lakeside), and public DFIs of multilateral funds (Kijani, Apollo, Etna2). Evidence related to the motivations for these investors putting their money forward is anecdotal and therefore implications should be considered tentative. The anecdotal evidence available suggests that the following factors contributed to leveraging additional finance:

- Innovative financial structures (notably yieldco structures that enabled an institutional investors to invest in renewable energy in South Africa);

- Sustainable investments where UKCI taking on more risk than private investors allowed growth which unlocked private investment in subsequent rounds;

- Positive influence of UK and Macquarie support which brought positive soft power benefits and the reputation of a commercial investor.

Lessons learned through this output, and recommendations for future programming

While we cannot say with confidence that UKCI will achieve its transformational change objectives – there is anecdotal evidence of mixed results and headline output figures reflect good performance.

It would be impossible to fully ascertain the impact of the various changes UKCI faced (significant changes at the delivery partner and COVID-19 in particular) on its ability to meet its objectives against expectations at the start. It is reasonable, however, for those working on similar programmes in the future to expect bumps along the road.

We can draw on the findings of the Ipsos Mori final evaluation of UKCI to consider the internal reasons identified for the slower than expected achievement of results:

- Very specific additionality and transformational change criteria: These criteria made it difficult for the UKCI team to source deals that would meet all the requirements. While they were mostly useful to ensure additionality of the investments, they slowed down the speed at which UKCI could commit its funds.

- Low adaptation to changes in context in target geographies: The target geographies were reviewed and expanded after UKCI was launched, but even so, UKCI was delayed partly due to some contextual aspects in its key geographies: In South Africa, the REIPPP was put on hold for several years (2014-2021), limiting investments in renewable energy; and in India, the GBP 30 million threshold for investments per project/firm was relatively low for the market.

- Learning curve: With the move of UKCI to Macquarie, the UKCI team and IC had to get up to speed on concepts that are less familiar to commercial investors (e.g., transformational change), meaning that processes to approve deals took longer at the beginning.

We expect that future programming in related areas would benefit from explicitly considering trade-offs from responding to the above findings. Arguably it is a better use of public funds to ensure additionality and transformational change impacts are achieved and ideally public funds would have greater patience in the timing of delivery to achieve these objectives. There is however a cost in doing so – both in terms of fees paid to delivery partners and greater use of public oversight resources. Future programmes should take into account the costs and benefits of more flexible policies on additionality, transformational change, and geography in reducing time to investment and overhead costs, against the potential decreases in impact of the programme.

To disseminate these findings, we recommend the publication of the Ipsos Mori final report on DevTracker; socialising the report internally and with relevant external partners; and a series of internal workshops outlining the findings of the Ipsos Mori final report and this PCR.

Output 2

| Output Title | Innovative Renewable Energy and Energy Efficiency measures are installed in priority markets. |  |  |
| --- | --- | --- | --- |
| Output Score | A+ |  |  |
| Impact Weighting (%) | 50% | Revised since last AR? | No |
| Risk Rating | Major | Revised since last AR? | No |

| Output Indicator | Starting Target | Final Logframe Target | Final Result Achieved (March 2023) |
| --- | --- | --- | --- |
| 2.1 Number of innovative low-carbon energy projects in India and South Africa (cumulative). | 10 | 6 | Achieved (met expectation) 6 |
| 2.2 Number of innovative low-carbon energy projects outside of India and South Africa (cumulative). | N/A | 1 | Achieved (met expectation) 1 |
| 2.3 Total level of clean energy capacity UKCI investments are committed to install (MW, Cumulative) | 333 | 1,026 – 1,129 | Achieved (moderately exceeded expectations) 1,403 Project; Total clean energy capacity committed to install (MW, cumul.). Bolt; 50. Apollo; 402. Oslo; 251. Etna2; 700. Total (Cumul.); 1,403. |
| 2.4 Total lifetime GHG emissions expected to be reduced or avoided directly by UKCI's committed investments (Million tCO2e, cumulative) | 31.9 MTCO2e (By 2050) – originally an outcome | 42.6-52.1 | Achieved (moderately exceeded expectations) 57.2-69.9 Project; Lifetime GHG avoided (Million tCO2e). Bolt; 2. Apollo; 11. Oslo; 13. Etna2; 38. Kijani; 0.05. Total (Cumul.); 64. |

Output summary and supporting narrative for the score

Over the course of the programme, decisions were made to decrease the total number of investments and to ensure a spread of investments beyond India and South Africa. The original set of geographies for UKCI consisted of India, South Africa, Kenya, Tanzania and Rwanda. In practice, investments were concentrated in India and South Africa with only one in another geography - Kenya.

The Ipsos Mori interim report (2018) found that UKCI was operating in markets with high levels of attractiveness and thus competition. A question was raised as to decisions to broaden the set of target geographies or to focus on novel technologies.

BEIS did broaden the geographic mandate but this failed to bear fruit and see investments outside of the original five target countries of the programme.

Additionality criteria did allow however for a move towards more innovative technologies and business models – as evidenced by the support to YieldCos.

It is important to note that the overall cost of renewable energy and energy efficiency technologies significantly declined over UKCI’s lifetime. This cost decrease can help to explain the uptick in targets related to energy capacity and GHG reductions from the original expectations.

Lessons learned through this output, and recommendations for future programming

In designing future programming, it will be important to remember that there are trade-offs in several areas.

Countries with more attractive investment climates will likely be easier for interventions like UKCI to be implemented and to attract private capital. This is because UKCI operates on commercial terms alongside other investors – and this is more likely in countries with good investment climates. As such, it is important to ensure that additionality and innovation criteria (and related oversight) are sufficiently robust to ensure investments are in fact at the cusp of commercial viability.

At the same time, if future programming wishes to have a wider geographic impact then the additionality and innovation criteria (and related oversight mechanisms) need to be responsive to local contexts. What is innovative and additional in one economy may already be fully established as commercially viable in another.

Programmes in climate should also be mindful of trends in reductions of costs of climate technology and project forward expected future movements to determine climate impacts in a more reliable manner.

Dissemination of these findings will follow the same path as for Output 1 described above.

Section D: Performance not captured by outputs

UKCI’s performance cannot be wholly captured by the outputs recorded in this report; considering the following metrics provides a more robust understanding of the programme: addressing market barriers, additionality, and support to HMG’s wider climate finance work.

Independent analysis of UKCI has found that UKCI contributed to addressing some key market barriers as a result of i) investment consideration against additionality and transformational change criteria, ii) UKCI’s ability to take on risk, and iii) the team’s expertise in structuring complex transactions. Notable market barriers addressed include:

- India: reduction of perceived risk of investing in the C&I sector; investment in the first yieldco in India;

- South Africa: investing in the first yieldco in South Africa; improvement of Black Economic Empowerment parties’ access to finance;

- Kenya: new route for institutional investors to invest in green infrastructure.

Investments needed to demonstrate additionality as well as innovation as recorded in the output. Independent analysis found that most investments made would not have proceeded at the size or against the timelines achieved without UKCI support. Investments were overall niche or new areas where private investors were reluctant to invest. Deals were considered against a set of additionality criteria as follows:

- Other investors were not crowded out;

- Project had not yet reached commercial operations (excepting yieldcos);

- Investments were on arm’s length commercial terms; and

- Investments contributed to a reduction of poverty and were classifiable as ODA.

UKCI actively supported and engaged in HMG’s wider work in climate finance notably in India and South Africa. The programme was in close contact with High Commission teams in both countries and had a mutually beneficial relationship resulting from this contact. In India, UKCI notably engaged with the International Solar Alliance and the UK-India Financial Partnership. Macquarie also took on a leading role in the inaugural Climate Finance Leadership Initiative (CFLI) country pilot in India which convenes leading companies to mobilize and scale private capital for climate solutions.

Section E: Value for Money

VfM assessment and performance compared to the original VfM proposition in the business case

Economy

UKCI’s business case predated commercial negotiations for the fund. In considering economy factors in VfM the business case therefore established a range of comparable costs for managing costs and hurdle rates / carry (a share of the returns on investments to the fund manager). The costs negotiated for UKCI were within the ranges established by this comparables analysis and therefore were considered to represent good value for money. This was achieved in the context of upward pressure on costs due to set up costs for the GIB in entering new markets via the fund.

The terms remained in place when the GIB was privatised, and Macquarie took control of UKCI.

Efficiency

At the writing of the business case, GIB had no track record in investing outside of the UK or against ICF transformational change criteria. The business case highlighted GIB’s early successes but flagged that the processes established for UK-based investments would need to be amended. To incentivise cost control by GIB, the business plan established that the target hurdle rate would be calculated on profits net of management costs.

A report into UKCI following its investment period by Ipsos Mori found that overall the LLP model of UKCI worked well. There was a shared understanding of the investment mandate and governance mechanisms functioned well. While delivery by Macquarie was not envisaged in the original business case; this delivery mechanism utilising a commercial investor was found to work well due to the broader resources of the financial services firm; solid understanding by the fund manager of infrastructure investment, asset management, operating contexts and target geographies; and a good understanding by the fund manager of how to work with HMG. At the same time, the mandate’s inflexibility and Macquarie’s learning curve on ODA compliance were challenges.

Effectiveness

UKCI’s business case determined potential effectiveness of the UKCI pilot against the results for an expected portfolio of investments. In practice it was unknown if the portfolio would change over time as market conditions evolved and projects advanced. The model assumed 2% management fees and 100% attribution for investments made on the basis that UKCI was designed to invest only in projects that without UKCI money would not be undertaken.

Key results from the model included:

- Total leverage of other finance was £1:£2.4 (0.39 for public and 2.02 for private); seen as favourable against GIB market analysis (established range of 4-6.7) and the ICF portfolio at the time (£1:£0.2 to £1:£10).

- Cost per tonne of CO2e was £5.65/tCO2e; seen as favourable against the DECC ICF portfolio at the time (£4 - £16 with spend weighted average attributed cost per tonne of £6.4)

- Cost per MW installed was £495,000, seen as well within the expected range of unit costs.

A report into UKCI following its investment period by Ipsos Mori highlighted that effectiveness was impacted by external factors (notably the privatisation of GIB and the COVID-19 pandemic) and the following internal factors:

- Very specific additionality and transformational change criteria which made deal sourcing difficult;

- Low adaptation to changes in context in target geographies, which were reviewed and expanded after launch and which saw contextual changes which delayed and changed pipelines in unexpected ways;

- Learning curve given the shift from GIB to Macquarie and thus the transfer of responsibility to a new team.

Equity

Considerations related to equity were not analysed as part of the VfM analysis in the original business case. It is understood that such consideration was not required by DECC at the time.

A report into UKCI following its investment period by Ipsos Mori acknowledged the lack of a GESI strategy or systematic approach to mainstreaming GESI in UKCI and went on to assess the contributions made albeit in a consequential rather than sought after way.

- Four of the UKCI investments directly sought to achieve GESI objectives: Oslo, Etna2 and (to a lesser extent) Dazzle, as they support Black Economic Empowerment (BEE) parties in South Africa to access funding, and Kijani, as it invests in green affordable housing in a country where around half of urban households live in slums.

- Macquarie promoted the development of diversity and inclusion (D&I) policies among their invested companies, including the UKCI portfolio. All companies have initiatives or policies to promote D&I, such as supporting broader diversity at board level focusing on the promotion of the diversity attributes of gender, race, culture, age, field of knowledge (Revego), and bringing in more women in the workforce (non-EPC roles) (Apollo).

- Invested companies undertook ESG activities which provided positive social benefit beyond climate change mitigation.

While these positive benefits accrued, given there was no formal strategy in place UKCI cannot claim accountability. Mainstreaming GESI in the programme could have ensured better returns.

The policy decision underpinning FCDO’s desire to transfer UKCI to management by BII was underpinned by views that such a move would improve the programme’s economy, efficiency and effectiveness in consideration of its maturity. BII has systems and procedures in place for managing assets similar to those held by UKCI and therefore was seen as better able to manage the assets as part of their normal course of business than HMG. As the investment period had ended before the decision to transfer to BII was made, there was no further scope to influence investment strategies to meet HMG policy objectives. Continued management within HMG would necessitate prolonging oversight and financial management, the latter of which had historically proved cumbersome within HMG systems.

Section F: Risk

Overall Risk Rating

Major from June 2015 to November 2020. Minor from December 2020.

Overview of programme risk during the past year and over the life of the programme

The following description of risks reflects those present at the time of the signing of the Transfer Agreement between BEIS, BII and FCDO which saw economic and financial risk transfer to BII. Due to procedural issues, legal transfer could not occur until October 2023. Nevertheless with the mechanisms underpinning the Transfer Agreement UKCI risks transferred effectively to BII as of 31 March 2023.

| Risk Description | Mitigation Strategy | Residual Risk Rating |
| --- | --- | --- |
| Economic: Investment Risk UKCI has fully committed the entire programme budget by November 2021. However There is an inherent risk that the projects committed to fails to utilise the programmes cash resources (200m investment). Through project failure or missing the November 2023 deadline. Resulting in BEIS underspend. | The programme team cannot reduce the likelihood of realising this risk. The Programme team will receive regular cash management updates from Macquarie, increasing the sight and time BEIS corporate have to meet or distribute the programmes cash spend, in line with ODA and SR spending targets. | Minor |
| Environmental/Developmental: Delivering transformational change (Theory of Change) Headline results are not delivered due to internal project factors. UKCI’s investments do not deliver intended results (as laid out in the investment cases at the IC) | All commitments have been made so minimal opportunities for additional developmental gains can be made. However, Macquarie have a place on various Boards and Committees of downstream projects – they can exert influence to ensure the intended developmental/environmental outcomes are secured. | Moderate |
| Political (and Macro-economic risks): Political and economic risks, manifesting through market conditions, could have a negative impact on the ability of UKCI’s investments to deliver against targets for construction and operation, resulting in incomplete project delivery and therefore impact UKCI results and BEIS departmental spending targets. | UKCI’s output results are largely achieved through the programme making investment commitments. As UKCI is now fully committed, the risk to output results is largely minimal – although outcome and impact results could be affected. UKCI is legally obligated to meet investment’s cash requirements as required by downstream projects. Monitoring can reduce impact on BEIS results and departmental spend, through: - Macquarie routinely monitors market and wider contextual conditions and works with BEIS to adapt its strategy accordingly. - BEIS routinely receives political economy updates from FCDO colleagues in-country to corroborate with Macquarie's market intelligence | Minor |
| Financial (Spend forecasting): Inaccurate financial forecasting by Macquarie means there is a risk that BEIS is unable to disburse funds between the months of January and March of every year when required. This could affect deal completion and have negative financial and reputational impacts for UKCI programme and BEIS ICF delivery. | BEIS frequently monitors the status of expected disbursements through bi-monthly calls with Macquarie whilst working closely with BEIS Finance to ensure disbursement needs are being accounted for in monthly BEIS Cash Management forecasts. | Major |
| Economic: Financial Returns/Sustainability: Investments may not generate enough returns during certain periods within the lifetime of the LLP to pay for Macquarie’s ongoing asset management fees and operation costs. | - UKCI IC will monitor asset performance to ensure commercial viability of overall portfolio including possible asset sales that would generate sufficient revenue to cover operations. - Returns from to 2025 may only partially cover UKCI operating costs due to time needed for investments to mature/financial underperformance. Contingency buffer (worst-case £12m) from uncommitted funds or Macquarie or BEIS loan could be put aside to manage this shortfall. | Minor |
| Environmental/Development: Downstream projects of our investments, due to poorly managed due diligence or delivery chain risks miss the minimum compliance to 'Do no harm' for people or environment | Macquarie to utilise investment frameworks that screen projects (IFC impact principles, MQ internal risk management systems - utilising the wider MQ group) and delivery chain partners that could increase this risk for people or environment. MQ to communicate to BEIS on any conflicts with the 'do no harm' principles, regularly at board meetings or in ad hoc catch-ups. | Moderate |

Overall the risk rating profile of UKCI was stable in its final year and within tolerance thresholds. The stability of the risk profile reflects the maturity of the programme which had fully committed its funds.

UKCI overall had a Major risk rating throughout its commitment phase before moving to minor risk after investments had been agreed. This shift is understandable in the context of an investment portfolio where delivery of the objectives set depends on the successful entering into a series of appropriate investments against countervailing pressures of market change and evolving external context. Investing is inherently uncertain and influenced significantly by factors beyond the control of the programme or the delivery partner.

The two reported drivers for the shift in the 2021 Annual Review were:

- The UKCI programme fully committing the £200m budget so risks associated with meeting the deadline for new commitments had subsided.

- Risks associated with BEIS meeting the funding requests for the projects (the cash spend) reducing. The spending period lasted two years to November 2023 for most assets, with Project Kijani extending out to 2026.

UKCI’s risk profile was within BEIS’ risk appetite throughout the programme. As a programme representing Major risk until the commitment phase had ended, UKCI received close oversight by the programme team and by BEIS ICF senior management. Financial management of the programme was difficult as a result of the mismatch between ODA budgeting practice in the UK and the uncertainty of investment timelines in commercial transactions which are heavily influenced by external factors and thus difficult to control. Consideration as to the means to mitigate uncertainty and volatility of ODA spend on future investment programmes undertaken by the UK is necessary to minimise such risk in the future.

Section G: Programme Management: Commercial and Financial Performance

Performance of partners and DESNZ, notably on commercial and financial issues

Items related to accounting, reporting, financial statements, anti-bribery, anti-corruption, compliance with regulations, compliance with economic sanctions, governance and investment selection were effectively contracted to Macquarie under the terms of the LLP Agreement for UKCI.

It was the responsibility of the delivery partner under the LLP Agreement to ensure accounting, reporting and financial statements (included their audit) is accurate, regular, and responds to regulatory requirements. Accounts were required on an annual basis at minimum.

The delivery partner was also responsible for prompt notifications of any incidents which could have material adverse effect on any investment made by UKCI. Notification was also required of any material allegation of illegal activities or corruption.

Meetings of the Board of Directors occurred quarterly at minimum and provided significant useful information to HMG to facilitate its oversight of the programme. HMG had the right to appoint up to two of the four members of the Board of Directors including the Chairperson. Board meetings include reporting and discussions related to the strategic direction of the fund, risk, finance, and governance.

HMG as member also had the right to call for a meeting for any purpose as it related to UKCI.

Investments were subject to conformity with the investment mandate and approved by the Investment Committee on which HMG was represented. The Investment Committee was responsible also for approving divestments and other relevant items related to the financing arranged by UKCI. Members of the Board of Directors had the right to be informed promptly of Investment Committee decisions and also to veto such decisions. As a result, HMG was provided significant information relating to the investment and financing activities undertaken by UKCI.

Delivery partners have provided good service against these obligations throughout the term of UKCI.

Financial management of UKCI proved difficult for HMG as capital calls are made with ten days’ notice and proved hard to predict due to the complexity and commercial nature of the transactions undertaken. ODA budgeting procedures within HMG made managing HMG financing of UKCI onerous, in particular where payments fell towards the end of the ODA year (aligned with the calendar year) and risked slipping into the final quarter of the UK fiscal year. Macquarie was proactive in supporting HMG in managing related risks through regular and timely updating on spend forecasts. It would be unreasonable to expect any further mitigation of these administrative issues given that payments to UKCI were tied closely to commercial processes over which UKCI had limited control.

| Date of last narrative financial report | 31 March 2023 |
| --- | --- |
| Date of last audited annual statement | 31 March 2023 |

Section H: Monitoring and Evaluation

Programme-level approach to monitoring and evaluation

Monitoring and evaluation of UKCI notably included an independent evaluation including series of independent reports. Ipsos UK was commissioned by BEIS in December 2015 for these purposes. The evaluation was divided into several phases:

- 2016-2018 – scoping research

- 2019 – assessed UKCI processes

- 2020 – evaluation questions re-defined and re-prioritised given changes in the UKCI pilot

- 2020-2022 – assessed the outcomes and impacts of UKCI investments

- 2023 – final evaluation report

Two reports have been published on DevTracker – the UKCI Evaluation Scoping Report and the UKCI 2018 Interim Report - for public access. Evaluation findings were disseminated and socialised internally within HMG.

Each stage produced recommendations and findings which were considered and integrated into the programme as appropriate. 

A theory-based approach informed the analysis and drew on UKCI’s Theory of Change, notably using contribution analysis to assess transformational change. A total of six case studies were conducted. Data collection methods included interviews with a broad range of stakeholders both in policy and investments; observations of governance meetings; analysis of monitoring data; portfolio and investment analysis; comparables analysis of similar funds; market analysis and benchmarking; a site visit to South Africa; and context reviews for target geographies.

GESI analysis was not conducted at the level of monitoring data but was included in the Ipsos UK evaluations. As stated previously, GESI considerations were not integrated into the programme’s design.

Agreements signed in March 2023 necessitated BII approval for material decisions. Legal transfer did not take place until later in the year due to logistical reasons.

The original business case assumed £178.4m of capital investments over the life of the fund. The implied cumulative nominal values are derived using this figure against the leverage ratio targeted in the first log frame.

For example the Kenyan shilling moved from ~100 KES to 1 USD in 2020 to ~132 to 1 in March 2023 a depreciation of 32%. The rand moved from ~15 to 1 to ~18 to 1 over the same period – a depreciation of 20%.